## DDR#318
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 318
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-11-04
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO/ HAMZA / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4585 / 4332.46 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 101.13
RIG REP. (TP): |  | TARIQ .M. BUTT / KHALID .M. JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4592 / 4336.87 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 23
2018-11-03 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | BIT NO. |  | 22RR1 | 22RR1 | BHA No. |  |  | 49 | IN (M) |  | 4543 |  | OUT (M) |  |  | STRING (BBL) | 207
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 4585 |  | SIZE (IN) |  | 6 | 6 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 618.4
DEPTH, MD (M) | 4573 | 4585 | TVD @ 00:00HR (M) |  | 4332.46 |  | MANUFACTURER |  | SMITH | SMITH | 6'' PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 |  |  | PITS (BBL) | 687
MW IN (SG) | 1.7 | 1.7 | DAILY PROGRESS (M) |  | 23 |  | TYPE |  | MDSi613WBPX | MDSi613WBPX | BIT SUB |  |  | 4.75 | 2 |  | 3 1/2 REG |  | 1.07 | 0.079643 |  | ACT. SYS (BBL) | 1512.4
MW OUT (SG) | 1.7 | 1.75 | INST. ROP (M/HR) |  | 1.9 |  | SERIAL NO. |  | JN5339 | JN5339 | ST. STAB |  |  | 5.875 | 2.25 |  | 3 1/2 IF |  | 1.77 | 0.13175 |  | RESV. SYS (BBL) | 425
ECD (SG) | 1.7572 | 1.8319 | AVG. ROP (M/HR) |  | 1.54 |  | IADC CODE |  |  |  | 1X DC |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 9.2 | 0.68478 |  | KILL MUD (BBL) | 1050
FL TEMP. °F | 122 | 118 | AVG. WOB (TON) |  | 1-6 |  | NOZZLES (1/32") |  | 6 X 13 | 6 X 13 | ST. STAB |  |  | 5.875 | 2.25 |  | 3 1/2 IF |  | 1.91 | 0.14217 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 51 | 54 | AVG. RPM SURFACE |  | 80 |  | DEPTH IN (M) |  | 4543 | 4543 | 11 X DC's |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 102.08 | 7.5981 |  | TOTAL | 2987.4
PV | 27 | 28 | AVG. RPM DOWNHOLE |  | 80 |  | DEPTH OUT (M) |  |  |  | 3 X HWDP |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 28.36 | 1.0555 |  | DIESEL (LTR)
YIELD POINT | 23 | 24 | FLOWRATE (GPM) |  | 260 |  | METERAGE (M) |  | 42 |  | D.JAR |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.18 | 0.34165 |  | RIG TANK | 102259
GEL ST. | 8/13 | 9/15 | PRESSURE (PSI) |  | 3150-3400 |  | RPM SURF. |  | 40-80 |  | 18 X HWDP |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.78 | 6.3186 |  | CAMP TANK | 20998
WL (ml/30 min.) | 3 | 2.8 | TORQ. ON-BTM (KLB-FT) |  | 4-7 |  | RPM BTM. |  | 40-80 | [12 empty] | CONSUMED | 8369
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 4-5 |  | WOB (TON) |  | 1-6 | [12 empty] | RECEIVED | 0
ALK (MUD) | 0.8 | 0.8 | STRING WT. (TON) - ROT |  | 140 |  | AVG. ROP (M/HR) |  | 1.4189 | [12 empty] | TOTAL | 123257
ALK (FILT.) | 0.3 | 0.3 | PICK-UP WT. (TON) |  | 150 |  | BIT ROT HRS. |  | 14.71 | [12 empty] | WATER (LTR)
PH | 10 | 10 | SLACK-OFF WT. (TON) |  | 135 |  | K-REVS IN 24 HRS |  | 71.59 | [12 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  | 139.64 | [12 empty] | CAMP STORAGE | 55000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 76.13 | [12 empty] | CONSUMED | 67470
KCl (mg/l) | 57201 | 57201 | JAR | 70.59 | STAB - 1 | 39.96 | JET VELOCITY (M/SEC) |  | 32.8 | [12 empty] | RECEIVED | 67470
CHLORIDES | 31500 | 31500 | 3 1/2" HWDPS | 70.59 | STAB - 2 | 39.96 | TFA (IN²) |  | 0.78 | [12 empty] | TOTAL | 455000
CALCIUM | 280 | 260 | 4 3/4" DCS | 70.59 | NMDC | 70.59 | HSI |  | 0.8 | [12 empty] | POB
OIL % | 5 | 5 | MUD MOTOR | 70.59 | SPSA | 70.59 | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 323.55 |  |  | MPCL | 5
LUBE % | 1.5 | 1.5 | BHA ROT. HRS |  | 70.59 |  | BIT NO. 22RR1 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 12 |  |  | MPCL SERV | 17
SOLIDS % | 24.2 | 25.21 | ON BOTTOM HRS |  | 29.6 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 7 |  |  | SECURITY | 4
M.B.T. | 5 | 5 | CIRC. HRS |  | 41.74 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 120 | 2 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4475/4255.10 |  | 41.12 |  | 82.75 |  |  | 7.5 |  | MWD |  | TOTAL | 106
DAILY WELL COST (US$) |  | 45311.15 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4504/4277.05 |  | 40.54 |  | 83.94 |  |  | 1 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 19623412.5045 | SHAKER-3 | 1 x 140 | 2 x 120 |  | 7" LINER |  |  | 4446 (TOL @ 3253) | 4528/4295.03 |  | 42.38 |  | 82.15 |  |  | 2.74 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 108.7% | MUD CLEANER | 1 x 140 | 2 x 170 | [16 empty] | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P3) | [5 empty] | MAASP (PSI) | 600
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 |  | 30 |  | 4566 |  | 710 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4566 |  | 980 |  | CHORGALI | 4353/4167.8
FIRE DRILL | 2018-10-04 | 2018-11-03 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 |  | 50 |  | 4566 |  | 1340 |  | SAKESAR | 4423/4217.4
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | NAMMAL | 4539/4303.64
KICK DRILL | 2018-10-07 | 2018-11-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | PATALA | 4566/4320.51
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-10-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | HANGU | 4571/4323.65
STRETCHER DRILL | 2018-10-04 | 2018-11-03 | NEXT BOP TEST DATE |  | 2018-11-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | DHANDOT-TOBRA | 4587/4333.72
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-03
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43407 | 43407.2917 | 7 | DRL | NPT-UP | D | DRILLED 6'' HOLE IN ROTARY MODE FROM 4560M TO 4573.85M. OBSERVED TORQUE INCREASED AND ROTARY STALLED. IMMEDIATELY PICKED UP STRING ABOUT 2M AND GOT STUCK.
43407.2917 | 43407.3229 | 0.75 | DRL | NPT-UP | STK | WORKED ON STUCK PIPE. RELEASED PIPE AFTER SEVERAL ATTEMPTS OF JARRING UP AT MAX 90 TON OVER PULL.
43407.3229 | 43407.3958 | 1.75 | DRL | NPT-UP | CS | SWEPT OUT 20 + 20 BBLS TANDEM PILL (LOW/HIGH) & COLLECTED BOTTOM SAMPLES.
43407.3958 | 43407.4062 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43407.4062 | 43407.4271 | 0.5 | DRL | NPT-UP | WT | POOH FROM 4573.85M TO 4544M (INSIDE 7" LINER).
43407.4271 | 43407.4896 | 1.5 | DRL | NPT-UP | CIR | CIRCULATED TO HOMOGENIZE MUD.
43407.4896 | 43407.5312 | 1 | DRL | NPT-UP | WT | RIH FROM 4544M TO 4568M. OBSV'D TIGHT HOLE @4568M. REAMED DOWN TO BOTTOM, MEANWHILE INCREASED MUD WEIGHT.
43407.5312 | 43407.5833 | 1.25 | DRL | NPT-UP | RW | REAMED DOWN TO BOTTOM. MEANWHILE INCREASED MUD WEIGHT.
43407.5833 | 43408 | 10 | DRL | PT-P | D | DRILLED 6'' HOLE IN ROTARY MODE FROM 4573.85M TO 4585M. WHILE DRILLING OBSERVED FREQUENT ROTARY STALLING & INCREASED MUD WEIGHT TO 1.75 SG.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-04
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43408 | 43408.0208 | 0.5 | DRL | PT-P | D | DRILLED 6'' HOLE IN ROTARY MODE FROM 4585M TO 4586M.
43408.0208 | 43408.0938 | 1.75 | DRL | PT-P | CIR | SWEPT OUT 10 BBL HI-VIS PILL & CIRCULATED TO CLEAN HOLE.
43408.0938 | 43408.1146 | 0.5 | DRL | PT-P | WT | PERFORMED SHORT WIPER TRIP TO 4532M. OBSERVED 10-15 TONS COMPRESSION @ 4567M - CLEARED SAME.
43408.1146 | 43408.25 | 3.25 | DRL | PT-P | D | DRILLED 6'' HOLE IN ROTARY MODE FROM 4586M TO 4592M.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | DRILLING 6" HOLE.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 6'' HOLE IN ROTARY MODE FROM 4560M TO 4573.85M. OBSERVED STRING STUCK. RELEASED AFTER SEVERAL ATTEMPTS OF JARRING UP AT MAX 90 TON OVER PULL. PERFORMED WIPER TRIP TO 4544M. DRILLED AHEAD TO 4585M AND INCREASED MW TO 1.75 SG.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 6" HOLE SECTION.
REMARKS |  |  | MARKED TOP OF HANGU @ 4571M, MARKED TOP OF DANDOT-TOBRA AT 4587M
Formulas:
DHARIAN-1-ST-3 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14