## DDR#32
9
MARI PETROLEUM COMPANY LIMITED
[22 empty] | Report No. |  | 32
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-01-22
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT RAO / SAIFULLAH TURK / HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 2201 | [6 empty] | DAYS SINCE SPUD: | [6 empty] | 31.5833
RIG REP.: |  | SARDAR NAEEM / IMRAN JAWAD |  |  | MD/TVD @ 06:00HRS: |  | 2201 | [6 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-01-21 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 17.5 |  | BIT No. |  | 3RR1 | 3RR1 | 3RR2 | BHA No. |  |  | 6 | IN (M) |  | 2201 |  | OUT (M) |  |  | STRING (BBL) | 110
CHECK TIME |  | 23:59 | MD @ 00:00HR (M) |  | 2201 |  | SIZE (IN) |  | 17.5 | 17.5 | 17.5 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 2102
DEPTH, MD (M) |  | 2201 | TVD @ 00:00HR (M) |  | 2201 |  | MANUFACTURER |  | NOV | NOV | NOV | 17 1/2" PDC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.36 | 0.35 |  | PITS (BBL) | 882
MW IN (SG) |  | 1.52 | DAILY PROGRESS (M) |  | 0 |  | TYPE |  | TFH519 | TFH519 | TFH519 | MUD MOTOR |  |  | 9.75 | 7.85 |  | 7 5/8 REG |  | 9.87 | 2.9 |  | ACT. SYS (BBL) | 3094
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | E244694 | E244694 | E244694 | FLOAT SUB |  |  | 9.5 | 2.5 |  | 7 5/8 REG |  | 0.47 | 0.2 |  | RESV. SYS (BBL) | 1000
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | S422 | S422 | S422 | STRING STAB |  |  | 17.375 | 2.9375 |  | 7 5/8 REG |  | 2.44 | 0.8 |  | KILL MUD (BBL) | 400
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 5 X 18/32" | 5X18/32" | 5 X 18/32" | LOWER SAVER SUB |  |  | 9.5 | 3.5 |  | 7 5/8 REG |  | 0.62 | 0.2 |  | KILL MW (SG) | 1.8
µ FUNNEL (SEC) |  | 65 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 1654 | 1654 | 2201 | SLIM PULSE |  |  | 9.375 | 5 |  | 7 5/8 REG |  | 9.43 | 2.7 |  | TOTAL | 4494
PV |  | 32 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  | 2201 |  |  | UPPER SAVER SUB |  |  | 9.375 | 3 |  | 7 5/8 REG |  | 0.47 | 0.1 |  | DIESEL (LTR)
YIELD POINT |  | 29 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  | 547 |  |  | NMDC |  |  | 8.875 | 3.5 |  | 7 5/8 REG |  | 9.4 | 2.4 |  | RIG TANK | 94000
GEL ST. |  | 9/28 | PRESSURE (PSI) |  |  |  | RPM SURF. |  | 100 - 115 |  |  | 3 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 27.68 | 8.9417 |  | CAMP TANK | 13050
WL (ml/30 min.) |  | 4.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  | 190 - 205 |  |  | X/O |  |  | 9.375 | 3 |  | 7 5/8 REG |  | 0.94 | 0.30366 |  | CONSUMED | 6550
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  | 3 - 10 |  |  | 2 X 8" DC'S |  |  | 8 | 2.75 |  | 7 5/8 REG |  | 18.5 | 5.9762 |  | RECEIVED
ALK (MUD) |  | 0.6 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  | 2.7612 |  |  | D.JAR |  |  | 8 | 3.25 |  | 6 5/8 REG |  | 5.15 | 1.15 |  | TOTAL | 107050
ALK (FILT.) |  | 0.3 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. |  | 198.1 |  |  | 2 X 8" DC'S |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.63 | 4.1601 |  | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  | 85 |  |  | X/O |  |  | 8.25 | 3 |  | 6 5/8 REG |  | 0.9 | 0.20097 |  | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 2190 |  |  | 6 X 5" HWDPS |  |  | 5 | 3 |  | 6 5/8 REG |  | 56.25 | 12.5605 |  | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | CONSUMED | 73000
KCl (mg/l) |  | 53387.6 | JAR | 0 | NMDC | 0 | JET VELOCITY (M/SEC) | [15 empty] | RECEIVED | 68370
CHLORIDES |  | 25000 | 5" HWDPS | 0 | STAB - 1 | 0 | TFA (IN²) |  | 1.24 | [13 empty] | TOTAL | 440000
CALCIUM |  | 140 | 8" DCS | 0 | STAB - 2 |  | HSI | [15 empty] | POB
OIL% |  | 2 | 9 1/2" DCS | 0 | SPSA | 0 | DULL CODE |  | (I/O/D/L/B/G/O/R) |  |  | TOTAL LENGTH (M) | [7 empty] | 161.11 |  |  | MPCL | 4
DIESEL % |  | 2 | BHA ROT. HRS |  | 0 |  | BIT No. 3RR1 |  | 2/2/WT/A/X/I/BU/BHA |  |  | BHA WT. IN MUD (TON) | [7 empty] | 27 |  |  | MPCL SERV | 22
SOLIDS % |  | 16.82 | ON BOTTOM HRS |  | 0 | [6 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 19 |  |  | SECURITY | 4
M.B.T. |  | 10 | CIRC. HRS |  | 0 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 52
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 12
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) |  | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 80 | 2 X 80 |  | 20" SURFACE CASING |  |  | 594 |  | 2080 |  | 0.89 |  | 89.99 |  |  | 0.39 |  | MWD |  | TOTAL | 119
DAILY WELL COST (US$) |  | 34020 | SHAKER-2 | 2 X 120 | 1 X 80 |  | 13 3/8" INTERMEDIATE CSG |  |  |  |  | 2108 |  | 1.05 |  | 96.19 |  |  | 0.2 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 3366986 | SHAKER-3 | 1 X 100 | 2 X 80 |  | 9 5/8" PRODUCTION CSG |  |  |  |  | 2137 |  | 1.47 |  | 109.86 |  |  | 0.53 |  | MWD |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 18.65% | MUD CLEANER | 3 X 170 |  |  | 7" LINER |  |  |  |  | 2165 |  | 1.83 |  | 108.59 |  |  | 0.39 |  | MWD |  | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | 0 | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 295
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE |  | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-01-09 | 2018-01-23 | ANNULAR | RONGSHENG | 20.75 | 3000 | P-1 - F-1600HL | 6 1/2" |  | 12" |  | 3980 PSI | 97% |  | 0.119 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | RONGSHENG | 20.75 | 3000 | P-2 - F-1600HL | 6 1/2" |  | 12" |  | 3980 PSI | 97% |  | 0.119 |  | 30 / 40 |  | 2200 |  | 260/400 |  | CHINJI | 342
FIRE DRILL | 2018-01-03 | 2018-01-17 | BLIND RAMS | RONGSHENG | 20.75 | 3000 | P-3 - F-1600HL | 6 1/2" |  | 12" |  | 3980 PSI | 97% |  | 0.119 |  | 30 / 40 |  | 2200 |  | 240/380 |  | KAMLIAL | 1255
PIT DRILL | 2018-01-16 | 2018-01-30 | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-01-09 | 2018-01-23 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-01-21 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-01-03 | 2018-01-17 | NEXT BOP TEST DATE |  | 2018-02-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-01-21
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43121 | 43121.0729 | 1.75 | DRL | PT-P | RW | CONT'D SOFT BACK REAMED FROM 847 M TO 588 M.
43121.0729 | 43121.0833 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - LEVEL STATIC
43121.0833 | 43121.125 | 1 | DRL | PT-P | RW | WHILE POOH INSIDE CSG, OBSERVED O/PULL (5-10 T). CONNECTED TDS AND PUMPED OUT FROM 588 M TO 528 M.
43121.125 | 43121.1667 | 1 | DRL | PT-P | POOH | POOH FROM 528 M TO 165 M ON ELEVATOR.
43121.1667 | 43121.1771 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - LEVEL STATIC.
43121.1771 | 43121.3958 | 5.25 | DRL | PT-P | BHA | CONT'D POOH FROM 165 M TO SURFACE. B/OUT BIT, FOUND MOTOR SLEEVE + BIT BALLED UP. L/DOWN BHA (8 x 9 1/2" DC + 3 x 5" HWDP + NMDC + JAR + MUD MOTOR + ALL X/O'S) FOR INSPECTION.
43121.3958 | 43121.5833 | 4.5 | DRL | PT-P | BOPT | RETRIEVED WEAR BUSHING & RIH TEST PLUG ASSY. HELD PJSM. FLUSHED BOP STACK WITH WATER. P/TESTED (20-3/4 X 3000 BOP STACK) AND DRILLING SPOOL @ 300 / 2700 PSI FOR 5 / 10 MIN - OK. P/TESTED ANNULAR BOP @ 300 / 2700 PSI FOR 5 / 10 MIN - OK. P/TESTED PIPE RAMS, BLIND RAMS, KILL/CHOKE LINE & IBOP/ROTARY HOSE/STAND PIPE MANIFOLD @ 300 / 2700 PSI FOR 5 / 10 MIN - OK.
43121.5833 | 43121.6875 | 2.5 | DRL | PT-P | BHA | P/UP NEW 962 GT MOTOR, ADJUSTED 1.5° BEND ON MOTOR. M/UP 17 1/2" USED TRI-CONE BIT WITH SLB NEW GT MUD MOTOR. M/UP SPSA & INSTALLED MWD TOOL. ADJUSTED TOOLFACE OFFSET. SHALLOW FUNCTION TESTED MUD MOTOR & MWD @ 650 GPM & 960 PSI - OK. B/OUT & L/DOWN TRI-CONE BIT.
43121.6875 | 43121.8229 | 3.25 | DRL | PT-P | BHA | M/UP 17 1/2'' RE-RUN PDC BIT + PERFORMANCE ASSY. RIH TO 162 M. (WHILE RIH P/UP SINGLE BY SINGLE INSPECTED BHA COMPONENTS FROM CATWALK).
43121.8229 | 43121.8646 | 1 | DRL | PT-P | RIH | CONT'D RIH FROM 162 M TO 587 M (INSIDE CSG SHOE).
43121.8646 | 43121.875 | 0.25 | DRL | PT-P | RS | SERVICED TDS, MEANWHILE FLOW CHECKED - WELL STATIC.
43121.875 | 43122 | 3 | DRL | PT-P | RIH | CONT'D RIH FROM 587 M TO 1470 M. FILLED UP STRING EVERY 15 STANDS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-01-22
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43122 | 43122.0833 | 2 | DRL | PT-P | RIH | CONT'D RIH FROM 1470 M TO 2167 M. OBSERVED COMPRESSION AT 2167 M.
43122.0833 | 43122.25 | 4 | DRL | PT-P | RW | CONNECTED TDS, REAMED/WASHED DOWN FROM 2167 M TO 2196 M. (OBSERVED HARD REAMING BELOW 2180 M).
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE (90% CLAYSTONE & 10% SANDSTONE)
OPERATIONS AT 06:00 HRS |  |  | REAMED DOWN TO 2196 M AND IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D POOH TO SURFACE MEANWHILE L/DOWN BHA FOR NECESSARY INSPECTION, PERFORMED BOP TEST, M/UP RR PDC BIT+ INSPECTED BHA AND RIH TO 1470 M
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE RIH TO BOTTOM AT 2201 M. DRILL AHEAD 17 1/2'' HOLE IN ROTARY / SLIDE MODE.
REMARKS |  |  | OBSERVED MINOR QUANTITY OF MECHANICAL CAVING WHILE REAMING BELOW 2167M.
Formulas:
DHARIAN - 1 = [DATE]+14
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14