## DDR#32
9
MARI PETROLEUM COMPANY LIMITED
[7 empty] | EID MUBARAK | [13 empty] | Report No. |  | 32
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-06-05
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | IKRAMULLAH / AHSEN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 2091 / 2091 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 31.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 2098 / 2098 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 6
2019-06-04 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 17.5 |  | BIT No. |  | 5 |  | BHA NO. |  |  | 6 | IN (M) |  | 2085 |  | OUT (M) |  |  | STRING (BBL) | 137
CHECK TIME | 11:00 | 22:59 | MD @ 00:00HR (M) |  | 2091 |  | SIZE (IN) |  | 17 1/2" |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1907
DEPTH, MD (M) | 2085 | 2090 | TVD @ 00:00HR (M) |  | 2091 |  | MANUFACTURER |  | HLB |  | TRICONE BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.51 | 0.16475 |  | PITS (BBL) | 1115
MW IN (SG) | 2.06 | 2.06 | DAILY PROGRESS (M) |  | 6 |  | TYPE |  | EBXTA3GRC |  | BIT SUB |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 1.07 | 0.34565 |  | ACT. SYS (BBL) | 3159
MW OUT (SG) |  |  | INST. ROP (M/HR) |  | 1.3 |  | SERIAL NO. |  | 13183610 |  | STRING STAB |  |  | 17.375 | 3.0625 |  | 7 5/8 REG |  | 2.43 | 0.78498 |  | RESV. SYS (BBL) | 1391
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 1.32 |  | IADC CODE |  | 135M |  | 1 X 9 1/2" DC |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 9.23 | 2.9816 |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  | 10 |  | NOZZLES |  | 3 X 20 + 1 X 22 |  | STRING STAB |  |  | 17.375 | 3 |  | 7 5/8 REG |  | 2.37 | 0.7656 |  | KILL MW (SG)
µ FUNNEL (SEC) | 65 | 64 | AVG. RPM SURFACE |  | 120 |  | DEPTH IN (M) |  | 2085 |  | 2 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 18.3 | 5.9116 |  | TOTAL | 4550
PV | 48 | 47 | AVG. RPM DOWNHOLE |  | 120 |  | DEPTH OUT (M) |  |  |  | STRING STAB |  |  | 17.375 | 3 |  | 7 5/8 REG |  | 2.14 | 0.6913 |  | DIESEL (LTR)
YIELD POINT | 33 | 31 | FLOWRATE (GPM) |  | 800 |  | METERAGE (M) |  | 6 |  | 4 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 36.91 | 11.9234 |  | RIG TANK | 122728
GEL ST. | 12/14 | 11/13 | PRESSURE (PSI) |  | 3250 - 3330 |  | RPM SURF. |  | 100 - 140 |  | X/OVER |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.93 | 0.30043 |  | CAMP TANK | 21077
WL (ml/30 min) | 6.8 | 6.5 | TORQ. ON-BTM (KLB-FT) |  | 6 - 7 |  | RPM BTM. |  | 100 - 140 |  | 2 X 8" DCS |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.34 | 4.0953 |  | CONSUMED | 7781
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 4 - 5 |  | WOB (TON) |  | 5 - 15 |  | DRILLING JAR |  |  | 7.9375 | 3 |  | 6 5/8 REG |  | 9.53 | 2.128 |  | RECEIVED
ALK (MUD) | 0.2 | 0.3 | STRING WT. (TON) - ROT |  | 130 |  | AVG. ROP (M/HR) |  | 1.3245 |  | 2 X 8" DCS |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.43 | 4.1154 |  | TOTAL | 143805
ALK (FILT.) | 0.3 | 0.4 | PICK-UP WT. (TON) |  | 135 |  | BIT ROT HRS. |  | 4.53 |  | X/OVER |  |  | 7.625 | 2.8125 |  | 5 1/2 FH |  | 0.81 | 0.18087 |  | WATER (LTR)
PH | 9.2 | 9.5 | SLACK-OFF WT. (TON) |  | 125 |  | K-REVS IN 24 HRS |  | 32.5 |  | 10 X 5 1/2" HWDPS |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 94.38 | 8.4468 |  | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 32.5 | [12 empty] | CAMP STORAGE | 85000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 18.6 | [12 empty] | CONSUMED | 83300
KCl (mg/l) | 50336.9 | 52434.3 | JAR | 19.9 | STAB - 1 | 218.4 | JET VELOCITY (M/SEC) |  | 60.57 | [12 empty] | RECEIVED | 88300
CHLORIDES (mg/l) | 24000 | 25000 | MOTOR |  | STAB - 2 | 218.4 | TFA (IN²) |  | 1.29 | [12 empty] | TOTAL | 485000
HARDNESS (mg/l) | 460 | 460 | 9 1/2" DCS | 228.4 | STAB - 3 | 19.9 | HSI |  | 1.175 | [12 empty] | POB
SAND % | 0.25 | 0.25 | 8" DCS | 228.4 | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 215.38 |  |  | MPCL | 4
LUBRICANT % | 0.5 | 0.5 | BHA ROT. HRS |  | 228.4 |  | BIT NO. 5 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 33 |  |  | MPCL SERV | 25
SOLIDS % | 34.57 | 34.78 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 22 |  |  | SECURITY
M.B.T. (lb/bbl) | 7.5 | 7.5 | CIRC. HRS |  | 18.53 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 42
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 30" CONDUCTOR |  |  | 37 | 1953/1953 |  | 0.08 | [6 empty] | MWD |  | TOTAL | 101
DAILY WELL COST (US$) |  | 83068.2758 | SHAKER-2 | 1 X 35 | 2 X 35 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 1981/1981 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 3473762.6292 | SHAKER-3 | 1 X 100 | 2 X 100 | [5 empty] | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 17.45% | MUD CLEANER | 3 x 120 | [6 empty] | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | LOT (EMW) | 2.16
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 82
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PRESS.PSI |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | JX CHINA | 21.25 | 5000 | P-1 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 30 |  | 2073 | 300 / 325 / 375 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JX CHINA | 21.25 | 5000 | P-2 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 40 |  | 2073 | 300 / 325 / 375 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-05-09 | 2019-06-08 | BLIND RAMS | JX CHINA | 21.25 | 5000 | P-3 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 50 |  | 2073 | 300 / 325 / 375 |  |  | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-06-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  | 2019-06-17 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-04
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43620 | 43620.2188 | 5.25 | DRL | NPT-UP | RW | RIH BIT FROM 1447M TO 2080M. OBSERVED & CLEARED TIGHT SPOTS FROM 1631M - 1635M, 1710M - 1717M & CLEARED HOLE FILL FROM 2076M - 2080M.
43620.2188 | 43620.4583 | 5.75 | DRL | NPT-UP | CIR | CIRCULATED & ADDED LCM / WELLBORE STRENGTHENING MATERIAL IN MUD SYSTEM AS PER PROGRAM. RECORDED MWT IN = MWT OUT = 2.06 SG AFTER HOMOGENIZING MUD. MIN MUD CUT OF 1.87 SG RECEIVED DURING CIRCULATION. GRADUALLY INCREASED FLOW RATE TO 850 GPM. OBSERVED NO LOSS / NO GAIN DURING CIRCULATION.
43620.4583 | 43620.4688 | 0.25 | DRL | NPT-UP | RR | WHILE CIRCULATING @ 850 GPM, ENGINES GOT TRIPPED & POWER SHUT DOWN OCCURED. RESTARTED ENGINES.
43620.4688 | 43620.4896 | 0.5 | DRL | NPT-UP | CIR | CIRCULATED @ 870 GPM & OBSERVED NO LOSS / NO GAIN DURING CIRCULATION.
43620.4896 | 43620.6458 | 3.75 | DRL | NPT-UP | RW | HARD REAMED FROM 2080M TO 2085M.
43620.6458 | 43620.6667 | 0.5 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43620.6667 | 43620.8542 | 4.5 | DRL | PT-P | D | DRILLED 17 1/2" HOLE FROM 2085M TO 2090M & ADJUSTED DRILLING PARAMETERS TO OPTIMIZE ROP.
43620.8542 | 43620.875 | 0.5 | DRL | NPT-UP | FC | FLOW CHECKED & OBSERVED WELL AT TRIP TANK - OBSERVED WELL TRICKLING.
43620.875 | 43620.9167 | 1 | DRL | PT-UP | CIR | SWEPT 20 BBL CAUSTIC PILL, CIRCULATED & ROTATED STRING @ HIGH RPM.
43620.9167 | 43621 | 2 | DRL | PT-P | D | DRILLED 17 1/2" HOLE FROM 2090M TO 2091M & ADJUSTED DRILLING PARAMETERS TO OPTIMIZE ROP.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-05
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43621 | 43621.25 | 6 | DRL | PT-P | D | CONT'D DRILLING 17 1/2" HOLE FROM 2091M TO 2098M & ADJUSTED DRILLING PARAMETERS TO OPTIMIZE ROP.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CIRCULATED & ADDED LCM / WELLBORE STRENGTHENING MATERIAL IN MUD SYSTEM AS PER PROGRAM. HARD REAMED FROM 2080M TO 2085M. DRILLED 17 1/2" HOLE FROM 2085M TO 2091M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 17 1/2" HOLE.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14