## DDR#320
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 320
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-03-19
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5506 / 5450 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | S. KHALID AZIM / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4815 | 4795.85 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 319.9792
RIG REP.: |  | TARIQ MAHMOOD BUTT / FAYYAZ HUSSAIN |  |  | MD/TVD @ 06:00HRS: |  | 4815 | 4795.85 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2020-03-18 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 0
CHECK TIME | 16:00 | 0:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 964.8
DEPTH, MD (M) | 4815 | 4815 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) | [15 empty] | PITS (BBL) | 191
MW IN (SG) | 1.96 | 1.96 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER | [15 empty] | ACT. SYS (BBL) | 1155.8
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE | [15 empty] | RESV. SYS (BBL) | 1193
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. | [15 empty] | KILL MUD (BBL) | 240
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE | [15 empty] | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 55 | 57 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") | [15 empty] | TOTAL | 2588.8
PV | 38 | 39 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [15 empty] | DIESEL (LTR)
YIELD POINT | 22 | 22 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 78491
GEL ST. | 11/19 | 10/19 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 20841
WL (ml/30 min) | 6 | 6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 5895
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED | 24000
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 99332
ALK (FILT.) | 0.3/1.3 | 0.4/1.5 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10 | 10.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 499654
MAX SHIELD % | 1.5 | 1.5 | D & I SURVEY-(OFF BIT-M)Telescope |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 80000
KCl (%) | 3.7 | 3.7 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 127860
KCl (mg/l) | 32413.9 | 32413.9 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 75900
CHLORIDES (mg/l) | 78000 | 78000 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) | 600 | 620 | 3 1/2" HWDPS |  | STAB - 2 |  | TFA (IN²) | [15 empty] | POB
PENETRAX % | 0 | 0 | 4 3/4" DCS |  | STAB - 3 |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 3
MAX GUARD % | 1 | 1 | DAILY BHA ROT. HRS |  |  |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 22
SOLIDS % | 37.15 | 37.15 | DAILY ON BOTTOM HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 2.48 |  | BIT NO. |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 48
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [11 empty] | TOTAL | 106
DAILY WELL COST (US$) |  | 42894.48 | SHAKER-2 | 2 x 200 + 1 x 170 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 22343995.887 | SHAKER-3 | 2 x 140 + 1 x 120 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | [11 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 112.2% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER (VM140HC, 32#, VT) |  |  |  | 4996 / 4496 (TOL) | [11 empty] | FIT (EMW)
[7 empty] | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4814 / 3397 (TOL) | [11 empty] | MAASP (PSI)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.96 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | PATALA | 4715/4703.61
FIRE DRILL | 2020-02-13 | 2020-03-15 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | HANGU | 4740/4726.58
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | DANDOT | 4753/4738.56
KICK DRILL | 2020-02-12 | 2020-03-12 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | BAGHANWALA | 4773/4757
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-03-09 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | JUTANA | 4788/4770.97
STRETCHER DRILL | 2020-02-13 | 2020-03-15 | NEXT BOP TEST DATE |  | 2020-03-23 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KUSSAK | 4813/4794.01
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-03-18
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43908 | 43908.0417 | 1 | DRL | PT-P | RIH | CONT'D RIH FROM 4265M TO 4752M.
43908.0417 | 43908.0729 | 0.75 | DRL | PT-P | COC | RIH WITH CIRCULATION & WORKED ON SCRAPPER FROM 4752M TO 4812M.
43908.0729 | 43908.1562 | 2 | DRL | PT-P | CIR | CIRCULATED BOTTOMS UP TILL SHAKERS CLEAN.
43908.1562 | 43908.5417 | 9.25 | DRL | PT-P | POOH | PUMPED SLUG & POOH FROM 4812M TO 336M (BHA TOP).
43908.5417 | 43908.5521 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43908.5521 | 43908.6146 | 1.5 | DRL | PT-P | BHA | POOH BHA TO SURFACE. L/D SCRAPPER, BIT SUB & BIT.
43908.6146 | 43908.6458 | 0.75 | DRL | PT-P | RU | HELD PJSM. R/U SLB WIRELINE GEARS.
43908.6458 | 43908.9688 | 7.75 | DRL | PT-P | W/L | CONDUCTED CASED HOLE WIRELINE LOG (USIT-CBL-VDL-CCL-GR).
43908.9688 | 43908.9896 | 0.5 | DRL | PT-P | RD | R/D SLB WIRELINE GEARS.
43908.9896 | 43909 | 0.25 | DRL | PT-P | OTH | SHIFTED 4 3/4" DC STANDS ON ONE SIDE OF DERRICK.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-03-19
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43909 | 43909.0521 | 1.25 | DRL | PT-P | BHA | M/U RR 6" PDC BIT + PD ORBIT + FLOAT SUB + SPSA & INSTALLED MWD TOOL + PBL SUB + ST. STAB. M/U PUP JOINT & X-OVER.
43909.0521 | 43909.0833 | 0.75 | DRL | PT-P | E/C | FUNCTION TESTED MWD, OK. DOWNLINKED PD ORBIT, COMMAND ACCEPTED SUCCESSFULLY.
43909.0833 | 43909.1042 | 0.5 | DRL | PT-P | E/C | FUNCTION TESTED PBL SUB, OK. PBL DEACTIVATED AT 2200 PSI. RETRIEVED DART & DEACTIVATION BALLS.
43909.1042 | 43909.1875 | 2 | DRL | PT-P | BHA | CONT'D RIH FROM 20M TO 321M. WHILE RIH, P/U DRL JAR & 12x 3 1/2" HWDP FROM CATWALK. DRIFTED AND FLUSHED EACH SINGLE. FLUSHED BHA.
43909.1875 | 43909.25 | 1.5 | DRL | PT-P | RIH | RIH FROM 321M TO 1037M & IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | RIH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH WITH 7" CSG SCRAPPER FROM 4265M TO 4752M. WORKED ON SCRAPPER FROM 4752M TO 4812M. CIRCULATED & POOH TO SURFACE. CONDUCTED CASED HOLE WIRELINE LOG (USIT-CBL-VDL-CCL-GR).
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH DOWN TO BOTTOM. DRILL CEMENT, DISPLACE MUD, DRILL FLOAT SHOE & NEW FORMATION (2-3M). CONDUCT FIT & DRILL 6" HOLE AS PER PLAN.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14