## DDR#321
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 321
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-11-07
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO/ HAMZA / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4628 / 4368.62 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 104.13
RIG REP. (TP): |  | JAVED IQBAL MUGHAL / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4635 / 4373.72 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 27
2018-11-06 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | BIT NO. |  | 22RR2 | 22RR2 | BHA No. |  |  | 50 | IN (M) |  | 4595 |  | OUT (M) |  |  | STRING (BBL) | 209.8
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 4628 |  | SIZE (IN) |  | 6 | 6 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 620.1
DEPTH, MD (M) | 4615 | 4628 | TVD @ 00:00HR (M) |  | 4368.62 |  | MANUFACTURER |  | SMITH | SMITH | 6'' PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 |  |  | PITS (BBL) | 602
MW IN (SG) | 1.75 | 1.75 | DAILY PROGRESS (M) |  | 27 |  | TYPE |  | MDSi613WBPX | MDSi613WBPX | MUD MOTOR |  |  | 4.75 | 2 |  | 3 1/2 REG |  | 7.2 | 0.53592 |  | ACT. SYS (BBL) | 1431.9
MW OUT (SG) | 1.75 | 1.75 | INST. ROP (M/HR) |  | 0.55 |  | SERIAL NO. |  | JN5339 | JN5339 | FLOAT SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.79 | 0.058802 |  | RESV. SYS (BBL) | 425
ECD (SG) | - | - | AVG. ROP (M/HR) |  | 1.34 |  | IADC CODE |  |  |  | ST. STAB |  |  | 5.875 | 2.0625 |  | 3 1/2 IF |  | 1.58 | 0.1176 |  | KILL MUD (BBL) | 1050
FL TEMP. °F | - | - | AVG. WOB (TON) |  | 1-5 |  | NOZZLES (1/32") |  | 4 X 13 | 4 X 13 | L.SAVER SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.46 | 0.034239 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 53 | 52 | AVG. RPM SURFACE |  | 0-80 |  | DEPTH IN (M) |  | 4595 | 4595 | SLIMPULSE |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 9.45 | 0.70339 |  | TOTAL | 2906.9
PV | 30 | 30 | AVG. RPM DOWNHOLE |  | 133-216 |  | DEPTH OUT (M) |  |  |  | NMDC |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 4.3 | 0.16003 |  | DIESEL (LTR)
YIELD POINT | 25 | 24 | FLOWRATE (GPM) |  | 237-250 |  | METERAGE (M) |  | 33 |  | 9 X DC's |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 83.41 | 6.2084 |  | RIG TANK | 92023
GEL ST. | 9/13 | 9/14 | PRESSURE (PSI) |  | 3750-4050 |  | RPM SURF. |  | 0-80 |  | 3 X HWDP's |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 28.36 | 1.0555 |  | CAMP TANK | 27355
WL (ml/30 min.) | 2.8 | 2.7 | TORQ. ON-BTM (KLB-FT) |  | 0-6 |  | RPM BTM. |  | 133-216 |  | D.JAR |  |  | 4.6875 | 2.25 |  | 3 1/2 IF |  | 9.18 | 0.34165 |  | CONSUMED | 5500
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 4-5 |  | WOB (TON) |  | 1-5 |  | 18 X HWDP's |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.78 | 6.3186 |  | RECEIVED | 0
ALK (MUD) | 0.7 | 0.7 | STRING WT. (TON) - ROT |  | 139 |  | AVG. ROP (M/HR) |  | 1.6984 | [12 empty] | TOTAL | 119378
ALK (FILT.) | 0.3 | 0.3 | PICK-UP WT. (TON) |  | 150 |  | BIT ROT HRS. |  | 19.43 | [12 empty] | WATER (LTR)
PH | 10 | 10 | SLACK-OFF WT. (TON) |  | 133 |  | K-REVS IN 24 HRS |  | 209.26 | [12 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  | 385.3 | [12 empty] | CAMP STORAGE | 50000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 65.15 | [12 empty] | CONSUMED | 30000
KCl (mg/l) | 57201 | 57201 | JAR | 102.78 | STAB - 1 | 22.69 | JET VELOCITY (M/SEC) |  | 61.2 | [12 empty] | RECEIVED | 30000
CHLORIDES | 32000 | 32000 | 3 1/2" HWDPS | 102.78 | STAB - 2 |  | TFA (IN²) |  | 0.39 | [12 empty] | TOTAL | 450000
CALCIUM | 280 | 260 | 4 3/4" DCS | 102.78 | NMDC | 22.69 | HSI |  | 2.6 | [12 empty] | POB
OIL % | 5 | 5 | MUD MOTOR | 22.69 | SPSA | 22.69 | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 314.71 |  |  | MPCL | 7
LUBE % | 2 | 2 | BHA ROT. HRS |  | 102.78 |  | BIT NO. 22RR2 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 12 |  |  | MPCL SERV | 16
SOLIDS % | 25.71 | 25.71 | ON BOTTOM HRS |  | 19.43 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 7 |  |  | SECURITY | 4
M.B.T. | 5 | 5 | CIRC. HRS |  | 35.9 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 50
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 21
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 120 | 2 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4553/4313.60 |  | 42.38 |  | 82.15 |  |  | 2.74 |  | MWD |  | TOTAL | 107
DAILY WELL COST (US$) |  | 41310.93 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4576/4330.65 |  | 41.67 |  | 80.95 |  |  | 1.29 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 19767980.6845 | SHAKER-3 | 1 x 140 | 2 x 120 |  | 7" LINER |  |  | 4446 (TOL @ 3253) | 4589/4340.17 |  | 42.67 |  | 82.45 |  |  | 1.85 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 109.5% | MUD CLEANER | 1 x 140 | 2 x 170 | [5 empty] | 4618/4361.31 |  | 43.24 |  | 82.8 |  |  | 0.75 |  | MWD |  | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P3) | [5 empty] | MAASP (PSI) | 300
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 |  | 30 |  | 4603 |  | 950 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4603 |  | 1350 |  | NAMMAL | 4539/4303.64
FIRE DRILL | 2018-10-04 | 2018-11-03 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 |  | 50 |  | 4603 |  | 1800 |  | PATALA | 4566/4320.51
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | HANGU | 4571/4323.65
KICK DRILL | 2018-10-07 | 2018-11-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | DHANDOT-TOBRA | 4587/4333.72
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-10-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | BHAGANWALA | 4608/4354.35
STRETCHER DRILL | 2018-10-04 | 2018-11-03 | NEXT BOP TEST DATE |  | 2018-11-14 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | JUTANA | 4627/4367.58
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-06
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43410 | 43410.4375 | 10.5 | DRL | PT-P | DCD | DRILLED 6" HOLE FROM 4601M TO 4617M WITH CONTROLLED PARAMETERS, IN ROTARY MODE.
43410.4375 | 43410.4688 | 0.75 | DRL | PT-P | DM | PICKED UP D/STRING. BACK REAM AND REAM DOWN. SET MWD TOOL FACE.
43410.4688 | 43410.6667 | 4.75 | DRL | PT-P | DM | DRILLED 6" HOLE FROM 4617M TO 4620.70M IN SLIDE MODE.
43410.6667 | 43410.7292 | 1.5 | DRL | PT-P | DM | DRILLED 6" HOLE FROM 4620.70M TO 4622.45M IN ROTATING MODE. PUMPED 15 BBLS HI-VIS PILL.
43410.7292 | 43410.7604 | 0.75 | DRL | PT-P | DM | PICKED UP D/STRING. BACK REAM AND REAM DOWN. SET MWD TOOL FACE.
43410.7604 | 43411 | 5.75 | DRL | PT-P | DM | DRILLED 6" HOLE FROM 4622.45M TO 4628M IN SLIDE MODE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-07
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43411 | 43411.25 | 6 | DRL | PT-P | DM | DRILLED 6" HOLE FROM 4628M TO 4635M IN ROTARY MODE.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | JUTANA / SILT, CLAY & DOLOMITE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 6" HOLE
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 6'' HOLE IN ROTARY & SLIDE MODE FROM 4601M TO 4628M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 6" HOLE SECTION.
REMARKS |  |  | MARKED JUTANA FORMATION @ 4627M.
Formulas:
DHARIAN-1-ST-3 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+21