## DDR#325
9
MARI PETROLEUM COMPANY LIMITED
[22 empty] | Report No. |  | 325
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-11-11
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / M. MOHSIN ALI |  |  | MD/TVD @ 00:00HRS: |  | 4730 / 4442.90 METER | [6 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 108.13
RIG REP. (TP): |  | JAVED IQBAL MUGHAL / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4730 / 4442.90 METER | [6 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 1
2018-11-10 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | BIT NO. |  | 22RR2 | 22RR2 | 23 | BHA No. |  |  | 51 | IN (M) |  | 4730 |  | OUT (M) |  |  | STRING (BBL) | 0
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 4730 |  | SIZE (IN) |  | 6 | 6 | 6 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 926.2
DEPTH, MD (M) | 5730 | 4730 | TVD @ 00:00HR (M) |  | 4442.9 |  | MANUFACTURER |  | SMITH | SMITH | HALIBURTON | 6'' PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.27 |  |  | PITS (BBL) | 555
MW IN (SG) | 1.75 | 1.75 | DAILY PROGRESS (M) |  | 1 |  | TYPE |  | MDSi613WBPX | MDSi613WBPX | GT64D | BIT SUB |  |  | 4.75 | 2 |  | 3 1/2 REG |  | 1.07 | 0.079643 |  | ACT. SYS (BBL) | 1481.2
MW OUT (SG) | 1.75 | 1.75 | INST. ROP (M/HR) |  | - |  | SERIAL NO. |  | JN5339 | JN5339 | 12919090 | ST. STAB |  |  | 5.875 | 2.25 |  | 3 1/2 IF |  | 1.81 | 0.13472 |  | RESV. SYS (BBL) | 292
ECD (SG) | - | - | AVG. ROP (M/HR) |  | 2 |  | IADC CODE |  |  |  | M434 | 1X DC |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 9.22 | 0.68627 |  | KILL MUD (BBL) | 1000
FL TEMP. °F | - | - | AVG. WOB (TON) |  | 3-4 |  | NOZZLES (1/32") |  | 4 X 13 | 4 X 13 | 3 X 14 | ST. STAB |  |  | 5.875 | 2.25 |  | 3 1/2 IF |  | 1.97 | 0.14663 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 50 | 50 | AVG. RPM SURFACE |  | 80 |  | DEPTH IN (M) |  | 4595 | 4595 | 4730 | 11 X DC's |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 101.79 | 7.5765 |  | TOTAL | 2773.2
PV | 34 | 34 | AVG. RPM DOWNHOLE |  | 212 |  | DEPTH OUT (M) |  | 4730 |  |  | 3 X HWDP |  |  | 4.6875 | 2.25 |  | 3 1/2 IF |  | 28.29 | 1.0529 |  | DIESEL (LTR)
YIELD POINT | 25 | 24 | FLOWRATE (GPM) |  | 243 |  | METERAGE (M) |  | 135 |  |  | D.JAR |  |  | 4.75 | 2.375 |  | 3 1/2 IF |  | 9.1 | 0.67734 |  | RIG TANK | 98508
GEL ST. | 12/16 | 12/16 | PRESSURE (PSI) |  | 3700-3750 |  | RPM SURF. |  | 0-80 |  |  | 18 X HWDP |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.92 | 6.3238 |  | CAMP TANK | 25236
WL (ml/30 min.) | 2.7 | 2.7 | TORQ. ON-BTM (KLB-FT) |  | 5-7 |  | RPM BTM. |  | 133-216 | [13 empty] | CONSUMED | 4214
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 4-5 |  | WOB (TON) |  | 1-5 | [13 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  | 140 |  | AVG. ROP (M/HR) |  | 1.5939 | [13 empty] | TOTAL | 123744
ALK (FILT.) | 0.3 | 0.3 | PICK-UP WT. (TON) |  | 150 |  | BIT ROT HRS. |  | 84.7 | [13 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 133 |  | K-REVS IN 24 HRS |  | 6.36 | [13 empty] | RIG STORAGE | 350000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  | 1158.88 | [13 empty] | CAMP STORAGE | 45000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 65.15 | [13 empty] | CONSUMED | 30000
KCl (mg/l) | 59107.7 | 59107.7 | JAR | 172.42 | STAB - 1 | 92.33 | JET VELOCITY (M/SEC) |  | 61.2 | [13 empty] | RECEIVED | 30000
CHLORIDES | 31000 | 31000 | 3 1/2" HWDPS | 172.42 | STAB - 2 |  | TFA (IN²) |  | 0.39 | [13 empty] | TOTAL | 395000
CALCIUM | 280 | 260 | 4 3/4" DCS | 172.42 | NMDC | 92.33 | HSI |  | 2.6 | [13 empty] | POB
OIL % | 5 | 5 | MUD MOTOR | 92.33 | SPSA | 92.33 | DULL CODE |  | I-O-D-L-B-G-O-R |  |  | TOTAL LENGTH (M) | [7 empty] | 323.44 |  |  | MPCL | 4
LUBE % | 2 | 2 | BHA ROT. HRS |  | 172.42 |  | BIT NO. 22RR2 |  | 3-4-BT-A-X-I-WT-BHA |  |  | BHA WT. IN MUD (TON) | [7 empty] | 12 |  |  | MPCL SERV | 15
SOLIDS % | 25.65 | 25.65 | ON BOTTOM HRS |  | 84.7 | [6 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 7 |  |  | SECURITY | 4
M.B.T. | 5 | 5 | CIRC. HRS |  | 107.67 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 54
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 11
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) |  | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 120 | 2 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 |  | 4647/4382.61 |  | 42.19 |  | 81.49 |  |  | 1.83 |  | MWD |  | TOTAL | 112
DAILY WELL COST (US$) |  | 32675.0775 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 |  | 4676/4403.94 |  | 43.13 |  | 83.16 |  |  | 1.52 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 19942598.872 | SHAKER-3 | 1 x 120 | 2 x 120 |  | 7" LINER |  |  | 4446 (TOL @ 3253) |  | 4701/4422.05 |  | 43.98 |  | 82.8 |  |  | 1.06 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 110.5% | MUD CLEANER | 1 x 140 | 2 x 170 | [6 empty] | 4713/4430.68 |  | 44.03 |  | 82.27 |  |  | 0.93 |  | MWD |  | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (P3) | [5 empty] | MAASP (PSI) | 300
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE |  | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" |  | 6725 PSI | 97% |  | 0.07 |  | 30 |  | 4662 |  | 950 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" |  | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4662 |  | 1380 |  | HANGU | 4571/4323.65
FIRE DRILL | 2018-11-08 | 2018-12-08 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" |  | 6725PSI | 97% |  | 0.07 |  | 50 |  | 4662 |  | 1850 |  | DHANDOT-TOBRA | 4587/4333.72
PIT DRILL | 2018-11-08 | 2018-11-23 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BHAGANWALA | 4608/4354.35
KICK DRILL | 2018-10-07 | 2018-11-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | JUTANA | 4627/4367.58
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-10-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK | 4657/4390.03
STRETCHER DRILL | 2018-11-08 | 2018-12-08 | NEXT BOP TEST DATE |  | 2018-11-14 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4724/4438.61
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-10
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43414 | 43414.0208 | 0.5 | DRL | PT-P | DCD | DRILLED 6" HOLE FROM 4729M TO 4730M IN ROTARY MODE.
43414.0208 | 43414.1458 | 3 | DRL | PT-P | CIR | SWEPT HOLE WITH 10 BBL LOW & 30 BBL HI-VIS TANDEM PILL & CIRCULATED TO CLEAN HOLE. RECORDED MWD SURVEY.
43414.1458 | 43414.1562 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43414.1562 | 43414.1979 | 1 | DRL | PT-P | POOH | POOH FROM 4730M TO 4435M (INSIDE 7" LINER).
43414.1979 | 43414.2083 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43414.2083 | 43414.5625 | 8.5 | DRL | PT-P | POOH | PUMPED SLUG. POOH FROM 4435M TO 315M.
43414.5625 | 43414.5833 | 0.5 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43414.5833 | 43414.7917 | 5 | DRL | PT-P | BHA | POOH BHA FROM 315M TO SURFACE. BROKE OUT BIT & DRAINED MUD MOTOR. L/DOWN 21 X HWDP, 9 X DC, JAR, S. STAB, NMDC, SPSA, MUD MOTOR & BIT.
43414.7917 | 43414.8125 | 0.5 | DRL | PT-P | WB | PJSM. RETRIEVED WEAR BUSHING.
43414.8125 | 43414.9375 | 3 | DRL | PT-P | BOPT | M/UP TEST PLUG ASSY WITH 5" DP & SET TEST PLUG INSIDE 11" THS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP, ROTARY HOSE & STANDPIPE @ 300/5000 PSI FOR 5/10 MIN - OK. P/TESTED UPPER VARIABLE PIPE RAM BOP (2 7/8" - 5"), LOWER 5" PIPE RAM BOP, TDS HYDRAULIC IBOP, TDS MANUAL IBOP, 4 1/2 IF FOSV, HCR VALVES, MANUAL VALVES @ KILL LINE/CHOKE LINE @ 300/8000 PSI FOR 5/10 MIN - OK. RETRIEVED & L/DOWN 5" DP TEST PLUG ASSY.
43414.9375 | 43415 | 1.5 | DRL | PT-P | BOPT | M/UP TEST PLUG ASSY WITH 3 1/2" DP & SET TEST PLUG INSIDE 11" THS. P/TESTED ANNULAR BOP @ 300/5000 PSI FOR 5/10 MIN - OK. P/TESTED UPPER VARIABLE PIPE RAM BOP (2 7/8" - 5"), 3 1/2 IF FOSV, CHOKE MANIFOLD MASTER VALVE, CO-FLEX HOSE & BLIND / SHEAR RAM BOP @ 300/8000 PSI FOR 5/10 MIN - OK.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-11
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43415 | 43415.0417 | 1 | DRL | PT-P | WB | SET WEAR BUSHING. RETRIEVED & L/DOWN 3 1/2" TEST PLUG ASSY.
43415.0417 | 43415.1875 | 3.5 | DRL | PT-P | BHA | P/U & M/U NEW 6" BIT & RIH INSPECTED PACKED BHA SINGLE BY SINGLE FROM SURFACE TO 323M.
43415.1875 | 43415.25 | 1.5 | DRL | PT-P | RIH | RIH FROM 323M TO 930M. FILL UP STRING EVERY 15 STANDS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA / SANDSTONE & CLAYSTONE
OPERATIONS AT 06:00 HRS |  |  | RIH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 6'' HOLE IN ROTARY MODE FROM 4729M TO 4730M. POOH TO SURFACE & L/D BHA. PERFORMED ROUTINE BOP PRESSURE TEST.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH TO BOTTOM. DRILL AHEAD 6" HOLE SECTION.
REMARKS |  |  | DIRECTIONAL DRILLING CREW & EQUIPMENT RELEASED ON 10 NOV 2018.
Formulas:
DHARIAN-1-ST-3 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+21