## DDR#325
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 325
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-03-24
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5506 / 5450 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | S. KHALID AZIM / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4929.24 | 4900.76 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 324.9792
RIG REP.: |  | TARIQ MAHMOOD BUTT / FAYYAZ HUSSAIN |  |  | MD/TVD @ 06:00HRS: |  | 4929.24 | 4900.76 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 2 METER
2020-03-23 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | RUN NO. |  |  | 66 |  | BHA NO. |  |  | 79 | IN (M) |  | 4929 |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 16:00 | 0:00 | MD @ 00:00HR (M) |  | 4929.24 |  | BIT NO. |  |  | 28 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 977.8
DEPTH, MD (M) | 4929 | 4929 | TVD @ 00:00HR (M) |  | 4900.76 |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 | 0.1 |  | PITS (BBL) | 334
MW IN (SG) | 1.65 | 1.65 | DAILY PROGRESS (M) |  | 2 |  | MANUFACTURER |  |  | NOV |  | PD ORBIT |  |  | 5 | 3.625 |  | 3 1/2 IF |  | 4.47 | 0.16835 |  | ACT. SYS (BBL) | 1311.8
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | SK613M |  | FLOAT SUB |  |  | 4.75 | 2.5 |  | 3 1/2 IF |  | 0.78 | 0.029377 |  | RESV. SYS (BBL) | 659
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | E260747 |  | L/ SAVER SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.45 | 0.016948 |  | KILL MUD (BBL) | 300
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | SPSA |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 9.45 | 0.35592 |  | KILL MW (SG) | 2.2
µ FUNNEL (SEC) | 50 | 52 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 6 x 12 |  | PBL SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 3.08 | 0.116 |  | TOTAL | 2270.8
PV | 24 | 25 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4929 |  | ST. STAB |  |  | 5.875 | 2.25 |  | 3 1/2 IF |  | 1.9 | 0.07156 |  | DIESEL (LTR)
YIELD POINT | 23 | 24 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | NMDC |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.12 | 0.34349 |  | RIG TANK | 89623
GEL ST. | 9/14 | 10/15 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | 18x 3 1/2" HWDP |  |  | 4.8125 | 2.25 |  | 3 1/2 IF |  | 169.92 | 6.3997 |  | CAMP TANK | 17593
WL (ml/30 min) | 3.8 | 3.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | DRL JAR |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.15 | 0.34462 |  | CONSUMED | 7482
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | 12x 3 1/2" HWDP |  |  | 4.8125 | 2.1875 |  | 3 1/2 IF |  | 113.19 | 4.2631 |  | RECEIVED | 0
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 107216
ALK (FILT.) | 0.3/1.3 | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 600487
MAX SHIELD % | 3 | 3 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 78000
KCl (%) | 5 | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 62120
KCl (mg/l) | 45760.8 | 45760.8 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 65400
CHLORIDES (mg/l) | 74000 | 74000 | JAR | 82.73 | STAB - 1 | 82.73 | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) | 380 | 380 | 3 1/2" HWDPS | 94.73 | PD ORBIT | 82.73 | TFA (IN²) |  |  | 0.6626 | [12 empty] | POB
PENETRAX % | 1.5 | 1.5 | 4 3/4" DCS |  | SPSA | 82.73 | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 321.71 |  |  | MPCL | 3
MAX GUARD % | 2 | 2 | DAILY BHA ROT. HRS |  | 5.16 |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 9 |  |  | MPCL SERV | 26
SOLIDS % | 21.39 | 21.08 | DAILY ON BOTTOM HRS |  | 2.52 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 8 |  |  | SECURITY
M.B.T. (lb/bbl) | 3.8 | 3.8 | DAILY CIRC. HRS |  | 6.28 |  | BIT NO. 20 RR4 |  |  | 3-3-HC-A-X-I-WT-PR |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 48
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 4
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4842.47/4820.57 |  | 26.39 |  | 290.39 |  |  | 2.53 |  | CHK SHT |  | TOTAL | 106
DAILY WELL COST (US$) |  | 42278 | SHAKER-2 | 3 x 140 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4848.66/4826.27 |  | 24.81 |  | 289.03 |  |  | 0.73 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 22648905 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4870.72/4846.41 |  | 23.39 |  | 287.64 |  |  | 2.08 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 113.8% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | 4900.74/4874.24 |  | 20.54 |  | 288.18 |  |  | 2.86 |  | MWD |  | FIT (EMW) | 2
[12 empty] | 4916.03/4888.58 |  | 20.21 |  | 285.21 |  |  | 2.13 |  | MWD |  | MAASP (PSI) | 2385
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4815 | 1000/1000 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4815 | 1500/1500 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-03-20 | 2020-04-19 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4815 | 2100/2100 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4773/4757
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4788/4770.97
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-03-23 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 10 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK | 4813/4794.01
STRETCHER DRILL | 2020-03-20 | 2020-04-19 | NEXT BOP TEST DATE |  | 2020-04-06 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 10 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4858/4834.66
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-03-23
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43913 | 43913.1771 | 4.25 | DRL | PT-P | DM | CONT'D DRILLING 6" HOLE FROM 4927M TO 4929M. OBSERVED LOW ROP, ATTEMPTED DIFFERENT PARAMETERS BUT ROP NOT IMPROVED. DECIDED TO POOH.
43913.1771 | 43913.2188 | 1 | DRL | PT-P | CIR | CIRCULATED TILL GEOLOGICAL SAMPLE SURFACED.
43913.2188 | 43913.25 | 0.75 | DRL | PT-P | RW | PUMPED OUT FROM 4929M TO 4796M (INSIDE CSG).
43913.25 | 43913.6667 | 10 | DRL | PT-P | POOH | PUMPED SLUG, POOH FROM 4796M TO 321M (TOP OF BHA).
43913.6667 | 43913.6771 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43913.6771 | 43913.7604 | 2 | DRL | PT-P | BHA | CONT'D POOH BHA FROM 321M TO SURFACE. MEANWHILE L/DOWN JAR & PDC BIT.
43913.7604 | 43913.9271 | 4 | DRL | PT-P | BOPT | M/U COMBINATION TOOL ASSY & RETRIEVED WEAR BUSHING. M/U TEST PLUG ASSEMBLY, SET TEST PLUG INSIDE 11'' THS. FLUSHED BOP STACK WITH WATER. P/T ANNULAR BOP @ 500/4500 PSI FOR 5/10 MIN - OK. P/T ROTARY HOSE & STANDPIPE MANIFOLD @ 500/6000 PSI FOR 5/10 MIN - OK. P/T UPPER VARIABLE PIPE RAMS (2 7/8" - 5"), LOWER PIPE RAMS, BLIND RAMS, HYD & MANUAL IBOP, FOSV, HCR & MANUAL VALVES @ KILL & CHOKE LINE, CHOKE MANIFOLD MASTER VALVE, CO-FLEXIP HOSE @ 500/9000 PSI FOR 5/10 MIN - OK. INSTALLED WEAR BUSHING & L/D TEST PLUG ASSEMBLY.
43913.9271 | 43914 | 1.75 | DRL | PT-P | BHA | P/UP AND M/UP NEW PD ORBIT + 6'' PDC BIT (NOV, SK613, SR # E260747, 6 X 12/32''). RIH AS PER BHA TO 20M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-03-24
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43914 | 43914.0208 | 0.5 | DRL | PT-P | E/C | FUNCTION TESTED DIRECTIONAL TOOLS AT 216 GPM, SPP = 900 PSI . DOWNLINKED PD, OK.
43914.0208 | 43914.0417 | 0.5 | DRL | PT-P | E/C | FUNCTION TESTED PBL SUB ON SURFACE, OK. OBSERVED INDICATION OF DEACTIVATION AT 3400 PSI. RECOVERED BALLS / DART FROM THE CATCHER.
43914.0417 | 43914.0833 | 1 | DRL | PT-P | BHA | CONT'D RIH BHA FROM 20M TO 351M. MEANWHILE ADDED NMDC AND D.JAR IN STRING. FLUSHED BHA.
43914.0833 | 43914.25 | 4 | DRL | PT-P | RIH | RIH FROM 351M TO 2216M. WHILE RIH FILLED UP STRING EVERY 15 STDS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA : SANDSTONE, CLAYSTONE, SHALE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | RIH WITH 6'' PDC + PD ORBIT IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 6" HOLE FROM 4927M TO 4929M. OBSERVED SLOW PENETRATION RATE, POOH AFTER GEOLOGICAL SAMPLES SURFACED, BOPT AS PER POLICY, P/UP AND M/UP NEW 6'' PDC + PD ORBIT AND RIH TO 20M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | FUNCTION TEST SLB DIRECTIONAL TOOLS & PBL SUB, RIH TO BTM AT 4929M AND RESUME DRILLING. DRILL AHEAD 6'' HOLE TILL WELL TD.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14