## DDR#326
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 326
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-03-25
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5506 / 5450 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | S. KHALID AZIM / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4938.64 | 4909.23 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 325.9792
RIG REP.: |  | TARIQ MAHMOOD BUTT / FAYYAZ HUSSAIN |  |  | MD/TVD @ 06:00HRS: |  | 4946 | 4917.15 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 9 METER
2020-03-24 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | RUN NO. |  |  | 66 |  | BHA NO. |  |  | 79 | IN (M) |  | 4929 |  | OUT (M) |  |  | STRING (BBL) | 230
CHECK TIME | 12:00 | 0:00 | MD @ 00:00HR (M) |  | 4938.64 |  | BIT NO. |  |  | 28 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 651.5
DEPTH, MD (M) | 4929 | 4938 | TVD @ 00:00HR (M) |  | 4909.23 |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 | 0.1 |  | PITS (BBL) | 290
MW IN (SG) | 1.65 | 1.65 | DAILY PROGRESS (M) |  | 9 |  | MANUFACTURER |  |  | NOV |  | PD ORBIT |  |  | 5 | 3.625 |  | 3 1/2 IF |  | 4.47 | 0.16835 |  | ACT. SYS (BBL) | 1171.5
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | SK613M |  | FLOAT SUB |  |  | 4.75 | 2.5 |  | 3 1/2 IF |  | 0.78 | 0.029377 |  | RESV. SYS (BBL) | 761
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 2.93 |  | SERIAL NO. |  |  | E260747 |  | L/ SAVER SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.45 | 0.016948 |  | KILL MUD (BBL) | 300
FL TEMP. °F |  | 111.2 | AVG. WOB (TON) |  | 2 |  | IADC CODE |  |  |  |  | SPSA |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 9.45 | 0.35592 |  | KILL MW (SG) | 2.2
µ FUNNEL (SEC) | 52 | 50 | AVG. RPM SURFACE |  | 80 |  | NOZZLES (1/32") |  |  | 6 x 12 |  | PBL SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 3.08 | 0.116 |  | TOTAL | 2232.5
PV | 25 | 26 | AVG. RPM DOWNHOLE |  | 80 |  | DEPTH IN (M) |  |  | 4929 |  | ST. STAB |  |  | 5.875 | 2.25 |  | 3 1/2 IF |  | 1.9 | 0.07156 |  | DIESEL (LTR)
YIELD POINT | 20 | 20 | FLOWRATE (GPM) |  | 250 |  | DEPTH OUT (M) |  |  |  |  | NMDC |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.12 | 0.34349 |  | RIG TANK | 84621
GEL ST. | 10/15 | 9/13 | PRESSURE (PSI) |  | 3600 - 3700 |  | METERAGE (M) |  |  | 9 |  | 18x 3 1/2" HWDP |  |  | 4.8125 | 2.25 |  | 3 1/2 IF |  | 169.92 | 6.3997 |  | CAMP TANK | 16958
WL (ml/30 min) | 4 | 4.2 | TORQ. ON-BTM (KLB-FT) |  | 3-4 |  | RPM SURF. |  |  | 80 |  | DRL JAR |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.15 | 0.34462 |  | CONSUMED | 5637
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 1-2.5 |  | RPM BTM. |  |  | 80 |  | 12x 3 1/2" HWDP |  |  | 4.8125 | 2.1875 |  | 3 1/2 IF |  | 113.19 | 4.2631 |  | RECEIVED | 0
ALK (MUD) | 0.4 | 0.5 | STRING WT. (TON) - ROT |  | 155 |  | WOB (TON) |  |  | 1-3 | [12 empty] | TOTAL | 101579
ALK (FILT.) | 0.3/1.3 | 0.3/1.4 | PICK-UP WT. (TON) |  | 160 |  | AVG. ROP (M/HR) |  |  | 2.9316 | [12 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  | 150 |  | BIT ROT HRS. |  |  | 3.07 | [12 empty] | RIG STORAGE | 620118
MAX SHIELD % | 3 | 3 | SLIMPULSE D & I OFF BIT - (M) |  | 10.6 |  | K-REVS IN 24 HRS |  |  | 14.92 | [12 empty] | CAMP STORAGE | 78000
KCl (%) | 5 | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  | 14.92 | [12 empty] | CONSUMED | 39450
KCl (mg/l) | 45760.8 | 45760.8 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  | 67.1 | [12 empty] | RECEIVED | 129200
CHLORIDES (mg/l) | 72000 | 70000 | JAR | 90.63 | STAB - 1 | 90.63 | JET VELOCITY (M/SEC) |  |  | 25.52 | [12 empty] | DRL WASTE | 92800
HARDNESS (mg/l) | 380 | 360 | 3 1/2" HWDPS | 102.63 | PD ORBIT | 7.9 | TFA (IN²) |  |  | 0.6626 | [12 empty] | POB
PENETRAX % | 1.5 | 2 | 4 3/4" DCS |  | SPSA | 7.9 | HSI |  |  | 0.45 |  | TOTAL LENGTH (M) | [7 empty] | 321.71 |  |  | MPCL | 3
MAX GUARD % | 2 | 2 | DAILY BHA ROT. HRS |  | 7.9 |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 9 |  |  | MPCL SERV | 29
SOLIDS % | 21.18 | 21.27 | DAILY ON BOTTOM HRS |  | 3.07 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 8 |  |  | SECURITY
M.B.T. (lb/bbl) | 3.8 | 3.8 | DAILY CIRC. HRS |  | 9.2 |  | BIT NO. |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 48
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 4
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4842.47/4820.57 |  | 26.39 |  | 290.39 |  |  | 2.53 |  | CHK SHT |  | TOTAL | 109
DAILY WELL COST (US$) |  | 69460 | SHAKER-2 | 3 x 140 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4848.66/4826.27 |  | 24.81 |  | 289.03 |  |  | 0.73 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 22718365 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4870.72/4846.41 |  | 23.39 |  | 287.64 |  |  | 2.08 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 114.1% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | 4900.74/4874.24 |  | 20.54 |  | 288.18 |  |  | 2.86 |  | MWD |  | FIT (EMW) | 2
[12 empty] | 4916.03/4888.58 |  | 20.21 |  | 285.21 |  |  | 2.13 |  | MWD |  | MAASP (PSI) | 2385
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4925 | 1200/1220 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4925 | 1700/1750 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-03-20 | 2020-04-19 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4925 | 2500/2500 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4773/4757
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4788/4770.97
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-03-23 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 12 | MUD LOSSES IN 24 HRS |  |  | 110 |  | MUD LOSSES |  |  |  | 110 |  | KUSSAK | 4813/4794.01
STRETCHER DRILL | 2020-03-20 | 2020-04-19 | NEXT BOP TEST DATE |  | 2020-04-06 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 12 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4858/4834.66
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-03-24
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43914 | 43914.0208 | 0.5 | DRL | PT-P | E/C | FUNCTION TESTED DIRECTIONAL TOOLS AT 216 GPM, SPP = 900 PSI . DOWNLINKED PD, OK.
43914.0208 | 43914.0417 | 0.5 | DRL | PT-P | E/C | FUNCTION TESTED PBL SUB ON SURFACE, OK. OBSERVED INDICATION OF DEACTIVATION AT 3400 PSI. RECOVERED BALLS / DART FROM THE CATCHER.
43914.0417 | 43914.0833 | 1 | DRL | PT-P | BHA | CONT'D RIH BHA FROM 20M TO 351M. MEANWHILE ADDED NMDC AND D.JAR IN STRING. FLUSHED BHA.
43914.0833 | 43914.5104 | 10.25 | DRL | PT-P | RIH | RIH FROM 351M TO 4795M. MEANWHILE FILLED UP STRING EVERY 15 STDS.
43914.5104 | 43914.5625 | 1.25 | DRL | NPT-P | RS | SLIPPED AND CUT 30M D. LINE. ADJUSTED ACS & CROWN O MATIC.
43914.5625 | 43914.5729 | 0.25 | DRL | PT-P | RIH | CONT'D RIH FROM 4795M TO 4882M.
43914.5729 | 43914.6458 | 1.75 | DRL | PT-P | RW | PRECAUTIONARY WASHED/REAMED FROM 4882M TO TAG BTM AT 4929M.
43914.6458 | 43914.7917 | 3.5 | DRL | PT-P | DM | COMMENCED DRILLING AFTER BREAK IN THE BIT. DRILLED 6'' DIRECTIONAL HOLE FROM 4929M TO 4938M. OBSERVED COMPLETE LOSS AT 4938.64M.
43914.7917 | 43914.8229 | 0.75 | DRL | NPT-UP | RW | PUMPED OUT FROM 4938M TO 4873M. CIRCULATED & OBSERVED LOSSES AT DIFFERENT FLOW RATES, OBSERVED NO LOSS.
43914.8229 | 43914.8646 | 1 | DRL | NPT-UP | RW | WAHSED / REAMED DOWN FROM 4873M TO 4917M, MEANWHILE PREPARED LCM PILL.
43914.8646 | 43914.9062 | 1 | DRL | NPT-UP | SP | SPOTTED 50 BBL (40 PPB, ND) PILL AT 4938M, WHILE DISPLACING LCM PILL OBSERVED COMPLETE LOSS.
43914.9062 | 43914.9375 | 0.75 | DRL | NPT-UP | RW | PUMPED OUT FROM 4938M TO 4805M (INSIDE CSG).
43914.9375 | 43914.9792 | 1 | DRL | NPT-UP | OTH | ALLOWED SOAKING TIME FOR LCM PILL MEANWHILE MONITORED WELL ON TRIP TANK. OBSERVED WELL STATIC.
43914.9792 | 43915 | 0.5 | DRL | NPT-UP | RW | PUMPED ANOTHER 50 BBL (40 PPB, ND) LCM PILL. MEANWHILE WASHED DOWN FROM 4805M TO 4920M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-03-25
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43915 | 43915.0417 | 1 | DRL | NPT-UP | RW | CONT'D WASHED / REAMED DOWN FROM 4920M TO 4938M, OBSERVED NO LOSS AT 150 GPM.
43915.0417 | 43915.1667 | 3 | DRL | PT-P | DM | HESITANTLY TAGGED BTM AT 4938.64M, DRILLED 6'' DIRECTIONAL HOLE FROM 4938.64M TO 4943M WITH CONTROL PARAMETERS. OBSERVED PARTIAL LOSSES DURING DRILLING. WHILE DRILLING AT 4943M OBSERVED ROP BREAK.
43915.1667 | 43915.1771 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43915.1771 | 43915.25 | 1.75 | DRL | PT-P | DM | RESUMED DRILLING, DRILLED AHEAD 6'' HOLE FROM 4943M TO 4946M. MEANWHILE REDUCED MUD DENSITY FROM 1.65 SG TO 1.64 SG.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA : SANDSTONE, CLAYSTONE, SHALE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 6'' DIRECTIONAL HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | FUNCTION TESTED SLB DIRECTIONAL TOOLS & PBL SUB, OK RIH TO 4795M, SLIPPED AND CUT DRILL LINE, CONT'D RIH TO BTM AT 4929M, RESUMED DRILLING, DRILLED AHEAD 6'' HOLE TO 4938M, OBSERVED COMPLETE LOSSES, SPOTTED LCM PILL, ATTEMPTING TO CURE LOSSES IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CURE LOSSES, DRILL AHEAD 6'' HOLE TILL WELL TD.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14