## DDR#327
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 327
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-11-13
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / M. MOHSIN ALI |  |  | MD/TVD @ 00:00HRS: |  | 4746 / 4454.82 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 110.13
RIG REP. (TP): |  | JAVED IQBAL / FAYYAZ HUSSAIN |  |  | MD/TVD @ 06:00HRS: |  | 4746 / 4454.82 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 4
2018-11-12 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | BIT NO. |  | 23 |  | BHA No. |  |  | 51 | IN (M) |  | 4730 |  | OUT (M) |  |  | STRING (BBL) | 179
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 4746 |  | SIZE (IN) |  | 6 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 675.7
DEPTH, MD (M) | 4746 | 4746 | TVD @ 00:00HR (M) |  | 4454.82 |  | MANUFACTURER |  | HALLIBURTON |  | 6'' PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.27 |  |  | PITS (BBL) | 670
MW IN (SG) | 1.7 | 1.7 | DAILY PROGRESS (M) |  | 4 |  | TYPE |  | GT64D |  | BIT SUB |  |  | 4.75 | 2 |  | 3 1/2 REG |  | 1.07 | 0.079643 |  | ACT. SYS (BBL) | 1548.5
MW OUT (SG) | 1.7 | 1.7 | INST. ROP (M/HR) |  | - |  | SERIAL NO. |  | 12919090 |  | ST. STAB |  |  | 5.875 | 2.25 |  | 3 1/2 IF |  | 1.81 | 0.13472 |  | RESV. SYS (BBL) | 240
ECD (SG) | - | - | AVG. ROP (M/HR) |  | 2.17 |  | IADC CODE |  | M434 |  | 1X DC |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 9.22 | 0.68627 |  | KILL MUD (BBL) | 800
FL TEMP. °F | - | - | AVG. WOB (TON) |  | 1-4 |  | NOZZLES (1/32") |  | 3 X 14 |  | ST. STAB |  |  | 5.875 | 2.25 |  | 3 1/2 IF |  | 1.97 | 0.14663 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 52 | 53 | AVG. RPM SURFACE |  | 110 |  | DEPTH IN (M) |  | 4730 |  | 11 X DC's |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 101.79 | 7.5765 |  | TOTAL | 2588.5
PV | 26 | 26 | AVG. RPM DOWNHOLE |  | 110 |  | DEPTH OUT (M) |  |  |  | 3 X HWDP |  |  | 4.6875 | 2.25 |  | 3 1/2 IF |  | 28.29 | 1.0529 |  | DIESEL (LTR)
YIELD POINT | 21 | 20 | FLOWRATE (GPM) |  | 250 |  | METERAGE (M) |  | 16 |  | D.JAR |  |  | 4.75 | 2.375 |  | 3 1/2 IF |  | 9.1 | 0.67734 |  | RIG TANK | 83485
GEL ST. | 8/12 | 8/11 | PRESSURE (PSI) |  | 3200-3350 |  | RPM SURF. |  | 110 |  | 18 X HWDP |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.92 | 6.3238 |  | CAMP TANK | 24255
WL (ml/30 min.) | 3 | 2.9 | TORQ. ON-BTM (KLB-FT) |  | 5-7 |  | RPM BTM. |  | 110 | [12 empty] | CONSUMED | 8175
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 4-5 |  | WOB (TON) |  | 1-4 | [12 empty] | RECEIVED
ALK (MUD) | 0.6 | 0.6 | STRING WT. (TON) - ROT |  | 140 |  | AVG. ROP (M/HR) |  | 2.2253 | [12 empty] | TOTAL | 107740
ALK (FILT.) | 0.3 | 0.3 | PICK-UP WT. (TON) |  | 150 |  | BIT ROT HRS. |  | 7.19 | [12 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 133 |  | K-REVS IN 24 HRS |  | 35.31 | [12 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  | 35.31 | [12 empty] | CAMP STORAGE | 45000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 70.72 | [12 empty] | CONSUMED | 91000
KCl (mg/l) | 59107.7 | 59107.7 | JAR | 16.4 | STAB - 1 | 16.4 | JET VELOCITY (M/SEC) |  | 57.3 | [12 empty] | RECEIVED | 141000
CHLORIDES | 34000 | 34000 | 3 1/2" HWDPS | 16.4 | STAB - 2 |  | TFA (IN²) |  | 0.45 | [12 empty] | TOTAL | 445000
CALCIUM | 280 | 260 | 4 3/4" DCS | 16.4 | NMDC |  | HSI |  | 2.5 | [12 empty] | POB
OIL % | 6 | 6 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 323.44 |  |  | MPCL | 4
LUBE % | 2 | 2 | BHA ROT. HRS |  | 16.4 |  | BIT NO. 22RR2 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 12 |  |  | MPCL SERV | 14
SOLIDS % | 25.65 | 25.65 | ON BOTTOM HRS |  | 7.19 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 7 |  |  | SECURITY | 4
M.B.T. | 5 | 5 | CIRC. HRS |  | 25.75 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 50
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 22
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 120 | 2 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4647/4382.61 |  | 42.19 |  | 81.49 |  |  | 1.83 |  | MWD |  | TOTAL | 102
DAILY WELL COST (US$) |  | 45982.085 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4676/4403.94 |  | 43.13 |  | 83.16 |  |  | 1.52 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 20025379.6153 | SHAKER-3 | 1 x 120 | 2 x 120 |  | 7" LINER |  |  | 4446 (TOL @ 3253) | 4701/4422.05 |  | 43.98 |  | 82.8 |  |  | 1.06 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 111% | MUD CLEANER | 1 x 140 | 2 x 170 | [5 empty] | 4713/4430.68 |  | 44.03 |  | 82.27 |  |  | 0.93 |  | MWD |  | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P3) | [5 empty] | MAASP (PSI) | 300
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 |  | 30 |  | 4730 |  | 905 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4730 |  | 1250 |  | HANGU | 4571/4323.65
FIRE DRILL | 2018-11-08 | 2018-12-08 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 |  | 50 |  | 4730 |  | 1680 |  | DHANDOT-TOBRA | 4587/4333.72
PIT DRILL | 2018-11-08 | 2018-11-23 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BHAGANWALA | 4608/4354.35
KICK DRILL | 2018-10-07 | 2018-11-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | JUTANA | 4627/4367.58
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-11-11 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  | 312 |  | MUD LOSSES |  |  |  | 402 |  | KUSSAK | 4657/4390.03
STRETCHER DRILL | 2018-11-08 | 2018-12-08 | NEXT BOP TEST DATE |  | 2018-11-25 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4724/4438.61
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-12
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43416 | 43416.0833 | 2 | DRL | PT-P | D | DRILLED 6" HOLE FROM 4741M TO 4746M. OBSERVED DYNAMIC LOSSES INCREASED TO 50 BBL/HR. PUMPED 30 BBL LCM PILL (75 PPB) @ 4745M. OBSERVED DYNAMIC LOSSES FURTHER INCREASED TO 100 BBL/HR. STOPPED DRILLING.
43416.0833 | 43416.1042 | 0.5 | DRL | NPT-UP | FC | MONITORED WELL THRU TRIP TANK FOR STATIC LOSSES. OBSERVED STATIC LOSSES @ 80 BBL/HR.
43416.1042 | 43416.1771 | 1.75 | DRL | NPT-UP | RW | PUMPED OUT FROM 4746M TO 4436M (INSIDE 7" LINER).
43416.1771 | 43416.2917 | 2.75 | DRL | NPT-UP | FC | MONITORED WELL THRU TRIP TANK. OBSERVED STATIC LOSSES @ 16 BBL/HR.
43416.2917 | 43416.3021 | 0.25 | DRL | NPT-UP | RIH | RIH FROM 4436M TO 4536M.
43416.3021 | 43416.3438 | 1 | DRL | NPT-UP | SP | PUMPED 40 BBL LCM PILL (90 PPB) & DISPLACED OUT OF BIT. LOST 18 BBL DURING SPOTTING LCM PILL.
43416.3438 | 43416.3646 | 0.5 | DRL | NPT-UP | POOH | POOH FROM 4536M TO 4433M (INSIDE 7" LINER).
43416.3646 | 43416.4167 | 1.25 | DRL | NPT-UP | FC | ALLOWED SOAKING TIME TO LCM PILL & MONITORED WELL THRU TRIP TANK FOR STATIC LOSSES. OBSERVED STATIC LOSS REDUCED FROM 4 BBL/HR TO 2 BBL/HR. MEANWHILE REDUCED SURFACE MUD VOLUME WEIGHT FROM 1.75 SG TO 1.70 SG.
43416.4167 | 43416.5729 | 3.75 | DRL | NPT-UP | CIR | CIRCULATED & HOMOGENIZED WHOLE MUD SYSTEM TO 1.70 SG.
43416.5729 | 43416.6042 | 0.75 | DRL | NPT-UP | CIR | CIRCULATED @ 245 GPM & MONITORED WELL FOR DYNAMIC LOSSES. OBSERVED NO DYNAMIC LOSS.
43416.6042 | 43416.8021 | 4.75 | DRL | NPT-UP | RW | REAMED DOWN FROM 4448M TO 4738M. REAMED 4530M - 4555M INTERVAL SEVERAL TIMES.
43416.8021 | 43416.8229 | 0.5 | DRL | NPT-UP | D | PUMPED 30 BBL LCM PILL (80 PPB) & STARTED DRILLING. OBSERVED TOTAL LOSS. STOPPED DRILLING. LOST 30 BBL.
43416.8229 | 43416.8438 | 0.5 | DRL | NPT-UP | SP | POOH FROM TO 4700M AND DISPLACED LCM PILL OUT OF BIT. LOST 28 BBL.
43416.8438 | 43416.8958 | 1.25 | DRL | NPT-UP | RW | PUMPED OUT FROM 4700M TO 4530M. LOST 12 BBL.
43416.8958 | 43416.9375 | 1 | DRL | NPT-UP | SP | PUMPED 50 BBL LCM PILL (100 PPB) & DISPLACED OUT OF BIT. LOST 30 BBL DURING SPOTTING LCM PILL.
43416.9375 | 43416.9479 | 0.25 | DRL | NPT-UP | POOH | POOH FROM 4536M TO 4443M (INSIDE 7" LINER). OBSERVED NO LOSS.
43416.9479 | 43416.9583 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - OBSERVED NO LOSS.
43416.9583 | 43417 | 1 | DRL | NPT-UP | POOH | POOH FROM 4443M TO 4097M. OBSERVED NO LOSS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-13
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43416 | 43416.0208 | 0.5 | DRL | NPT-UP | CIR | CIRCULATED @ 245 GPM & MONITORED WELL FOR DYNAMIC LOSSES. OBSERVED NO DYNAMIC LOSS.
43416.0208 | 43416.25 | 5.5 | DRL | NPT-UP | POOH | POOH FROM 4097M TO 1617M. OBSERVED NO LOSS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA / SANDSTONE & CLAYSTONE
OPERATIONS AT 06:00 HRS |  |  | POOH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 6" HOLE FROM 4741M TO 4746M. OBSERVED DYNAMIC LOSSES WHILE DRILLING. STOPPED DRILLING. PUMPED OUT TO 7" LINER SHOE. RIH TO 4536M & PUMPED LCM PILL. POOH TO 7" LINER SHOE. REDUCED MUD SYSTEM WEIGHT TO 1.70 SG. REAMED DOWN FROM 4448M TO 4738M. PUMPED LCM PILL & STARTED DRILLING. OBSERVED TOTAL LOSS. POOH TO 4700M AND DISPLACED LCM PILL. POOH TO 4530M. PUMPED LCM PILL & POOH TO 4097M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE. REPLACE BIT, RIH TO BOTTOM, CURE LOSSES AND DRILL AHEAD 6" HOLE SECTION.
REMARKS
Formulas:
DHARIAN-1-ST-3 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14