## DDR#329
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 329
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-11-15
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / M. MOHSIN ALI |  |  | MD/TVD @ 00:00HRS: |  | 4766 / 4469.21 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 112.13
RIG REP. (TP): |  | JAVED IQBAL / FAYYAZ HUSSAIN |  |  | MD/TVD @ 06:00HRS: |  | 4770 / 4472.09 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 20
2018-11-14 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | BIT NO. |  | 24 |  | BHA No. |  |  | 52 | IN (M) |  | 4746 |  | OUT (M) |  |  | STRING (BBL) | 215.6
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 4766 |  | SIZE (IN) |  | 6 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 625.6
DEPTH, MD (M) | 4760 | 4766 | TVD @ 00:00HR (M) |  | 4469.21 |  | MANUFACTURER |  | SMITH |  | TCI BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.19 |  |  | PITS (BBL) | 680
MW IN (SG) | 1.7 | 1.7 | DAILY PROGRESS (M) |  | 20 |  | TYPE |  | XR30TODPS |  | BIT SUB |  |  | 4.75 | 2 |  | 3 1/2 REG |  | 1.07 | 0.079643 |  | ACT. SYS (BBL) | 1521.2
MW OUT (SG) | 1.7 | 1.7 | INST. ROP (M/HR) |  | 1.15 |  | SERIAL NO. |  | RJ5735 |  | 1X DC |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 9.22 | 0.68627 |  | RESV. SYS (BBL) | 305
ECD (SG) | 1.76 | 1.76 | AVG. ROP (M/HR) |  | 1.15 |  | IADC CODE |  | 537X |  | ST. STAB |  |  | 5.875 | 2.25 |  | 3 1/2 IF |  | 1.97 | 0.14663 |  | KILL MUD (BBL) | 700
FL TEMP. °F | 119 | 119 | AVG. WOB (TON) |  | 3-5 |  | NOZZLES (1/32") |  | OPEN |  | 11 X DC's |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 101.79 | 7.5765 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 51 | 53 | AVG. RPM SURFACE |  | 95 |  | DEPTH IN (M) |  | 4746 |  | 3 X HWDP |  |  | 4.6875 | 4.25 |  | 3 1/2 IF |  | 28.29 | 2.1057 |  | TOTAL | 2526.2
PV | 30 | 29 | AVG. RPM DOWNHOLE |  | 95 |  | DEPTH OUT (M) |  |  |  | D. JAR |  |  | 4.75 | 5.25 |  | 3 1/2 IF |  | 9.1 | 0.33867 |  | DIESEL (LTR)
YIELD POINT | 19 | 20 | FLOWRATE (GPM) |  | 182-214 |  | METERAGE (M) |  | 20 |  | 18 X HWDP |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.85 | 12.6424 |  | RIG TANK | 110897
GEL ST. | 7/11 | 8/12 | PRESSURE (PSI) |  | 1750-2350 |  | RPM SURF. |  | 95 | [12 empty] | CAMP TANK | 23259
WL (ml/30 min.) | 2.8 | 2.9 | TORQ. ON-BTM (KLB-FT) |  | 5-7 |  | RPM BTM. |  | 95 | [12 empty] | CONSUMED | 6307
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 4-5 |  | WOB (TON) |  | 3-5 | [12 empty] | RECEIVED
ALK (MUD) | 0.6 | 0.6 | STRING WT. (TON) - ROT |  | 144 |  | AVG. ROP (M/HR) |  | 1.1494 | [12 empty] | TOTAL | 134156
ALK (FILT.) | 0.3 | 0.3 | PICK-UP WT. (TON) |  | 152 |  | BIT ROT HRS. |  | 17.4 | [12 empty] | WATER (LTR)
PH | 10 | 10 | SLACK-OFF WT. (TON) |  | 133 |  | K-REVS IN 24 HRS |  | 100.06 | [12 empty] | RIG STORAGE | 350000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  | 100.06 | [12 empty] | CAMP STORAGE | 45000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 66.74 | [12 empty] | CONSUMED | 30000
KCl (mg/l) | 59107.7 | 59107.7 | JAR | 40.63 | STAB - 1 | 40.63 | JET VELOCITY (M/SEC) |  | 10.3 | [12 empty] | RECEIVED | 30000
CHLORIDES | 32000 | 32000 | 3 1/2" HWDPS | 40.63 | STAB - 2 |  | TFA (IN²) |  | 2.2 | [12 empty] | TOTAL | 395000
CALCIUM | 280 | 280 | 4 3/4" DCS | 40.63 | NMDC |  | HSI |  | 0.1 | [12 empty] | POB
OIL % | 5 | 5 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 321.48 |  |  | MPCL | 4
LUBE % | 2 | 2 | BHA ROT. HRS |  | 40.63 |  | BIT NO. 23 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 12 |  |  | MPCL SERV | 13
SOLIDS % | 24.69 | 24.69 | ON BOTTOM HRS |  | 17.39 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 7 |  |  | SECURITY | 4
M.B.T. | 5 | 5 | CIRC. HRS |  | 26.7 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 50
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 120 | 2 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4647/4382.61 |  | 42.19 |  | 81.49 |  |  | 1.83 |  | MWD |  | TOTAL | 104
DAILY WELL COST (US$) |  | 33966.85 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4676/4403.94 |  | 43.13 |  | 83.16 |  |  | 1.52 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 20096908.8653 | SHAKER-3 | 1 x 120 | 2 x 120 |  | 7" LINER |  |  | 4446 (TOL @ 3253) | 4701/4422.05 |  | 43.98 |  | 82.8 |  |  | 1.06 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 111.3% | MUD CLEANER | 1 x 140 | 2 x 170 | [5 empty] | 4713/4430.68 |  | 44.03 |  | 82.27 |  |  | 0.93 |  | MWD |  | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P3) | [5 empty] | MAASP (PSI) | 600
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 |  | 30 |  | 4756 |  | 675 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4756 |  | 975 |  | HANGU | 4571/4323.65
FIRE DRILL | 2018-11-14 | 2018-12-14 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 |  | 50 |  | 4756 |  | 1330 |  | DHANDOT-TOBRA | 4587/4333.72
PIT DRILL | 2018-11-14 | 2018-11-29 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BHAGANWALA | 4608/4354.35
KICK DRILL | 2018-10-07 | 2018-11-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | JUTANA | 4627/4367.58
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-11-11 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  | 0 |  | MUD LOSSES |  |  |  | 402 |  | KUSSAK | 4657/4390.03
STRETCHER DRILL | 2018-11-08 | 2018-12-08 | NEXT BOP TEST DATE |  | 2018-11-25 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4724/4438.61
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-14
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43418 | 43418.0938 | 2.25 | DRL | NPT-UP | RW | HARD REAMED DOWN FROM 4728M TO 4746M. PUMPED 30 BBL LCM PILL (90 PPB) WHILE REAMING @ 4744M.
43418.0938 | 43419 | 21.75 | DRL | PT-P | D | TAGGED BOTTOM @ 4746M. BROKE IN BIT & DRILLED 6" HOLE FROM 4746M TO 4766M. NO LOSSES OBSERVED DURING DRILLING.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-15
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43419 | 43419.2292 | 5.5 | DRL | PT-P | D | DRILLED 6" HOLE FROM 4766M TO 4770M. NO LOSSES OBSERVED DURING DRILLING. OBSERVED ERRATIC TORQUE @ 4770M. STOPPED DRILLING & DECIDED TO POOH.
43419.2292 | 43419.25 | 0.5 | DRL | PT-P | CIR | CIRCULATION TO CLEAN HOLE IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA / SANDSTONE & CLAYSTONE
OPERATIONS AT 06:00 HRS |  |  | CIRCULATION TO CLEAN HOLE IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | HARD REAMED DOWN FROM 4728M TO 4746M. DRILLED 6" HOLE FROM 4746M TO 4766M
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CIRCULATE TO CLEAN HOLE. POOH TO SURFACE. CHANGE BIT. RIH TO BOTTOM & DRILL AHEAD 6" HOLE SECTION.
REMARKS
Formulas:
DHARIAN-1-ST-3 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14