## DDR#332
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 332
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-11-18
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / MUHAMMAD AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 4770 / 4472.09 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 115.13
RIG REP. (TP): |  | JAVED IQBAL / FAYYAZ HUSSAIN |  |  | MD/TVD @ 06:00HRS: |  | 4770 / 4472.09 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-11-17 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 17
CHECK TIME |  | 13:00 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 899
DEPTH, MD (M) |  | 4770 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  |  |  | SMS-MULE SHOE |  |  | 4.75 | 2.6 |  | 3 1/2 IF |  | 0.48 |  |  | PITS (BBL) | 692
MW IN (SG) |  | 1.7 | DAILY PROGRESS (M) |  |  |  | TYPE |  |  |  | LANDING / CIR. SUB |  |  | 4.75 | 2.4 |  | 3 1/2 IF |  | 2.49 |  |  | ACT. SYS (BBL) | 1608
MW OUT (SG) |  | - | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  | 3 1/2" GARAGE PIPE |  |  | 3.5 | 2.7 |  | 3 1/2 IF |  | 43.22 |  |  | RESV. SYS (BBL) | 204
ECD (SG) |  | - | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | LOWER LATCH |  |  | 4.75 | 2.56 |  | 3 1/2 IF |  | 1.68 |  |  | KILL MUD (BBL) | 650
FL TEMP. °F |  | - | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  |  |  | UPPER LATCH |  |  | 4.75 | 2.56 |  | 3 1/2 IF |  | 1.37 |  |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 57 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  |  | 3 1/2" DP |  |  | 3.5 | 2.56 |  | 3 1/2 IF |  | 5.01 |  |  | TOTAL | 2462
PV |  | 29 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 3 1/2" FLOAT VALVE |  |  | 3.5 | 2.5 |  | 3 1/2 IF |  | 0.71 |  |  | DIESEL (LTR)
YIELD POINT |  | 19 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 135063
GEL ST. |  | 7/11 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 21705
WL (ml/30 min.) |  | 2.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 5705
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED | 40000
ALK (MUD) |  | 0.6 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 156768
ALK (FILT.) |  | 0.3 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 10 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 350000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 35000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 80000
KCl (mg/l) |  | 59107.7 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 30000
CHLORIDES |  | 32000 | 3 1/2" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 385000
CALCIUM |  | 280 | 4 3/4" DCS |  | NMDC |  | HSI | [14 empty] | POB
OIL % |  | 5 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 54.96 |  |  | MPCL | 4
LUBE % |  | 2 | BHA ROT. HRS |  |  |  | BIT NO. |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 19
SOLIDS % |  | 24.69 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. |  | 5 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 120 | 2 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4647/4382.61 |  | 42.19 |  | 81.49 |  |  | 1.83 |  | MWD |  | TOTAL | 109
DAILY WELL COST (US$) |  | 30015.55 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4676/4403.94 |  | 43.13 |  | 83.16 |  |  | 1.52 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 20190838.8453 | SHAKER-3 | 1 x 120 | 2 x 120 |  | 7" LINER |  |  | 4446 (TOL @ 3253) | 4701/4422.05 |  | 43.98 |  | 82.8 |  |  | 1.06 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 111.9% | MUD CLEANER | 1 x 140 | 2 x 170 | [5 empty] | 4713/4430.68 |  | 44.03 |  | 82.27 |  |  | 0.93 |  | MWD |  | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P3) | [5 empty] | MAASP (PSI) | 600
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | HANGU | 4571/4323.65
FIRE DRILL | 2018-11-14 | 2018-12-14 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 | [7 empty] | DANDOT-TOBRA | 4587/4333.72
PIT DRILL | 2018-11-14 | 2018-11-29 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BHAGANWALA | 4608/4354.35
KICK DRILL | 2018-10-07 | 2018-11-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | JUTANA | 4627/4367.58
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-11-11 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  | 0 |  | MUD LOSSES |  |  |  | 402 |  | KUSSAK | 4657/4390.03
STRETCHER DRILL | 2018-11-08 | 2018-12-08 | NEXT BOP TEST DATE |  | 2018-11-25 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4724/4438.61
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-17
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43421 | 43421.4583 | 11 | DRL | NPT-UP | POOH | POOH MILL BIT FROM 3246M TO TOP OF BHA @ 322M. DURING POOH L/D 138 X 3 1/2" G-105 15.5 PPF DPS.
43421.4583 | 43421.4688 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43421.4688 | 43421.5312 | 1.5 | DRL | NPT-UP | BHA | POOH FROM 322M TO SURFACE. L/D BIT SUB, JUNK SUB & MILL BIT. RECOVERED 1.60 KG JUNK FROM JUNK SUB.
43421.5312 | 43421.5417 | 0.25 | EVAL | PT-P | SM | HELD PJSM FOR W.F CWS LOGGING.
43421.5417 | 43421.75 | 5 | EVAL | PT-P | TCL | P/U, ASSEMBLED & RIH W.F LOGGING TOOLS & BHA FOR CWS LOG # 1 (RESISTIVITY+SONIC+GR) TO 54M. SURFACE TESTED CONNECTIVITY OF TOOLS, FOUND OK.
43421.75 | 43422 | 6 | EVAL | PT-P | TCL | RIH W.F CWS LOGGING TOOLS ON 3 1/2" DPS FROM 54M TO 827M. WHILE RIH P/U 69 X 3 1/2" G-105 13.3 PPF DPS SINGLE BY SINGLE FROM PIPE RACKS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-18
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43422 | 43422.25 | 6 | EVAL | PT-P | TCL | CONT'D RIH W.F CWS LOGGING TOOLS ON 3 1/2" DPS FROM 827M TO 2433M. WHILE RIH FILLED UP STRING WITH MUD.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA / SANDSTONE & CLAYSTONE
OPERATIONS AT 06:00 HRS |  |  | RIH W.F CWS LOGGING TOOLS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH MILL BIT FROM 3246M TO SURFACE & RECOVERED 1.60 KG JUNK FROM JUNK SUB. M/U & RIH W.F LOGGING TOOLS FOR CWS LOG # 1 (RESISTIVITY+SONIC+GR) TO 827M ON 3 1/2" DPS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RECORD W.F CWS LOG # 1 (RESISTIVITY+SONIC+GR) AS PER PROGRAM.
REMARKS |  |  | W.F CWS LOGGING TOOLS BATTERY SWITCHED ON @ 1700 HRS ON 17-11-2018 (BATTERY LIFE: 16 HRS & 40 MIN IN SLEEP MODE + 25 HRS IN RECORDING MODE = 41 HRS 40 MIN).
Formulas:
DHARIAN-1-ST-3 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14