## DDR#332
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 332
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-03-31
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5506 / 5450 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | S. KHALID AZIM / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4976.2 | 4944.79 |  |  | WELL TD |  |  | DAYS SINCE SPUD: | [6 empty] | 331.9792
RIG REP.: |  | TARIQ MAHMOOD BUTT / FAYYAZ HUSSAIN |  |  | MD/TVD @ 06:00HRS: |  | 4976.2 | 4944.79 | [5 empty] | DAILY PROGRESS @ 00:00HRS:
2020-03-30 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 16:00 | 0:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 983.1
DEPTH, MD (M) |  | 4976 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) | [15 empty] | PITS (BBL) | 385
MW IN (SG) |  | 1.63 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER | [15 empty] | ACT. SYS (BBL) | 1368.1
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE | [15 empty] | RESV. SYS (BBL) | 416
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. | [15 empty] | KILL MUD (BBL) | 160
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE | [15 empty] | KILL MW (SG) | 2.2
µ FUNNEL (SEC) |  | 58 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") | [15 empty] | TOTAL | 1944.1
PV |  | 30 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [15 empty] | DIESEL (LTR)
YIELD POINT |  | 28 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 141680
GEL ST. |  | 11/17 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 27572
WL (ml/30 min) |  | 3.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 4756
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) |  | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 169252
ALK (FILT.) |  | 0.3/1.2 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH |  | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 585076
MAX SHIELD % |  | 3 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 72000
KCl (%) |  | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 47500
KCl (mg/l) |  | 45760 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 65400
CHLORIDES (mg/l) |  | 72000 | JAR | 6.92 | STAB - 1 | 119.51 | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | 162400
HARDNESS (mg/l) |  | 340 | 3 1/2" HWDPS | 131.51 | STAB - 2 | 6.92 | TFA (IN²) | [15 empty] | POB
PENETRAX % |  | 2 | 4 3/4" DCS | 18.92 | SPSA |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 0 |  |  | MPCL | 3
MAX GUARD % |  | 2 | DAILY BHA ROT. HRS |  |  |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 29
SOLIDS % |  | 20.13 | DAILY ON BOTTOM HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) |  | 3.8 | DAILY CIRC. HRS |  |  |  | BIT NO. |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 47
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 4
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4870.72/4846.41 |  | 23.39 |  | 287.64 |  |  | 2.08 |  | MWD |  | TOTAL | 108
DAILY WELL COST (US$) |  | 29230 | SHAKER-2 | 3 x 140 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4900.74/4874.24 |  | 20.54 |  | 288.18 |  |  | 2.86 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 22998123 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4916.03/4888.58 |  | 20.21 |  | 285.21 |  |  | 2.13 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 115.5% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | 4934.58/4905.93 |  | 20.45 |  | 288.74 |  |  | 0.31 |  | MWD |  | FIT (EMW) | 2
[12 empty] | 4962.88/4932.45 |  | 20.39 |  | 287.81 |  |  | 0.35 |  | MWD |  | MAASP (PSI) | 2520
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4925 | 1200/1220 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4925 | 1700/1750 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-03-20 | 2020-04-19 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4925 | 2500/2500 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4773/4757
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4788/4770.97
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-03-23 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 11 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 250 |  | KUSSAK | 4813/4794.01
STRETCHER DRILL | 2020-03-20 | 2020-04-19 | NEXT BOP TEST DATE |  | 2020-04-06 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4858/4834.66
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-03-30
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43920 | 43920.1771 | 4.25 | EVAL | NPT-UP | RIH | CONT'D RIH FROM 1271M TO 3397M (TOL).
43920.1771 | 43920.1875 | 0.25 | EVAL | NPT-UP | CIR | BROKE CIRCULATION.
43920.1875 | 43920.3438 | 3.75 | EVAL | NPT-UP | RIH | CONT'D RIH FROM 3397M TO 4829M. MEANWHILE FILLED UP STRING (INSIDE LINER) & RECORDED STRING WEIGHTS.
43920.3438 | 43920.375 | 0.75 | EVAL | NPT-UP | RW | WASHED DOWN FROM 4829M TO TAG TOP OF FISH @ 4885.5M.
43920.375 | 43920.3958 | 0.5 | EVAL | NPT-UP | F | P/UP STRING, RIH SLOWLY AND RECONFIRMED TOF = 4885.5M. AS PER SLB W/LINE ENGR's INSTRUCTIONS, ATTEMPTED TO LATCH FISH WITH 2-3 TON COMPRESSION. TURNED ON PUMP ON SLOW SPM, OBSERVED MINOR INDICATION OF SPP. (SUSPECTED FISH LATCHED)
43920.3958 | 43920.4271 | 0.75 | EVAL | NPT-UP | POOH | POOH SLB OVERSHOT ASSEMBLY FROM 4885M TO 4815M (INSIDE LINER).
43920.4271 | 43920.4375 | 0.25 | EVAL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43920.4375 | 43920.6146 | 4.25 | EVAL | NPT-UP | POOH | POOH FROM 4815M TO 3391M.
43920.6146 | 43920.625 | 0.25 | EVAL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43920.625 | 43920.9271 | 7.25 | EVAL | NPT-UP | POOH | CONT'D POOH FROM 3391M TO 326M (TOP OF BHA).
43920.9271 | 43920.9375 | 0.25 | EVAL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43920.9375 | 43921 | 1.5 | EVAL | NPT-UP | BHA | POOH FROM 326M TO SURFACE. FOUND NO FISH (W/LINE LOGGING TOOLS) IN OVERSHOT GRAPPLE. WHILE POOH L/DOWN JAR AND STABS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-03-31
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43921 | 43921.0417 | 1 | EVAL | NPT-UP | BHA | B/OUT AND L/DOWN SLB FISHING ASSEMBLY.
43921.0417 | 43921.25 | 5 | EVAL | NPT-UP | DP | P/UP, M/UP AND RIH 3 1/2'' DP's SINGLE BY SINGLE (TO MEET W.FORD CWS LOGGING REQUIREMENTS) IS IN PROGRESS. MEANWHILE ARRANGING TOOLS FOR FISHING OPERATION.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA : SANDSTONE, CLAYSTONE, SHALE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | RIH 3 1/2'' DP's SGL BY SGL IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH FROM 1271M TO TAG TOF AT 4885.5M, ATTEMPTED TO LATCH FISH, POOH TO SURFACE, FOUND NOTHING IN OVERSHOT GRAPPLE. ATTEMPT # 1 CONCLUDED UNSUCCESSFUL.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | ATTEMPT # 2 TO RECOVER SLB W/LINE LOGGING TOOLS.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14