## DDR#334
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 334
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-04-02
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5506 / 5450 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | S. KHALID AZIM / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4976.2 | 4944.79 |  |  | WELL TD |  |  | DAYS SINCE SPUD: | [6 empty] | 333.9792
RIG REP.: |  | TARIQ MAHMOOD BUTT / FAYYAZ HUSSAIN |  |  | MD/TVD @ 06:00HRS: |  | 4976.2 | 4944.79 | [5 empty] | DAILY PROGRESS @ 00:00HRS:
2020-04-01 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  | 82 | IN (M) |  | 4976 |  | OUT (M) |  |  | STRING (BBL) | 216
CHECK TIME | 16:00 | 0:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 672
DEPTH, MD (M) |  | 4976 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  |  | OVERSHOT ASSEMBLY |  |  | 5.75 | 2.75 |  | 3 1/2 IF |  | 1.94 |  |  | PITS (BBL) | 448
MW IN (SG) |  | 1.63 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  |  |  | 3 X DC's |  |  | 4.75 | 2.125 |  | 3 1/2 IF |  | 27.1 |  |  | ACT. SYS (BBL) | 1336
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  |  |  | 18 X HWDP's |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.92 |  |  | RESV. SYS (BBL) | 432
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  |  | D. JAR |  |  | 4.625 | 2.25 |  | 3 1/2 IF |  | 9.02 |  |  | KILL MUD (BBL) | 160
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 12 X HWDP's |  |  | 3.5 | 2.1875 |  | 3 1/2 IF |  | 113.19 |  |  | KILL MW (SG) | 2.2
µ FUNNEL (SEC) |  | 55 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") | [15 empty] | TOTAL | 1928
PV |  | 28 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [15 empty] | DIESEL (LTR)
YIELD POINT |  | 25 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 134380
GEL ST. |  | 10/17 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 26492
WL (ml/30 min) |  | 3.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 3597
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) |  | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 160872
ALK (FILT.) |  | 0.3/1.3 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH |  | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 581573
MAX SHIELD % |  | 3 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 70000
KCl (%) |  | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 56237
KCl (mg/l) |  | 45760 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 31500
CHLORIDES (mg/l) |  | 72000 | JAR | 6.92 | STAB - 1 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) |  | 340 | 3 1/2" HWDPS | 131.51 | STAB - 2 |  | TFA (IN²) | [15 empty] | POB
PENETRAX % |  | 2 | 4 3/4" DCS | 18.92 | SPSA |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 321.17 |  |  | MPCL | 3
MAX GUARD % |  | 2 | DAILY BHA ROT. HRS |  |  |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 34
SOLIDS % |  | 20.66 | DAILY ON BOTTOM HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) |  | 3.8 | DAILY CIRC. HRS |  |  |  | BIT NO. |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 47
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 4
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4870.72/4846.41 |  | 23.39 |  | 287.64 |  |  | 2.08 |  | MWD |  | TOTAL | 113
DAILY WELL COST (US$) |  | 29727 | SHAKER-2 | 3 x 140 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4900.74/4874.24 |  | 20.54 |  | 288.18 |  |  | 2.86 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 23058720 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4916.03/4888.58 |  | 20.21 |  | 285.21 |  |  | 2.13 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 115.8% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | 4934.58/4905.93 |  | 20.45 |  | 288.74 |  |  | 0.31 |  | MWD |  | FIT (EMW) | 2
[12 empty] | 4962.88/4932.45 |  | 20.39 |  | 287.81 |  |  | 0.35 |  | MWD |  | MAASP (PSI) | 2520
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4925 | 1200/1220 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4925 | 1700/1750 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-03-20 | 2020-04-19 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4925 | 2500/2500 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4773/4757
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4788/4770.97
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-03-23 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 250 |  | KUSSAK | 4813/4794.01
STRETCHER DRILL | 2020-03-20 | 2020-04-19 | NEXT BOP TEST DATE |  | 2020-04-06 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4858/4834.66
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-01
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43922 | 43922.1458 | 3.5 | EVAL | NPT-UP | RIH | CONT'D RIH FROM 3419M TO 4793M. (INSIDE 7'' LINER). FLUSHED STRING.
43922.1458 | 43922.1979 | 1.25 | EVAL | NPT-UP | RS | CUT AND SLIPPED 30M D. LINE. ADJUSTED CROWN O MATIC AND ACS.
43922.1979 | 43922.2708 | 1.75 | EVAL | NPT-UP | RW | PRECAUTIONARY WASHED DOWN (WITH SLOW CIRCULATION) FROM 4793M TO 4885.5M, MEANWHILE RECORDED STRING WEIGHTS (UP/DOWN) INSIDE LINER AND OPEN HOLE.
43922.2708 | 43922.2917 | 0.5 | EVAL | NPT-UP | F | SWALLOWED FISH SUCCESSFULLY AT 4886M, SPP INCREASED TO 300 PSI OVER CIRCULATING PRESSURE. COMPRESSED 3 TONS ON STRING. P/UP AND RECONIFIRMED O/SHOT ENGAGEMENT WITH COMPRESSION OF 2-3 TONS, SPP ALSO INCREASED (WHILE PUMP ON WITH SLOW SPM). TURNED OFF PUMP, P/UP & OBSERVED O/PULL (MAX : 5 TONS). FISH LATCHED.
43922.2917 | 43922.6042 | 7.5 | EVAL | NPT-UP | F | CONT'D WORK ON STRING WITH COMPRESSION (MAX: 2-3 TON) AND TENSION (MAX: 5-6 TON). NO SUCCESS.
43922.6042 | 43922.75 | 3.5 | EVAL | NPT-UP | F | CONT'D WORK ON STUCK FISH, GRADUALLY INCREASED TENSION (MAX: 18 TONS). KEPT WORKING WITH COMPRESSION (MAX: 2-3 TON) AND TENSION. NO SUCCESS.
43922.75 | 43923 | 6 | EVAL | NPT-UP | F | CONT'D WORK ON STUCK FISH, GRADUALLY INCREASED TENSION (MAX: 21 TONS). KEPT WORKING WITH COMPRESSION (MAX: 2-3 TON) AND TENSION. NO SUCCESS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-02
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43923 | 43923.25 | 6 | EVAL | NPT-UP | F | CONT'D WORK ON STUCK FISH. KEPT WORKING WITH COMPRESSION (MAX: 2-3 TON) AND TENSION (MAX: 18-19 TON). NO SUCCESS
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA : SANDSTONE, CLAYSTONE, SHALE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | WORKING ON STUCK FISH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH TO +/- 4793M, SLIPPED & CUT D. LINE, WASHED DOWN FROM 4793M TO ENGAGE FISH AT 4886M. FISH LATCHED, WORKING ON STUCK FISH WITH COMPRESSION & TENSION IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | ATTEMPT #2 TO RECOVER FISH IN PROGRESS.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14