## DDR#335
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 335
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-11-21
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | IKRAMULLAH / MUHAMMAD AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 4770 / 4472.09 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 118.13
RIG REP. (TP): |  | JAVED IQBAL / FAYYAZ HUSSAIN |  |  | MD/TVD @ 06:00HRS: |  | 4770 / 4472.09 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2018-11-20 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 22RR3 | 22RR2 | BHA No. |  |  | 54 | IN (M) |  | 4770 |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME |  | 23:00 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 6 | 6 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 931
DEPTH, MD (M) |  | 4770 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | SMITH | SMITH | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 | 0.014887 |  | PITS (BBL) | 725
MW IN (SG) |  | 1.7 | DAILY PROGRESS (M) |  |  |  | TYPE |  | MDSi613WBPX | MDSi613WBPX | BIT SUB |  |  | 4.75 | 2 |  | 3 1/2 IF |  | 1.07 | 0.079643 |  | ACT. SYS (BBL) | 1656
MW OUT (SG) |  | - | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | JN5339 | JN5339 | 1 X DC |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 9.22 | 0.68627 |  | RESV. SYS (BBL) | 162
ECD (SG) |  | - | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | - |  | ST. STAB |  |  | 5.875 | 2.25 |  | 3 1/2 IF |  | 1.97 | 0.14663 |  | KILL MUD (BBL) | 650
FL TEMP. °F |  | - | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 6 X OPEN | 4 X 13 | 11 X DCS |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 101.79 | 7.5765 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 58 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4770 | 4595 | 3 X HWDPS |  |  | 4.6875 | 4.25 |  | 3 1/2 IF |  | 28.29 | 1.095 |  | TOTAL | 2468
PV |  | 30 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | D. JAR |  |  | 4.75 | 5.25 |  | 3 1/2 IF |  | 9.1 | 0.67734 |  | DIESEL (LTR)
YIELD POINT |  | 19 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | 18 X HWDPS |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.85 | 6.5741 |  | RIG TANK | 123628
GEL ST. |  | 7/10 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 20210
WL (ml/30 min.) |  | 3 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 4498
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  | 0.6 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 143838
ALK (FILT.) |  | 0.3 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 10 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 350000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 35000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 20000
KCl (mg/l) |  | 57201 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 20000
CHLORIDES |  | 32000 | 3 1/2" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 385000
CALCIUM |  | 280 | 4 3/4" DCS |  | NMDC |  | HSI | [14 empty] | POB
OIL % |  | 5 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 321.49 |  |  | MPCL | 4
LUBE % |  | 2 | BHA ROT. HRS |  |  |  | BIT NO. |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 12 |  |  | MPCL SERV | 21
SOLIDS % |  | 24.69 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 7 |  |  | SECURITY | 4
M.B.T. |  | 5 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 47
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 21
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 120 | 2 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4647/4382.61 |  | 42.19 |  | 81.49 |  |  | 1.83 |  | MWD |  | TOTAL | 105
DAILY WELL COST (US$) |  | 30012.1514 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4676/4403.94 |  | 43.13 |  | 83.16 |  |  | 1.52 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 20278596.111 | SHAKER-3 | 1 x 120 | 2 x 120 |  | 7" LINER |  |  | 4446.0 (TOL @ 3253) | 4701/4422.05 |  | 43.98 |  | 82.8 |  |  | 1.06 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 112.4% | MUD CLEANER | 1 x 140 | 2 x 170 | [5 empty] | 4713/4430.68 |  | 44.03 |  | 82.27 |  |  | 0.93 |  | MWD |  | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P3) | [5 empty] | MAASP (PSI) | 600
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | HANGU | 4571/4323.65
FIRE DRILL | 2018-11-14 | 2018-12-14 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 | [7 empty] | DANDOT-TOBRA | 4587/4333.72
PIT DRILL | 2018-11-14 | 2018-11-29 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BHAGANWALA | 4608/4354.35
KICK DRILL | 2018-10-07 | 2018-11-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | JUTANA | 4627/4367.58
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-11-11 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  | 0 |  | MUD LOSSES |  |  |  | 402 |  | KUSSAK | 4657/4390.03
STRETCHER DRILL | 2018-11-08 | 2018-12-08 | NEXT BOP TEST DATE |  | 2018-11-25 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4724/4438.61
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-20
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43424 | 43424.3125 | 7.5 | EVAL | PT-P | TCL | RIH W.F CWS LOGGING TOOLS FROM 2756M TO 4752M. M/U TDS & TAGGED BTM @ 4770M WITH CIRCULATION. WHILE RIH FILLED UP STRING WITH MUD AFTER EVERY 15 STANDS.
43424.3125 | 43424.3333 | 0.5 | EVAL | PT-P | TCL | CIRCULATED TO BREAK GELL, RECIPROCATED STRING & RECORDED 1680 PSI SPP @ 3.8 BPM. P/BACK STRING & SPACED OUT TO 4743M.
43424.3333 | 43424.3958 | 1.5 | EVAL | PT-P | TCL | DROPPED MESSENGER DART INSIDE STRING & CHASED THE SAME WITH 203 BBL MUD. OBSERVED CLEAR CHANGE IN SPP & LOGGING TOOLS DEPLOYED.
43424.3958 | 43424.4167 | 0.5 | EVAL | PT-P | TCL | CIRCULATED & CONFIRMED LOGGING TOOLS DEPLOYMENT, RECORDED 1370 PSI SPP @ 3.8 BPM.
43424.4167 | 43424.5417 | 3 | EVAL | PT-P | TCL | POOH LOGGING TOOLS TO 7" LINER SHOE WHILE RECORDING CWS LOG # 2 (NEUTRON-DENSITY-CALIPER-GR) IN MEMORY MODE.
43424.5417 | 43424.5521 | 0.25 | EVAL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43424.5521 | 43424.9688 | 10 | EVAL | PT-P | TCL | PUMPED SLUG & POOH FROM 7" LINER SHOE TO 35M.
43424.9688 | 43425 | 0.75 | EVAL | PT-P | TCL | POOH FROM 35M TO SURFACE, L/DOWN W.F CWS TOOLS IS IN PROGRESS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-21
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43425 | 43425.0417 | 1 | EVAL | PT-P | TCL | CONT'D L/DOWN W.F CWS TOOLS & RETRIEVED DATA FROM MEMORY.
43425.0417 | 43425.1042 | 1.5 | EVAL | PT-P | BHA | P/U, M/U & RIH 6" PDC BIT (22RR3) WITH ROTARY BHA TO 321M.
43425.1042 | 43425.25 | 3.5 | EVAL | PT-P | RIH | RIH FROM 321M TO 1777M. WHILE RIH FILLED UP STRING WITH MUD AFTER EVERY 15 STANDS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA / SANDSTONE & CLAYSTONE
OPERATIONS AT 06:00 HRS |  |  | RIH BIT FOR CONDITION TRIP
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH W.F LOGGING TOOLS FOR CWS LOG # 2 (NEUTRON-DENSITY-CALIPER-GR) FROM 2756M TO BTM @ 4770M ON 3 1/2" DPS & 5" DPS. DEPLOYED LOGGING TOOLS, RECORDED CWS LOG # 2 TO 7" LINER SHOE & POOH TO SURFACE.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | PERFORM CONDITION TRIP PRIOR TO RECORD W.F CWS LOG # 3 (CMI-GR).
REMARKS
Formulas:
DHARIAN-1-ST-3 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14