## DDR#337
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 337
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-04-05
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5506 / 5450 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | S. KHALID AZIM / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4976.2 | 4944.79 |  |  | WELL TD |  |  | DAYS SINCE SPUD: | [6 empty] | 336.9792
RIG REP.: |  | TARIQ MAHMOOD BUTT / FAYYAZ HUSSAIN |  |  | MD/TVD @ 06:00HRS: |  | 4976.2 | 4944.79 | [5 empty] | DAILY PROGRESS @ 00:00HRS:
2020-04-04 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  | 82 | IN (M) |  | 4976 |  | OUT (M) |  |  | STRING (BBL) | 216
CHECK TIME | 16:00 | 0:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 672
DEPTH, MD (M) |  | 4976 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  |  | OVERSHOT ASSEMBLY |  |  | 5.75 | 2.75 |  | 3 1/2 IF |  | 1.94 |  |  | PITS (BBL) | 364
MW IN (SG) |  | 1.63 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  |  |  | 3 X DC's |  |  | 4.75 | 2.125 |  | 3 1/2 IF |  | 27.1 |  |  | ACT. SYS (BBL) | 1252
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  |  |  | 18 X HWDP's |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.92 |  |  | RESV. SYS (BBL) | 416
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  |  | D. JAR |  |  | 4.625 | 2.25 |  | 3 1/2 IF |  | 9.02 |  |  | KILL MUD (BBL) | 250
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 12 X HWDP's |  |  | 3.5 | 2.1875 |  | 3 1/2 IF |  | 113.19 |  |  | KILL MW (SG) | 2.2
µ FUNNEL (SEC) |  | 54 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") | [15 empty] | TOTAL | 1918
PV |  | 26 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [15 empty] | DIESEL (LTR)
YIELD POINT |  | 24 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 125370
GEL ST. |  | 11/17 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 24860
WL (ml/30 min) |  | 3.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 3177
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) |  | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 150230
ALK (FILT.) |  | 0.3/1.2 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH |  | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 611409
MAX SHIELD % |  | 3 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 79000
KCl (%) |  | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 46109
KCl (mg/l) |  | 45760 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 117400
CHLORIDES (mg/l) |  | 72000 | JAR | 6.92 | STAB - 1 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | 69600
HARDNESS (mg/l) |  | 340 | 3 1/2" HWDPS | 131.51 | STAB - 2 |  | TFA (IN²) | [15 empty] | POB
PENETRAX % |  | 2 | 4 3/4" DCS | 18.92 | SPSA |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 321.17 |  |  | MPCL | 3
MAX GUARD % |  | 2 | DAILY BHA ROT. HRS |  |  |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 30
SOLIDS % |  | 20.66 | DAILY ON BOTTOM HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) |  | 3.8 | DAILY CIRC. HRS |  |  |  | BIT NO. |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 46
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 4
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4870.72/4846.41 |  | 23.39 |  | 287.64 |  |  | 2.08 |  | MWD |  | TOTAL | 108
DAILY WELL COST (US$) |  | 27402 | SHAKER-2 | 3 x 140 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4900.74/4874.24 |  | 20.54 |  | 288.18 |  |  | 2.86 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 23153496 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4916.03/4888.58 |  | 20.21 |  | 285.21 |  |  | 2.13 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 116.3% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | 4934.58/4905.93 |  | 20.45 |  | 288.74 |  |  | 0.31 |  | MWD |  | FIT (EMW) | 2
[12 empty] | 4962.88/4932.45 |  | 20.39 |  | 287.81 |  |  | 0.35 |  | MWD |  | MAASP (PSI) | 2520
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4925 | 1200/1220 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4925 | 1700/1750 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-03-20 | 2020-04-19 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4925 | 2500/2500 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4773/4757
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4788/4770.97
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-03-23 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 250 |  | KUSSAK | 4813/4794.01
STRETCHER DRILL | 2020-03-20 | 2020-04-19 | NEXT BOP TEST DATE |  | 2020-04-06 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4858/4834.66
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-04
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43925 | 43925.4583 | 11 | EVAL | NPT-UP | F | CONT'D WORK ON STUCK FISH. KEPT WORKING WITH COMPRESSION (MAX: 2-4 TON) AND TENSION (MAX: 18-20 TON) INTERMITTENTLY. NO SUCCESS.
43925.4583 | 43925.6875 | 5.5 | EVAL | NPT-UP | F | ATTEMPTED TO REGAIN CIRCULATION (INCREASED SPP TO 2500, 3000, 3500 & 4500 PSI IN INTERVALS, OBSERVED NO PRESSURE DROP / NO RETURN) WHILE WORKING ON STUCK FISH INTERMITTENTLY. (MAX COMP. 4 TONS, MAX TEN. 18 -20 TONS). NO SUCCESS.
43925.6875 | 43925.75 | 1.5 | EVAL | NPT-UP | F / DP | B/OUT 2 X 5'' DP JOINTS FROM STRING & L/DOWN SGL BY SGL FROM CATWALK.
43925.75 | 43925.8125 | 1.5 | EVAL | NPT-UP | F | CONNECTED TDS, CONT'D WORK ON STUCK FISH. KEPT WORKING WITH COMPRESSION (MAX: 2-4 TON) AND TENSION (MAX: 18-20 TON) INTERMITTENTLY. NO SUCCESS
43925.8125 | 43925.8854 | 1.75 | EVAL | NPT-UP | F / RU | HELD PJSM, R/UP CIRCULATING SWAGE & DOWEL LINES/UNIT.
43925.8854 | 43925.8958 | 0.25 | EVAL | NPT-UP | F / P /T | CLOSED LO-TORQUE VALVE, P/TESTED DOWEL LINES AT 6000 PSI, HELD FOR 5 MINS, OK.
43925.8958 | 43925.9062 | 0.25 | EVAL | NPT-UP | F | OPENED LO-TORQUE VALVE, STARTED PUMPING FROM DOWEL UNIT IN INCREMENT OF PRESSURE, OBSERVED LEAKAGE AT 2500 PSI FROM CIRCULATING SWAGE AND DP CONNECTION (HAND TIGHT WITH CHAIN TONG). BLED OFF PRESSURE.
43925.9062 | 43925.9271 | 0.5 | EVAL | NPT-UP | F / RD | R/DOWN CIRCULATING SWAGE AND DOWEL LINES.
43925.9271 | 43926 | 1.75 | EVAL | NPT-UP | F | CONT'D WORK ON STUCK FISH. KEPT WORKING WITH COMPRESSION (MAX: 2-4 TON) AND TENSION (MAX: 18-20 TON) INTERMITTENTLY. NO SUCCESS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-05
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43926 | 43926.125 | 3 | EVAL | NPT-UP | F | ATTEMPTED TO REGAIN CIRCULATION (INCREASED SPP TO 5000 PSI, OBSERVED NO PRESSURE DROP / NO RETURN) WHILE WORKING ON STUCK FISH INTERMITTENTLY. (MAX COMP. 4 TONS, MAX TEN. 18 -20 TONS). NO SUCCESS.
43926.125 | 43926.25 | 3 | EVAL | NPT-UP | F | CONT'D WORK ON STUCK FISH. KEPT WORKING WITH COMPRESSION (MAX: 2-4 TON) AND TENSION (MAX: 18-20 TON) INTERMITTENTLY. NO SUCCESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA : SANDSTONE, CLAYSTONE, SHALE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | WORKING ON STUCK FISH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D WORK ON STUCK FISH. KEPT WORKING WITH COMPRESSION (MAX: 4 TON) AND TENSION (MAX: 20 TON) INTERMITTENTLY. NO SUCCESS. ATTEMPTED TO REGAIN CIRCULATION, NO SUCCESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | ATTEMPT #2 TO RECOVER FISH IN PROGRESS.
REMARKS
Formulas:
MIRAJ-1-ST-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14