## DDR#339
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 339
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-11-25
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / MUHAMMAD AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 4770 / 4472.09 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 122.13
RIG REP. (TP): |  | TARIQ BUTT / FAYYAZ HUSSAIN |  |  | MD/TVD @ 06:00HRS: |  | 4770 / 4472.09 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2018-11-24 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 22RR4 | 22RR2 | BHA No. |  |  | 55 | IN (M) |  | 4770 |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME |  | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 6 | 6 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 931
DEPTH, MD (M) |  | 4770 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | SMITH | SMITH | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 | 0.014887 |  | PITS (BBL) | 654
MW IN (SG) |  | 1.7 | DAILY PROGRESS (M) |  |  |  | TYPE |  | MDSi613WBPX | MDSi613WBPX | BIT SUB (F.V) |  |  | 4.75 | 2 |  | 3 1/2 IF |  | 1.07 | 0.079643 |  | ACT. SYS (BBL) | 1585
MW OUT (SG) |  | - | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | JN5339 | JN5339 | 1 X DC |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 9.22 | 0.68627 |  | RESV. SYS (BBL) | 190
ECD (SG) |  | - | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | - |  | ST. STAB |  |  | 5.875 | 2.375 |  | 3 1/2 IF |  | 1.97 | 0.14663 |  | KILL MUD (BBL) | 650
FL TEMP. °F |  | - | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 6 X OPEN | 4 X 13 | 1 X DC |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 9.29 | 0.69148 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 62 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4770 | 4595 | ST. STAB |  |  | 5.875 | 2.375 |  | 3 1/2 IF |  | 1.81 | 0.13472 |  | TOTAL | 2425
PV |  | 30 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 4 X DCS |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 36.86 | 2.7436 |  | DIESEL (LTR)
YIELD POINT |  | 18 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | 9 X HWDPS |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 84.84 | 3.2837 |  | RIG TANK | 126426
GEL ST. |  | 7/11 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | D. JAR |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.18 | 0.68329 |  | CAMP TANK | 18387
WL (ml/30 min.) |  | 2.7 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 12 X HWDPS |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 113.3 | 4.3853 |  | CONSUMED | 27784
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED | 40000
ALK (MUD) |  | 0.5 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 144813
ALK (FILT.) |  | 0.3 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 35000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 25000
KCl (mg/l) |  | 57201 | JAR | 62.15 | STAB - 1 | 62.15 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 25000
CHLORIDES |  | 31000 | 3 1/2" HWDPS | 62.15 | STAB - 2 | 62.15 | TFA (IN²) | [14 empty] | TOTAL | 435000
CALCIUM |  | 280 | 4 3/4" DCS | 62.15 | NMDC |  | HSI | [14 empty] | POB
OIL % |  | 5 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 267.74 |  |  | MPCL | 4
LUBE % |  | 2 | BHA ROT. HRS |  | 62.15 |  | BIT NO. 22RR4 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 10 |  |  | MPCL SERV | 30
SOLIDS % |  | 24.23 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 6 |  |  | SECURITY | 4
M.B.T. |  | 5 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 45
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD (M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 120 | 2 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4647/4382.61 |  | 42.19 |  | 81.49 |  |  | 1.83 |  | MWD |  | TOTAL | 116
DAILY WELL COST (US$) |  | 34886.5017 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4676/4403.94 |  | 43.13 |  | 83.16 |  |  | 1.52 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 20436247.5458 | SHAKER-3 | 1 x 120 | 2 x 120 |  | 7" LINER |  |  | 4446.0 (TOL @ 3253) | 4701/4422.05 |  | 43.98 |  | 82.8 |  |  | 1.06 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 113.2% | MUD CLEANER | 1 x 140 | 2 x 170 | [5 empty] | 4713/4430.68 |  | 44.03 |  | 82.27 |  |  | 0.93 |  | MWD |  | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P3) | [5 empty] | MAASP (PSI) | 600
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | HANGU | 4571/4323.65
FIRE DRILL | 2018-11-14 | 2018-12-14 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 | [7 empty] | DANDOT-TOBRA | 4587/4333.72
PIT DRILL | 2018-11-14 | 2018-11-29 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BHAGANWALA | 4608/4354.35
KICK DRILL | 2018-10-07 | 2018-11-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | JUTANA | 4627/4367.58
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-11-11 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 12 | MUD LOSSES IN 24 HRS |  |  | 0 |  | MUD LOSSES |  |  |  | 402 |  | KUSSAK | 4657/4390.03
STRETCHER DRILL | 2018-11-08 | 2018-12-08 | NEXT BOP TEST DATE |  | 2018-12-02 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4724/4438.61
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-24
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43428 | 43428.0521 | 1.25 | EVAL | PT-P | TCL | POOH LOGGING TOOLS TO 4403M WHILE RECORDING CWS LOG # 3 (CMI-GR) IN MEMORY MODE.
43428.0521 | 43428.0625 | 0.25 | EVAL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43428.0625 | 43428.5 | 10.5 | EVAL | PT-P | TCL | PUMPED SLUG & POOH FROM 4403M TO 40M (CWS BHA).
43428.5 | 43428.6042 | 2.5 | EVAL | PT-P | TCL | POOH FROM 40M TO SURFACE & L/D W.F CWS LOGGING TOOLS, GARAGE PIPES & WASH PIPES.
43428.6042 | 43428.6354 | 0.75 | EVAL | PT-P | RU | HELD PJSM. R/U & PRESSURE TESTED SHOOTING NIPPLE + W/LINE BOP (AGAINST BLIND RAM BOP) @ 400 PSI, TEST OK.
43428.6354 | 43428.8021 | 4 | EVAL | NPT-UP | W/L | R/U SLB W/LINE GEAR. P/U, M/U & SURFACE TESTED W/LINE TOOLS FOR USIT-CBL-VDL-GR LOG. OBSERVED TOOLS MALFUNCTIONED, TROUBLESHOT & RECTIFIED PROBLEM.
43428.8021 | 43429 | 4.75 | EVAL | PT-P | W/L | RIH W/LINE TOOLS & RECORDING USIT-CBL-VDL-GR LOG IN PROGRESS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-25
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43429 | 43429.1146 | 2.75 | EVAL | PT-P | W/L | RECORDED SLB USIT-CBL-VDL-GR LOG FROM 4442M TO 3312M & POOH W/LINE TOOLS TO SURFACE.
43429.1146 | 43429.1667 | 1.25 | EVAL | PT-P | RD | R/D TOOLS, W/LINE GEAR, SHOOTING NIPPLE & W/LINE BOP.
43429.1667 | 43429.2396 | 1.75 | EVAL | PT-P | BHA | P/U, M/U & RIH 6" PDC BIT (22RR4) WITH 02 X STRING STABS ROTARY BHA TO 267M. WHILE RIH BHA SHIFTED 02 X 4 3/4" DC STANDS FROM OFF-DRILLER SIDE TO DRILLER SIDE.
43429.2396 | 43429.25 | 0.25 | EVAL | PT-P | RIH | RIH FROM 267M TO 353M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA / SANDSTONE & CLAYSTONE
OPERATIONS AT 06:00 HRS |  |  | RIH BIT
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RECORDED CWS LOG # 3 (CMI-GR) & POOH W.F CWS LOGGING TOOLS FROM 4403M TO SURFACE. R/U SLB W/LINE GEAR & RIH W/LINE TOOLS TO RECORD USIT-GR LOG.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONDUCT CONDITION TRIP PRIOR RIH 5" LINER.
REMARKS |  |  | W.F LINER HANGER ENGINEER & W.F TRS EQUIPMENT ARRIVED AT WELLSITE ON 24-NOV-2018.
Formulas:
DHARIAN-1-ST-3 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+21