## DDR#341
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 341
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-11-27
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / MUHAMMAD AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 4770 / 4472.09 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 124.13
RIG REP. (TP): |  | TARIQ BUTT / FAYYAZ HUSSAIN |  |  | MD/TVD @ 06:00HRS: |  | 4770 / 4472.09 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2018-11-26 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | 5" LINER TALLY | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 15
CHECK TIME | 5:59 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 916
DEPTH, MD (M) | 4770 | 4770 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  |  |  | REAMER SHOE |  |  | 5.6875 | 18 PPF |  | TSHW513 |  | 0.7 | 0.018757 |  | PITS (BBL) | 606
MW IN (SG) | 1.7 | 1.7 | DAILY PROGRESS (M) |  |  |  | TYPE |  |  |  | 2 X 5" CSG JOINTS |  |  | 5 | 18 PPF |  | TSHW513 |  | 23.115 | 0.61939 |  | ACT. SYS (BBL) | 1537
MW OUT (SG) | 1.69 | - | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  | FLOAT COLLAR |  |  | 5 | 18 PPF |  | TSHW513 |  | 0.715 | 0.019159 |  | RESV. SYS (BBL) | 278
ECD (SG) | - | - | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | 1 X 5" CSG JOINT |  |  | 5 | 18 PPF |  | TSHW513 |  | 11.462 | 0.30713 |  | KILL MUD (BBL) | 650
FL TEMP. °F | - | - | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  |  |  | LANDING COLLAR |  |  | 5 | 18 PPF |  | TSHW513 |  | 0.515 | 0.0138 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 58 | 60 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  |  | 31 X 5" CSG JOINTS |  |  | 5 | 18 PPF |  | TSHW513 |  | 354.915 | 9.5102 |  | TOTAL | 2465
PV | 29 | 30 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 5" LINER HANGER |  |  | 5 | 15 PPF |  | TSHW513 |  | 7.58 | 0.20311 |  | DIESEL (LTR)
YIELD POINT | 20 | 21 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | STICK UP |  |  | 3.5 | 13.3 PPF |  | 3 1/2 IF |  | 1.245 |  |  | RIG TANK | 118177
GEL ST. | 7/10 | 8/10 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 3.5" X 32 DP STANDS |  |  | 3.5 | 13.3 PPF |  | 3 1/2 IF |  | 912.65 |  |  | CAMP TANK | 26638
WL (ml/30 min.) | 2.8 | 2.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 5847
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [12 empty] | 10.0534 |  | RECEIVED
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 144815
ALK (FILT.) | 0.6 | 0.6 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 35000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 96600
KCl (mg/l) | 57201 | 57201 | JAR | 71.16 | STAB - 1 | 71.16 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 96600
CHLORIDES | 31000 | 31000 | 3 1/2" HWDPS | 71.16 | STAB - 2 | 71.16 | TFA (IN²) | [14 empty] | TOTAL | 435000
CALCIUM | 280 | 280 | 4 3/4" DCS | 71.16 | NMDC |  | HSI | [14 empty] | POB
OIL % | 5 | 5 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 1312.897 |  |  | MPCL | 6
LUBE % | 2 | 2 | BHA ROT. HRS |  | 71.16 |  | BIT NO. 22RR4 |  | 3-4-BT-A-X-I-WT-TD |  | BHA WT. IN MUD (TON) | [7 empty] | 10 |  |  | MPCL SERV | 21
SOLIDS % | 24.23 | 24.23 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 6 |  |  | SECURITY | 4
M.B.T. | 5 | 5 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 47
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD (M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 120 | 2 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4647/4382.61 |  | 42.19 |  | 81.49 |  |  | 1.83 |  | MWD |  | TOTAL | 112
DAILY WELL COST (US$) |  | 40160.1509 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4676/4403.94 |  | 43.13 |  | 83.16 |  |  | 1.52 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 20514288.5931 | SHAKER-3 | 1 x 120 | 2 x 120 |  | 7" LINER |  |  | 4446.0 (TOL @ 3253) | 4701/4422.05 |  | 43.98 |  | 82.8 |  |  | 1.06 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 113.7% | MUD CLEANER | 1 x 140 | 2 x 170 | [5 empty] | 4713/4430.68 |  | 44.03 |  | 82.27 |  |  | 0.93 |  | MWD |  | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P3) | [5 empty] | MAASP (PSI) | 600
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | HANGU | 4571/4323.65
FIRE DRILL | 2018-11-14 | 2018-12-14 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 | [7 empty] | DANDOT-TOBRA | 4587/4333.72
PIT DRILL | 2018-11-14 | 2018-11-29 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BHAGANWALA | 4608/4354.35
KICK DRILL | 2018-10-07 | 2018-11-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | JUTANA | 4627/4367.58
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-11-11 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  | 0 |  | MUD LOSSES |  |  |  | 402 |  | KUSSAK | 4657/4390.03
STRETCHER DRILL | 2018-11-08 | 2018-12-08 | NEXT BOP TEST DATE |  | 2018-12-02 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4724/4438.61
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-26
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43430 | 43430.0417 | 1 | EVAL | PT-P | CIR | CIRCULATED & SWEPT 15 BBL EACH LOW-VIS + HI-VIS TANDEM PILL.
43430.0417 | 43430.0521 | 0.25 | EVAL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43430.0521 | 43430.1458 | 2.25 | EVAL | PT-P | WT | CONDUCTED WIPER TRIP FROM BTM (4770M) TO 7" LINER SHOE (4446M) ON ELEVATORS & OBSERVED GOOD HOLE CONDITION.
43430.1458 | 43430.2292 | 2 | EVAL | PT-P | CIR | CIRCULATED FOR BTM UP.
43430.2292 | 43430.2708 | 1 | EVAL | PT-P | SP | SPOTTED 65 BBL LUBRA BEADS PILL (5 PPB EACH FINE + COARSE) IN OPEN HOLE.
43430.2708 | 43430.3229 | 1.25 | EVAL | PT-P | POOH | POOH FROM 4770M TO 4400M (INSIDE 7" LINER) ON ELEVATORS. FOUND HOLE CONDITION GOOD.
43430.3229 | 43430.3333 | 0.25 | EVAL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43430.3333 | 43430.6771 | 8.25 | EVAL | PT-P | POOH | PUMPED SLUG & POOH FROM 4400M TO TOP OF BHA @ 267M.
43430.6771 | 43430.6875 | 0.25 | EVAL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43430.6875 | 43430.7292 | 1 | EVAL | PT-P | BHA | POOH FROM 267M TO SURFACE. L/DOWN JAR, ST. STABS & BIT.
43430.7292 | 43430.7812 | 1.25 | EVAL | PT-P | RU | R/U WF TRS GEAR & PREPARED RIG FLOOR TO RIH 5" LINER.
43430.7812 | 43431 | 5.25 | EVAL | PT-P | RC | HELD PJSM. P/U, M/U, THREAD LOCKED & RIH 5" LINER SHOE TRACK ( R/SHOE + 1ST JOINT+ 2ND JOINT + F/COLLAR + 3RD JOINT + L/COLLAR = 36.508M). CHECKED & CONFIRMED INTEGRITY OF THE FLOATS - OK. RIH 5" LINER (18 PPF, P-110, TSH W513) DOWN TO 265M (23 JOINTS). WHILE RIH INSTALLED CENTRALIZERS & FILLED UP CSG AS PER PROGRAM.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-27
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43431 | 43431.0625 | 1.5 | EVAL | PT-P | RC | CONT'D RIH 5" LINER (18 PPF, P-110, TSH W513) FROM 265M TO 391M (TOTAL 34 JOINTS). WHILE RIH INSTALLED CENTRALIZERS & FILLED UP CSG AS PER PROGRAM.
43431.0625 | 43431.0938 | 0.75 | EVAL | PT-P | RC | P/U 5" LINER HANGER ASSY. CONNECTED LINER WIPER PLUG & SET BALL SEAT TO SHEAR @ 2280 PSI, WIPER PLUG TO SHEAR @ 1072 PSI, HANGER SLIPS TO SET @ 1100 PSI & HOLD DOWN SUB TO SET @ 1040 PSI. M/U & RIH LINER HANGER ASSY WITH 5" LINER TO 400M.
43431.0938 | 43431.125 | 0.75 | EVAL | PT-P | CIR | INSTALLED CIRCULATING HEAD & CIRCULATED FOR COMPLETE CYCLE. RECORDED CIRCULATING PRESSURE & STRING WT. FILLED PBR WITH HI-VIS GEL. MEANWHILE R/D WF TRS GEAR.
43431.125 | 43431.25 | 3 | EVAL | PT-P | RC | RIH 5" LINER ON 3 1/2" DPS FROM 400M TO 1312M. WHILE RIH FILLED UP STRING AFTER EVERY 10 STANDS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA / SANDSTONE & CLAYSTONE
OPERATIONS AT 06:00 HRS |  |  | RIH 5" LINER ON DPS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONDUCTED WIPER TRIP FROM BTM TO 7" LINER SHOE & OBSERVED GOOD HOLE CONDITION. CIRCULATED & SPOTTED LUBRA BEADS PILL IN OPEN HOLE. POOH FROM 4770M TO SURFACE. R/U WF TRS GEAR & RIH 5" LINER TO 265M AS PER TALLY.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH, SET & CEMENT 5" LINER AS PER PROGRAM.
REMARKS
Formulas:
DHARIAN-1-ST-3 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+21