## DDR#342
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 342
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-11-28
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / MUHAMMAD AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 4770 / 4472.09 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 125.13
RIG REP. (TP): |  | TARIQ BUTT / FAYYAZ HUSSAIN |  |  | MD/TVD @ 06:00HRS: |  | 4770 / 4472.09 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2018-11-27 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | 5" LINER TALLY | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 223
CHECK TIME | 11:59 | 20:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 609
DEPTH, MD (M) | 4770 | 4770 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  |  |  | REAMER SHOE |  |  | 5.6875 | 18 PPF |  | TSHW513 |  | 0.7 | 0.018757 |  | PITS (BBL) | 683
MW IN (SG) | 1.7 | 1.7 | DAILY PROGRESS (M) |  |  |  | TYPE |  |  |  | 2 X 5" CSG JOINTS |  |  | 5 | 18 PPF |  | TSHW513 |  | 23.115 | 0.61939 |  | ACT. SYS (BBL) | 1515
MW OUT (SG) | - | - | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  | FLOAT COLLAR |  |  | 5 | 18 PPF |  | TSHW513 |  | 0.715 | 0.019159 |  | RESV. SYS (BBL) | 355
ECD (SG) | - | - | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | 1 X 5" CSG JOINT |  |  | 5 | 18 PPF |  | TSHW513 |  | 11.462 | 0.30713 |  | KILL MUD (BBL) | 650
FL TEMP. °F | - | - | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  |  |  | LANDING COLLAR |  |  | 5 | 18 PPF |  | TSHW513 |  | 0.515 | 0.0138 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 58 | 56 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  |  | 31 X 5" CSG JOINTS |  |  | 5 | 18 PPF |  | TSHW513 |  | 354.915 | 9.5102 |  | TOTAL | 2520
PV | 30 | 28 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 5" LINER HANGER |  |  | 5 | 15 PPF |  | TSHW513 |  | 7.58 | 0.20311 |  | DIESEL (LTR)
YIELD POINT | 20 | 19 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | STICK UP |  |  | 3.5 | 13.3 PPF |  | 3 1/2 IF |  | 1.245 |  |  | RIG TANK | 114569
GEL ST. | 8/11 | 7/10 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 3.5" X 43 STD + X/O |  |  | 3.5 | 13.3 PPF |  | 3 1/2 IF |  | 1230.22 |  |  | CAMP TANK | 26053
WL (ml/30 min.) | 2.8 | 2.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 5" X 109 STD + 2 DPS |  |  | 5 | 19.5 |  | 4 1/2 IF |  | 3136.82 |  |  | CONSUMED | 4193
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [12 empty] | 10.0534 |  | RECEIVED
ALK (MUD) | 0.6 | 0.6 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 140622
ALK (FILT.) | 0.3 | 0.4 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 35000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 80500
KCl (mg/l) | 57201 | 57201 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 80500
CHLORIDES | 31000 | 31000 | 3 1/2" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 435000
CALCIUM | 280 | 280 | 4 3/4" DCS |  | NMDC |  | HSI | [14 empty] | POB
OIL % | 5 | 5 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 4767.287 |  |  | MPCL | 6
LUBE % | 2 | 2 | BHA ROT. HRS |  |  |  | BIT NO. |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 10 |  |  | MPCL SERV | 22
SOLIDS % | 24.23 | 24.23 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 6 |  |  | SECURITY | 4
M.B.T. | 5 | 5 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 46
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD (M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 120 | 2 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4647/4382.61 |  | 42.19 |  | 81.49 |  |  | 1.83 |  | MWD |  | TOTAL | 112
DAILY WELL COST (US$) |  | 36600.6133 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4676/4403.94 |  | 43.13 |  | 83.16 |  |  | 1.52 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 20550889.2065 | SHAKER-3 | 1 x 120 | 2 x 120 |  | 7" LINER |  |  | 4446.0 (TOL @ 3253) | 4701/4422.05 |  | 43.98 |  | 82.8 |  |  | 1.06 |  | MWD |  | LAST CSG SIZE | 5"
% OF AFE SPENT |  | 113.9% | MUD CLEANER | 1 x 140 | 2 x 170 |  | 5" LINER |  |  | 4767.0 (TOL @ 4368) | 4713/4430.68 |  | 44.03 |  | 82.27 |  |  | 0.93 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P3) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | HANGU | 4571/4323.65
FIRE DRILL | 2018-11-14 | 2018-12-14 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 | [7 empty] | DANDOT-TOBRA | 4587/4333.72
PIT DRILL | 2018-11-14 | 2018-11-29 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BHAGANWALA | 4608/4354.35
KICK DRILL | 2018-10-07 | 2018-11-06 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | JUTANA | 4627/4367.58
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-11-11 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  | 0 |  | MUD LOSSES |  |  |  | 402 |  | KUSSAK | 4657/4390.03
STRETCHER DRILL | 2018-11-08 | 2018-12-08 | NEXT BOP TEST DATE |  | 2018-12-02 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4724/4438.61
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-27
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43431 | 43431.0625 | 1.5 | EVAL | PT-P | RC | RIH 5" LINER (18 PPF, P-110, TSH W513) FROM 265M TO 391M (TOTAL 34 JOINTS). WHILE RIH INSTALLED CENTRALIZERS & FILLED UP CSG AS PER PROGRAM.
43431.0625 | 43431.0938 | 0.75 | EVAL | PT-P | RC | P/U 5" LINER HANGER ASSY. CONNECTED LINER WIPER PLUG & SET BALL SEAT TO SHEAR @ 2280 PSI, WIPER PLUG TO SHEAR @ 1072 PSI, HANGER SLIPS TO SET @ 1100 PSI & HOLD DOWN SUB TO SET @ 1040 PSI. M/U & RIH LINER HANGER ASSY WITH 5" LINER TO 400M.
43431.0938 | 43431.125 | 0.75 | EVAL | PT-P | CIR | INSTALLED CIRCULATING HEAD & CIRCULATED FOR COMPLETE CYCLE. RECORDED CIRCULATING PRESSURE & STRING WT. FILLED PBR WITH HI-VIS GEL. MEANWHILE R/D WF TRS GEAR.
43431.125 | 43431.4792 | 8.5 | EVAL | PT-P | RC | RIH 5" LINER ON 3 1/2" X 5" DPS FROM 400M TO 3240M. WHILE RIH FILLED UP STRING AFTER EVERY 10 STANDS.
43431.4792 | 43431.5208 | 1 | EVAL | PT-P | CIR | CIRCULATED FOR STRING CAPACITY.
43431.5208 | 43431.6458 | 3 | EVAL | PT-P | RC | RIH 5" LINER ON 5" DPS FROM 3240M TO 4445M (INSIDE 7" LINER SHOE). WHILE RIH FILLED UP STRING AFTER EVERY 10 STANDS.
43431.6458 | 43431.6875 | 1 | EVAL | PT-P | CIR | CIRCULATED FOR STRING CAPACITY.
43431.6875 | 43431.75 | 1.5 | EVAL | PT-P | RC | RIH 5" LINER ON 5" DPS FROM 4445M TO 4744M. PRECAUTIONARY REAMED / WASHED DOWN LINER FROM 4744M TO BTM @ 4770M.
43431.75 | 43431.7917 | 1 | EVAL | PT-P | CIR | CIRCULATED TO CONDITION MUD & SPACED OUT LINER TO 4767M.
43431.7917 | 43431.8125 | 0.5 | EVAL | PT-P | RU | P/U CEMENTING HEAD WITH PRE-LOADED DP DART. DROPPED BALL INSIDE STRING & M/U CEMENT HEAD.
43431.8125 | 43431.8958 | 2 | EVAL | PT-P | RC | CHASED BALL WITH MUD @ 2 - 3 BPM. OBSERVED BALL SEATED & INCREASED PRESSURE TO 1300 PSI. HELD PRESSURE FOR 5 MIN. BLED OFF TO 700 PSI. SLACKED OFF STRING. OBSERVED LINER HANGER SLIPS BITE & HOLDING. APPLIED LINER WEIGHT + 15 TON WEIGHT ON SLIPS, INCREASED SPP TO 1600 PSI TO RELEASE SETTING TOOL. HELD PRESSURE FOR 5 MIN. P/U STRING, OBSERVED FREE STRING MOVEMENT & ROTATION @ NEUTRAL WEIGHT & CONFIRMED SETTING TOOL RELEASED. INCREASED PRESSURE FROM 2200 PSI TO 2600 PSI IN GRADUAL INCREMETNS, SHEARED BALL SEAT @ 2600 PSI & RESUMED CIRCULATION. SLACKED OFF 20 TON WEIGHT ON LINER HANGER.
43431.8958 | 43431.9792 | 2 | EVAL | PT-P | CIR | CIRCULATED TO CONDITION MUD. MEANWHILE STARTED PREPARING MIX FLUID AND HOOKED UP SLB CEMENT PUMP & RIG PUMP TO CEMENT HEAD.
43431.9792 | 43432 | 0.5 | EVAL | PT-P | P/T | HELD PJSM. STOPPED CIRCULATION, FLUSHED & P/TESTED CEMENT PUMP LINE & RIG PUMP LINE @ 500 PSI LOW & 5000 PSI HIGH, FOUND OK.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-28
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43432 | 43432.0417 | 1 | EVAL | PT-P | CIR | CIRCULATED TO CONDITION MUD. MEANWHILE WEIGHED UP CEMENT SLURRY.
43432.0417 | 43432.1146 | 1.75 | EVAL | PT-P | CMC | CARRIED OUT 5" LINER CEMENT JOB AS PER PROGRAM. SWITCHED OVER TO CEMENT UNIT & PUMPED 75 BBL MUDPUSH II SPACER OF 15.2 PPG @ 5 BPM, FOLLOWED BY 50 BBL BATCH MIXED TAIL SLURRY OF 16.2 PPG @ 5 BPM. RELEASED DRILL PIPE DART, DISPLACED CEMENT WITH 25 BBL SPACER + 193 BBL MUD (TOTAL DISPLACEMENT = 218 BBL) THRU CEMENT PUMPING UNIT @ 5 BPM & BUMPED PLUGS @ 2600 PSI PUMPING PRESS. INCREASED & HELD PRESS TO 4000 PSI FOR 5 MIN, FOUND NO PRESS DROP. BLED OFF PRESS, OBSERVED NO BACK FLOW, FOUND FLOATS HOLDING & NO LOSS DURING CMT JOB. P/U STRING & APPLIED 20 TON COMPRESSION & SET 5" LINER TOP PACKER, FOUND CLEAR INDICATION OF PACKER SETTING AT SURFACE.
43432.1146 | 43432.125 | 0.25 | EVAL | PT-P | RD | R/DOWN CEMENTING HEAD & CEMENT LINES.
43432.125 | 43432.1562 | 0.75 | EVAL | PT-P | POOH | POOH LINER HANGER SETTING TOOL TO 4230M.
43432.1562 | 43432.2188 | 1.5 | EVAL | PT-P | CIR | M/U TDS, DIRECT CIRCULATED @ 8 BPM & DISCARDED 90 BBL SPACER CONTAMINATION ON BTM UP.
43432.2188 | 43432.25 | 0.75 | EVAL | PT-P | POOH | PUMPED SLUG & POOH FROM 4230M TO 4100M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA / SANDSTONE & CLAYSTONE
OPERATIONS AT 06:00 HRS |  |  | POOH LINER HANGER SETTING TOOL
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH 5" LINER DOWN TO 4767M AS PER TALLY. SET LINER HANGER, RELEASED SETTING TOOL & SHEARED BALL SEAT. CIRCULATED TO CONDITION MUD. MEANWHILE PREPARED MIX FLUID FOR CEMENT JOB.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH LINER HANGER SETTING TOOL TO SURFACE. M/U & RIH 6" BIT WITH SLICK BHA TO CLEAR TOP OF 5" LINER.
REMARKS
Formulas:
DHARIAN-1-ST-3 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+21