## DDR#343
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 343
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-11-29
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / MUHAMMAD AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 4770 / 4472.09 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 126.13
RIG REP. (TP): |  | TARIQ BUTT / FAYYAZ HUSSAIN |  |  | MD/TVD @ 06:00HRS: |  | 4770 / 4472.09 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2018-11-28 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 22RR5 | 22RR2 | BHA No. |  |  | 56 | IN (M) |  | 4770 |  | OUT (M) |  |  | STRING (BBL) | 108
CHECK TIME | 13:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 6 | 6 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 729
DEPTH, MD (M) | 4770 | 4770 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | SMITH | SMITH | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 | 0.014887 |  | PITS (BBL) | 807
MW IN (SG) | 1.7 | 1.7 | DAILY PROGRESS (M) |  |  |  | TYPE |  | MDSi613WBPX | MDSi613WBPX | BIT SUB (F.V) |  |  | 4.75 | 2 |  | 3 1/2 IF |  | 1.07 | 0.079643 |  | ACT. SYS (BBL) | 1644
MW OUT (SG) | - | - | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | JN5339 | JN5339 | 12 X DCS |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 111.01 | 8.2628 |  | RESV. SYS (BBL) | 0
ECD (SG) | - | - | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | - |  | D. JAR |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.18 | 0.68329 |  | KILL MUD (BBL) | 600
FL TEMP. °F | - | - | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  | 6 X OPEN | 4 X 13 | 12 X HWDPS |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 198.14 | 7.669 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 55 | 60 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4770 | 4595 | [11 empty] | TOTAL | 2244
PV | 29 | 30 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT | 15 | 19 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 109202
GEL ST. | 7/12 | 7/13 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 25460
WL (ml/30 min.) | 2.8 | 2.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 5960
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) | 0.7 | 0.7 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 134662
ALK (FILT.) | 0.3 | 0.3 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 35000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 25000
KCl (mg/l) | 57201 | 57201 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 25000
CHLORIDES | 31000 | 31000 | 3 1/2" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 435000
CALCIUM | 280 | 280 | 4 3/4" DCS |  | NMDC |  | HSI | [14 empty] | POB
OIL % | 5 | 5 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 319.6 |  |  | MPCL | 4
LUBE % | 2 | 2 | BHA ROT. HRS |  |  |  | BIT NO. 22RR5 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 13.0836 |  |  | MPCL SERV | 19
SOLIDS % | 24.23 | 24.23 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 6.5488 |  |  | SECURITY | 4
M.B.T. | 5 | 5 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD (M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 120 | 2 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4647/4382.61 |  | 42.19 |  | 81.49 |  |  | 1.83 |  | MWD |  | TOTAL | 113
DAILY WELL COST (US$) |  | 29458.1952 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4676/4403.94 |  | 43.13 |  | 83.16 |  |  | 1.52 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 20580347.4017 | SHAKER-3 | 1 x 120 | 2 x 120 |  | 7" LINER |  |  | 4446.0 (TOL @ 3253) | 4701/4422.05 |  | 43.98 |  | 82.8 |  |  | 1.06 |  | MWD |  | LAST CSG SIZE | 5"
% OF AFE SPENT |  | 114% | MUD CLEANER | 1 x 140 | 2 x 170 |  | 5" LINER |  |  | 4767.0 (TOL @ 4368) | 4713/4430.68 |  | 44.03 |  | 82.27 |  |  | 0.93 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P3) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | HANGU | 4571/4323.65
FIRE DRILL | 2018-11-14 | 2018-12-14 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 | [7 empty] | DANDOT-TOBRA | 4587/4333.72
PIT DRILL | 2018-11-14 | 2018-11-29 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BHAGANWALA | 4608/4354.35
KICK DRILL | 2018-11-28 | 2018-12-28 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | JUTANA | 4627/4367.58
TRIP DRILL | 2018-11-28 | 2018-12-28 | LAST BOP TEST DATE |  | 2018-11-11 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK | 4657/4390.03
STRETCHER DRILL | 2018-11-08 | 2018-12-08 | NEXT BOP TEST DATE |  | 2018-12-02 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4724/4438.61
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-28
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43432 | 43432.0417 | 1 | EVAL | PT-P | CIR | CIRCULATED TO CONDITION MUD. MEANWHILE WEIGHED UP CEMENT SLURRY.
43432.0417 | 43432.1146 | 1.75 | EVAL | PT-P | CMC | CARRIED OUT 5" LINER CEMENT JOB AS PER PROGRAM. SWITCHED OVER TO CEMENT UNIT & PUMPED 75 BBL MUDPUSH II SPACER OF 15.2 PPG @ 5 BPM, FOLLOWED BY 50 BBL BATCH MIXED TAIL SLURRY OF 16.2 PPG @ 5 BPM. RELEASED DRILL PIPE DART, DISPLACED CEMENT WITH 25 BBL SPACER + 193 BBL MUD (TOTAL DISPLACEMENT = 218 BBL) THRU CEMENT PUMPING UNIT @ 5 BPM & BUMPED PLUGS @ 2600 PSI PUMPING PRESS. INCREASED & HELD PRESS TO 4000 PSI FOR 5 MIN, FOUND NO PRESS DROP. BLED OFF PRESS, OBSERVED NO BACK FLOW, FOUND FLOATS HOLDING & NO LOSS DURING CMT JOB. P/U STRING & APPLIED 20 TON COMPRESSION & SET 5" LINER TOP PACKER, FOUND CLEAR INDICATION OF PACKER SETTING AT SURFACE.
43432.1146 | 43432.125 | 0.25 | EVAL | PT-P | RD | R/DOWN CEMENTING HEAD & CEMENT LINES.
43432.125 | 43432.1562 | 0.75 | EVAL | PT-P | POOH | POOH LINER HANGER SETTING TOOL TO 4230M.
43432.1562 | 43432.2188 | 1.5 | EVAL | PT-P | CIR | M/U TDS, DIRECT CIRCULATED @ 8 BPM & DISCARDED 90 BBL SPACER CONTAMINATION ON BTM UP.
43432.2188 | 43432.375 | 3.75 | EVAL | PT-P | POOH | PUMPED SLUG & POOH FROM 4230M TO 3000M.
43432.375 | 43432.3958 | 0.5 | EVAL | NPT-P | RS | SERVICED TDS.
43432.3958 | 43432.6458 | 6 | EVAL | PT-P | POOH | POOH FROM 3000M TO SURFACE & L/D LINER HANGER SETTING TOOL.
43432.6458 | 43432.7083 | 1.5 | EVAL | PT-P | BHA | P/U, M/U & RIH 6" PDC BIT (22RR5) WITH SLICK ROTARY BHA TO 319M.
43432.7083 | 43432.7188 | 0.25 | EVAL | PT-P | CIR | CIRCULATED TO FLUSH BHA.
43432.7188 | 43433 | 6.75 | EVAL | PT-P | RIH | RIH FROM 319M TO 3098M. WHILE RIH FILLED UP STRING WITH MUD AFTER EVERY 15 STANDS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-11-29
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43433 | 43433.0208 | 0.5 | EVAL | PT-P | RIH | CONT'D RIH FROM FROM 3098M TO 3239M.
43433.0208 | 43433.0729 | 1.25 | EVAL | NPT-P | RS | CUT & SLIPPED 35M DRILLING LINE. CALIBRATED ACS + CROWN-O-MATIC + HOOK LOAD SENSORS.
43433.0729 | 43433.1667 | 2.25 | EVAL | PT-P | RIH | RIH FROM 3239M TO 4180M.
43433.1667 | 43433.1875 | 0.5 | EVAL | PT-P | RW | M/U TDS, PRECAUTIONARY WASHED DOWN FROM 4180M & TAGGED COMPRESSION / CONTAMINATED CEMENT @ 4245M.
43433.1875 | 43433.25 | 1.5 | EVAL | PT-P | DC | DRILLED OUT CEMENT FROM 4245M TO 4303M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA / SANDSTONE & CLAYSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING CEMENT ABOVE 5" LINER TOP
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CARRIED OUT 5" LINER CEMENT JOB AS PER PROGRAM. SET LINER TOP PACKER & POOH LINER HANGER SETTING TOOL TO SURFACE. M/U & RIH 6" PDC BIT (22RR5) WITH SLICK ROTARY BHA TO 3098M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL CEMENT / CLEAN OUT TO 5" LINER TOP. CIRCULATE & POOH TO SURFACE WHILE L/DOWN 68 X 5" DP STANDS TO MAKE SPACE AT DERRICK FOR DST STRING.
REMARKS |  |  | WF TRS CREW & EQUIPMENT + WF LINER ENGINEER & EQUIPMENT RELEASED ON 28-NOV-2018.
Formulas:
DHARIAN-1-ST-3 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+21