## DDR#348
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 348
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-04-16
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 5506 / 5450 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | S. KHALID AZIM / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4976.2 | 4944.79 |  |  | 4761 mMD PBTD |  |  | DAYS SINCE SPUD: | [6 empty] | 347.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ HUSSAIN |  |  | MD/TVD @ 06:00HRS: |  | 4976.2 | 4944.79 |  |  | 4761 mMD PBTD |  |  | DAILY PROGRESS @ 00:00HRS:
2020-04-15 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  | 86 | IN (M) |  | 4761 |  | OUT (M) | 4761 |  | STRING (BBL) | 210
CHECK TIME |  | 20:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 664.2
DEPTH, MD (M) |  | 4976 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  |  | W/F WINDOW MILL |  |  | 6 |  |  | 3 1/2 REG |  | 0.48 |  |  | PITS (BBL) | 576
MW IN (SG) |  | 1.63 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  |  |  | BIT SUB |  |  | 4.75 | 1.5 |  | 3 1/2 IF |  | 0.45 |  |  | ACT. SYS (BBL) | 1450.2
MW OUT (SG) |  | 1.63 | INST. ROP (M/HR) |  |  |  | TYPE |  |  |  |  | CSG SCRAPER |  |  | 6 | 1.875 |  | 3 1/2 IF |  | 1.6 |  |  | RESV. SYS (BBL) | 320
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  |  | 1 X DC |  |  | 4.75 | 2.125 |  | 3 1/2 IF |  | 9.27 |  |  | KILL MUD (BBL) | 60
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | X/O |  |  | 4.75 | 2.6875 |  | 3 1/2 REG |  | 1.09 |  |  | KILL MW (SG) | 2.2
µ FUNNEL (SEC) |  | 62 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  |  |  | WATERMELON MILL |  |  | 6 | 1.5 |  | 3 1/2 REG |  | 1.64 |  |  | TOTAL | 1830.2
PV |  | 31 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  |  |  | X/O |  |  | 4.75 | 1.5 |  | 3 1/2 IF |  | 0.46 |  |  | DIESEL (LTR)
YIELD POINT |  | 27 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | 12 X DC's |  |  | 4.75 | 2.125 |  | 3 1/2 IF |  | 109.86 |  |  | RIG TANK | 116092
GEL ST. |  | 12/16 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | 27 X HWDP |  |  | 3.5 | 2.8125 |  | 3 1/2 IF |  | 254.83 |  |  | CAMP TANK | 19022
WL (ml/30 min) |  | 5.2 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 4290
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) |  | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 135114
ALK (FILT.) |  | 0.4/1.3 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH |  | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 679036
MAX SHIELD % |  | 2 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 78000
KCl (%) |  | 4.2 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 43875
KCl (mg/l) |  | 40040.7 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 42000
CHLORIDES (mg/l) |  | 72000 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) |  | 600 | 3 1/2" HWDPS | 4.53 | STAB - 2 |  | TFA (IN²) | [15 empty] | POB
PENETRAX % |  | 1 | 4 3/4" DCS | 4.53 | SPSA |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 379.68 |  |  | MPCL | 3
MAX GUARD % |  | 1 | DAILY BHA ROT. HRS |  | 4.53 |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 15 |  |  | MPCL SERV | 21
SOLIDS % |  | 20.61 | DAILY ON BOTTOM HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) |  | 3.8 | DAILY CIRC. HRS |  | 5.05 |  | BIT NO. |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 4
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4870.72/4846.41 |  | 23.39 |  | 287.64 |  |  | 2.08 |  | MWD |  | TOTAL | 109
DAILY WELL COST (US$) |  | 33135 | SHAKER-2 | 3 x 140 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4900.74/4874.24 |  | 20.54 |  | 288.18 |  |  | 2.86 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 23981382 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4916.03/4888.58 |  | 20.21 |  | 285.21 |  |  | 2.13 |  | MWD |  | LAST CSG SIZE
% OF AFE SPENT |  | 120.5% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | 4934.58/4905.93 |  | 20.45 |  | 288.74 |  |  | 0.31 |  | MWD |  | FIT (EMW)
[12 empty] | 4962.88/4932.45 |  | 20.39 |  | 287.81 |  |  | 0.35 |  | MWD |  | MAASP (PSI)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4925 | 1200/1220 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4925 | 1700/1750 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-03-20 | 2020-04-19 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4925 | 2500/2500 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4773/4757
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4788/4770.97
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-04-10 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 22 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 250 |  | KUSSAK | 4813/4794.01
STRETCHER DRILL | 2020-03-20 | 2020-04-19 | NEXT BOP TEST DATE |  | 2020-04-24 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4858/4834.66
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-15
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43936 | 43936.1354 | 3.25 | EVAL | NPT-UP | BHA / DP | CONT'D POOH BHA FROM 104M TO SURFACE, MEANWHILE L/DOWN ALL BHA COMPONENTS (FROM HOLE AND DERRICK) SGL BY SGL FROM CATWALK FOR NECESSARY INSPECTION.
43936.1354 | 43936.1875 | 1.25 | EVAL | NPT-UP | BHA / DP | P/UP & M/UP W/F 6'' MILL + BIT SUB + 6'' SCRAPER + 1 X 4 3/4'' DC + 6'' WATERMELON MILL. RIH TO 15M.
43936.1875 | 43936.3021 | 2.75 | EVAL | NPT-UP | BHA / DP | CONT'D RIH FROM 15M TO 379M. MEANWHILE P/UP 12 x 4 3/4'' DC's & 27 x 3 1/2'' HWDP's SL BY SGL FROM CATWALK. FLUSHED BHA.
43936.3021 | 43936.5521 | 6 | EVAL | NPT-UP | RIH | CONT'D RIH FROM 379M TO 3395M (TOL).
43936.5521 | 43936.5625 | 0.25 | EVAL | NPT-UP | CIR | FLUSHED STRING. MEANWHILE SERVICED TDS.
43936.5625 | 43936.625 | 1.5 | EVAL | NPT-UP | RS | CUT AND SLIPPED 40M D.LINE. ADJUSTED CROWN O MATIC & RESET ACS.
43936.625 | 43936.6458 | 0.5 | EVAL | NPT-UP | RIH | CONT'D RIH FROM 3395M TO 3567M.
43936.6458 | 43936.6875 | 1 | EVAL | NPT-UP | RR | WHILE RIH AT 3567M, OBSERVED COMPLETE POWER SHUT DOWN. TROUBLESHOOTED & RECTIFIED THE SAME.
43936.6875 | 43936.8021 | 2.75 | EVAL | NPT-UP | RIH | CONT'D RIH FROM 3567M TO 4713M.
43936.8021 | 43936.8125 | 0.25 | EVAL | NPT-UP | RW | CONNECTED TDS, PRECAUTIONARY WASHED DOWN FROM 4713M TO TAG BTM AT 4761M.
43936.8125 | 43936.9792 | 4 | EVAL | NPT-UP | COC / CIR | WORKED ON SCRAPER WHILE ROTATING AND RECIPROCATING STRING. MEANWHILE CIRCULATED TO CLEAN HOLE. (SCRAPED INTERVAL: 4712M TO 4761M). OBSERVED CMT AT BTM UP.
43936.9792 | 43936.9896 | 0.25 | EVAL | NPT-UP | FC | FLOW CHECKED- WELL STATIC.
43936.9896 | 43937 | 0.25 | EVAL | NPT-UP | POOH | PUMPED SLUG, POOH FROM 4761M TO 4712M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-16
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43937 | 43937.25 | 6 | EVAL | NPT-UP | POOH | CONT'D POOH FROM 4712M TO 1694M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA : SANDSTONE, CLAYSTONE, SHALE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | POOH W/F 6'' MILL & SCRAPER ASSEMBLY IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE, L/DOWN BHA COMPONENTS, P/UP AND M/UP W/F 6'' MILL AND SCRAPER ASSEMBLY, RIH TO 3395M, CUT AND SLIPPED D. LINE, RIH TO TAG BTM AT 4761M, WORKED ON SCRAPER FROM 4761-4712M MEANWHILE CIRCULATION, POOH TO 4712M & IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE, L/DOWN W/F MILL AND SCRAPER ASSEMBLY, WHIPSTOCK JOB.
REMARKS |  |  | RECEIVED SLB DIRECTIONAL TOOLS.
Formulas:
MIRAJ-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14