## DDR#349
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 349
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-12-05
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO / M. AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 4770 / 4472.09 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 132.13
RIG REP. (TP): |  | TARIQ BUTT / FAYYAZ HUSSAIN MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4770 / 4472.09 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2018-12-04 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5 % KCL PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  |  |  | BHA No. |  |  | 59 | IN (M) |  | 4770 |  | OUT (M) |  |  | STRING (BBL) | 45
CHECK TIME | 8:30 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 811
DEPTH, MD (M) | 4770 | 4770 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  |  |  | MILL BIT |  |  | 4.0625 | 1 |  | 2 3/8 REG |  | 0.51 |  |  | PITS (BBL) | 319
MW IN (SG) | 1.7 | 1.7 | DAILY PROGRESS (M) |  |  |  | TYPE |  |  |  | 5" SCRAPER |  |  | 5 | 1 |  | 2 3/8 REG |  | 0.89 |  |  | ACT. SYS (BBL) | 1175
MW OUT (SG) | - | - | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  | BIT SUB |  |  | 3.125 | 1.5625 |  | 2 7/8 PAC |  | 0.73 |  |  | RESV. SYS (BBL) | 321
ECD (SG) | - | - | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | 15 X DCS |  |  | 3.125 | 1.5625 |  | 2 7/8 PAC |  | 138.42 |  |  | KILL MUD (BBL) | 320
FL TEMP. °F | - | - | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") |  |  |  | 29 X DPS |  |  | 2.875 | 1.5 |  | 2 7/8 PAC |  | 274.58 |  |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 56 | 56 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  |  | X-OVER |  |  | 4.75 | 1.5 |  | 3 1/2 IF |  | 0.33 |  |  | TOTAL | 1816
PV | 30 | 29 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | X-OVER |  |  | 4.6875 | 1.5 |  | 3 1/2 REG |  | 0.44 |  |  | DIESEL (LTR)
YIELD POINT | 20 | 21 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | 7" SCRAPER |  |  | 7 | 1.75 |  | 3 1/2 REG |  | 0.94 |  |  | RIG TANK | 96095
GEL ST. | 7/11 | 7/11 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | BIT SUB |  |  | 4.5625 | 2.4375 |  | 3 1/2 IF |  | 0.92 |  |  | CAMP TANK | 32114
WL (ml/30 min.) | 3 | 3 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 5891
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED | 25000
ALK (MUD) | 0.6 | 0.6 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 128209
ALK (FILT.) | 0.3 | 0.3 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 35000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 107700
KCl (mg/l) | 53387.6 | 53387.6 | JAR | 96.85 | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 107700
CHLORIDES | 29000 | 29000 | 3 1/8" DCS | 34.65 | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 435000
CALCIUM | 280 | 280 | 2 7/8" DPS | 34.65 | NMDC |  | HSI | [14 empty] | POB
OIL % | 4 | 4 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 417.76 |  |  | MPCL | 4
LUBE % | 1 | 1 | BHA ROT. HRS |  |  |  | BIT NO. |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 3 |  |  | MPCL SERV | 16
SOLIDS % | 23.77 | 23.77 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. | 5 | 5 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 50
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 15
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD (M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 120 | 2 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4647/4382.61 |  | 42.19 |  | 81.49 |  |  | 1.83 |  | MWD |  | TOTAL | 113
DAILY WELL COST (US$) |  | 30152.2789 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4676/4403.94 |  | 43.13 |  | 83.16 |  |  | 1.52 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 21308611.2858 | SHAKER-3 | 1 x 120 | 2 x 120 |  | 7" LINER |  |  | 4446.0 (TOL @ 3253) | 4701/4422.05 |  | 43.98 |  | 82.8 |  |  | 1.06 |  | MWD |  | LAST CSG SIZE | 5"
% OF AFE SPENT |  | 118.1% | MUD CLEANER | 1 x 140 | 2 x 170 |  | 5" LINER |  |  | 4766.0 (TOL @ 4367) | 4713/4430.68 |  | 44.03 |  | 82.27 |  |  | 0.93 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P3) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | HANGU | 4571/4323.65
FIRE DRILL | 2018-11-14 | 2018-12-14 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 | [7 empty] | DANDOT-TOBRA | 4587/4333.72
PIT DRILL | 2018-11-14 | 2018-11-29 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BHAGANWALA | 4608/4354.35
KICK DRILL | 2018-11-28 | 2018-12-28 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | JUTANA | 4627/4367.58
TRIP DRILL | 2018-11-28 | 2018-12-28 | LAST BOP TEST DATE |  | 2018-11-11 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 9 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK | 4657/4390.03
STRETCHER DRILL | 2018-11-08 | 2018-12-08 | NEXT BOP TEST DATE |  | 2018-12-02 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 9 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4724/4438.61
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-12-04
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43438 | 43438.0938 | 2.25 | EVAL | PT-P | CIR | CIRCULATED FOR BTM UP.
43438.0938 | 43438.1042 | 0.25 | EVAL | PT-P | PS | PUMPED SLUG.
43438.1042 | 43438.4688 | 8.75 | EVAL | PT-P | POOH | POOH MILL BIT FROM 4762M TO TOP OF BHA @ 424M.
43438.4688 | 43438.5104 | 1 | EVAL | NPT-P | RS | SERVICED TDS.
43438.5104 | 43438.5208 | 0.25 | EVAL | PT-P | RU | R/U WELLSERVE POWER TONG.
43438.5208 | 43438.6667 | 3.5 | EVAL | PT-P | BHA | POOH FROM 424M TO SURFACE. WHILE POOH L/D JAR, 15 X 3 1/8" DCS, 30 X 2 7/8" DPS SINGLE BY SINGLE & MILL BIT.
43438.6667 | 43438.8438 | 4.25 | EVAL | PT-P | COC | P/U, M/U 4 1/16" FLAT BTM MILL BIT (RR) WITH SLIM BHA & 5" X 7" CASING SCRAPERS IN TANDEM & RIH DOWN TO 417M.
43438.8438 | 43439 | 3.75 | EVAL | PT-P | COC | RIH TANDEM SCRAPER BHA FROM 417M TO 2225M ON 3 1/2" DPS. WHILE RIH P/U 4 3/4" DRILLING JAR.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-12-05
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43439 | 43439.25 | 6 | EVAL | PT-P | COC | CONT'D RIH TANDEM SCRAPER BHA FROM 2225M TO 4600M ON 3 1/2" / 5" DPS. SCRAPED TWICE FROM 4367M TO 4600M.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | RIH TANDEM SCRAPER BHA
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH MILL BIT TO SURFACE. M/U MILL BIT (RR) WITH SLIM BHA & 5" X 7" CASING SCRAPERS IN TANDEM & RIH DOWN TO 2225M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONDUCT 5" X 7" TANDEM CASING SCRAPERS TRIP. RECORD 5" LINER CBL-VDL-USIT & VSP LOG AS PER PROGRAM.
REMARKS
Formulas:
DHARIAN-1-ST-3 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+21