## DDR#35
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 35
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-06-08
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | IKRAMULLAH / AHSEN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 2222 / 2222 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 34.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 2239 / 2239 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 61
2019-06-07 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 17.5 |  | BIT NO. |  | 4RR1 |  | BHA NO. |  |  | 7 | IN (M) |  | 2101 |  | OUT (M) |  |  | STRING (BBL) | 147
CHECK TIME | 16:00 | 23:59 | MD @ 00:00HR (M) |  | 2222 |  | SIZE (IN) |  | 17.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 2023
DEPTH, MD (M) | 2203 | 2222 | TVD @ 00:00HR (M) |  | 2222 |  | MANUFACTURER |  | NOV |  | PDC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.36 | 0.11629 |  | PITS (BBL) | 1154
MW IN (SG) | 2.06 | 2.06 | DAILY PROGRESS (M) |  | 61 |  | TYPE |  | TFH519S |  | BIT SUB (F.V) |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 1.07 | 0.34565 |  | ACT. SYS (BBL) | 3324
MW OUT (SG) | 2.06 | 2.06 | INST. ROP (M/HR) |  | 1.9 |  | SERIAL NO. |  | E260745 |  | STRING STAB |  |  | 17.375 | 3.0625 |  | 7 5/8 REG |  | 2.43 | 0.78498 |  | RESV. SYS (BBL) | 1539
ECD (SG) | 2.07 | 2.07 | AVG. ROP (M/HR) |  | 2.96 |  | IADC CODE |  | S422 |  | 1 X 9 1/2" DC |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 9.23 | 2.9816 |  | KILL MUD (BBL)
FL TEMP. °F | 160 | 160 | AVG. WOB (TON) |  | 12 |  | NOZZLES (1/32") |  | 5 X 16 |  | STRING STAB |  |  | 17.375 | 3 |  | 7 5/8 REG |  | 2.37 | 0.7656 |  | KILL MW (SG)
µ FUNNEL (SEC) | 62 | 63 | AVG. RPM SURFACE |  | 130 |  | DEPTH IN (M) |  | 2101 |  | 2 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 18.3 | 5.9116 |  | TOTAL | 4863
PV | 39 | 40 | AVG. RPM DOWNHOLE |  | 130 |  | DEPTH OUT (M) |  |  |  | STRING STAB |  |  | 17.375 | 3 |  | 7 5/8 REG |  | 2.14 | 0.6913 |  | DIESEL (LTR)
YIELD POINT | 32 | 31 | FLOWRATE (GPM) |  | 800 |  | METERAGE (M) |  | 121 |  | 4 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 36.91 | 11.9234 |  | RIG TANK | 87808
GEL ST. | 12/14 | 11/14 | PRESSURE (PSI) |  | 3600 - 3750 |  | RPM SURF. |  | 80 - 150 |  | X/OVER |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.93 | 0.30043 |  | CAMP TANK | 19110
WL (ml/30 min) | 6.4 | 6.6 | TORQ. ON-BTM (KLB-FT) |  | 7 - 12 |  | RPM BTM. |  | 80 - 150 |  | 2 X 8" DCS |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.34 | 4.0953 |  | CONSUMED | 14345
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 5 - 6 |  | WOB (TON) |  | 5 - 15 |  | DRILLING JAR |  |  | 7.9375 | 3 |  | 6 5/8 REG |  | 9.53 | 2.128 |  | RECEIVED
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  | 130 |  | AVG. ROP (M/HR) |  | 3.2475 |  | 2 X 8" DCS |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.43 | 4.1154 |  | TOTAL | 106918
ALK (FILT.) | 0.4 | 0.4 | PICK-UP WT. (TON) |  | 135 |  | BIT ROT HRS. |  | 37.26 |  | X/OVER |  |  | 7.625 | 2.8125 |  | 5 1/2 FH |  | 0.81 | 0.18087 |  | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 125 |  | K-REVS IN 24 HRS |  | 167.39 |  | 10 X 5 1/2" HWDPS |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 94.38 | 8.4468 |  | RIG STORAGE | 480000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 311.46 | [12 empty] | CAMP STORAGE | 81000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 18.6 | [12 empty] | CONSUMED | 170400
KCl (mg/l) | 51862.2 | 51862.2 | JAR | 71.36 | STAB - 1 | 269.86 | JET VELOCITY (M/SEC) |  | 79.4 | [12 empty] | RECEIVED | 195400
CHLORIDES (mg/l) | 25000 | 25000 | MOTOR |  | STAB - 2 | 269.86 | TFA (IN²) |  | 0.98 | [12 empty] | TOTAL | 561000
HARDNESS (mg/l) | 400 | 400 | 9 1/2" DCS | 279.86 | STAB - 3 | 71.36 | HSI |  | 2.008 | [12 empty] | POB
SAND % | 0.2 | 0.2 | 8" DCS | 279.86 | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 215.23 |  |  | MPCL | 5
LUBRICANT % | 1 | 1 | BHA ROT. HRS |  | 279.86 |  | BIT NO. 4RR1 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 33 |  |  | MPCL SERV | 25
SOLIDS % | 34.54 | 34.54 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 22 |  |  | SECURITY
M.B.T. (lb/bbl) | 7.5 | 7.5 | CIRC. HRS |  | 23 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 44
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 7
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 30" CONDUCTOR |  |  | 37 | 1953/1953 |  | 0.08 | [6 empty] | MWD |  | TOTAL | 105
DAILY WELL COST (US$) |  | 60286.1075 | SHAKER-2 | 1 X 100 | 2 X 100 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 1981/1981 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 3638556.9467 | SHAKER-3 | 1 X 100 | 2 X 100 | [5 empty] | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 18.28% | MUD CLEANER | 3 X 140 | [6 empty] | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | LOT (EMW) | 2.16
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 82
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PRESS PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | JX CHINA | 21.25 | 5000 | P-1 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 30 |  | 2218 | 250 / 230 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JX CHINA | 21.25 | 5000 | P-2 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 40 |  | 2218 | 300 / 300 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-05-09 | 2019-06-08 | BLIND RAMS | JX CHINA | 21.25 | 5000 | P-3 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 50 |  | 2218 | 400 / 400 |  |  | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-06-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  | 2019-06-17 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-07
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43623 | 43623.4271 | 10.25 | DRL | PT-P | D | DRILLED 17 1/2" HOLE FROM 2161M TO 2188M & ADJUSTED DRILLING PARAMETERS TO OPTIMIZE ROP.
43623.4271 | 43623.4583 | 0.75 | DRL | NPT-UP | RR | WORKED ON MUD PUMPS.
43623.4583 | 43623.5208 | 1.5 | DRL | PT-P | D | DRILLED 17 1/2" HOLE FROM 2188M TO 2190M. REAMED / WASHED DRILLED INTERVAL AT CONNECTION.
43623.5208 | 43623.5417 | 0.5 | DRL | NPT-P | RS | SERVICED TDS.
43623.5417 | 43624 | 11 | DRL | PT-P | D | DRILLED 17 1/2" HOLE FROM 2190M TO 2222M & ADJUSTED DRILLING PARAMETERS TO OPTIMIZE ROP. REAMED / WASHED DRILLED INTERVAL AT CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-08
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43624 | 43624.25 | 6 | DRL | PT-P | D | DRILLED 17 1/2" HOLE FROM 2222M TO 2239M & ADJUSTED DRILLING PARAMETERS TO OPTIMIZE ROP.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 17 1/2" HOLE FROM 2161M TO 2222M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 17 1/2" HOLE.
REMARKS |  |  | CHANGED MUD PUMP # 1 SUCTION & DISCHARGE VALVES + SEATS + GASKET, MUD PUMP # 2 LINERS + PISTONS + SUCTION & DISCHARGE VALVES + SEATS + GASKETS AND MUD PUMP # 3 LINERS + PISTONS + SUCTION & DISCHARGE VALVES + SEATS DURING DRILLING.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14