## DDR#350
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [14 empty] | Report No. |  | 350
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-04-18
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4995 / 4945 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | S. KHALID AZIM / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4761 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 349.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ HUSSAIN |  |  | MD/TVD @ 06:00HRS: |  | 4761 | [5 empty] | DAILY PROGRESS @ 00:00HRS:
2020-04-17 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  | BHA NO. |  |  | 87 | IN (M) |  | 4761 |  | OUT (M) | 4761 |  | STRING (BBL) | 197
CHECK TIME | 14:00 | 21:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 654
DEPTH, MD (M) | 4759 | 4761 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | W/F WHIPSTOCK |  |  | 5.5 |  |  |  |  | 4.82 |  |  | PITS (BBL) | 592
MW IN (SG) | 1.65 | 1.65 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  |  | W/F LEAD MILL |  |  | 6 | 2.25 |  | 3 1/2 REG |  | 0.61 |  |  | ACT. SYS (BBL) | 1443
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  |  | W/F FLEX MILL |  |  | 6 | 1.9375 |  | 3 1/2 IF |  | 1.64 |  |  | RESV. SYS (BBL) | 390
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  | 1 X HWDP |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 9.42 |  |  | KILL MUD (BBL)
FL TEMP. °F | 120 | 125 | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  | MWD |  |  | 4.75 | 2.25 |  | 3 1/2 REG |  | 9.91 |  |  | KILL MW (SG)
µ FUNNEL (SEC) | 52 | 55 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  |  | 12 X DC's |  |  | 4.75 | 2.125 |  | 3 1/2 REG |  | 109.86 |  |  | TOTAL | 1833
PV | 31 | 32 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  |  | 26 X HWDP |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 245.41 |  |  | DIESEL (LTR)
YIELD POINT | 28 | 29 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [14 empty] | RIG TANK | 125235
GEL ST. | 12/15 | 13/16 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [14 empty] | CAMP TANK | 25022
WL (ml/30 min) | 4.8 | 4.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [14 empty] | CONSUMED | 6026
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | RECEIVED | 27000
ALK (MUD) | 0.4 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [14 empty] | TOTAL | 150257
ALK (FILT.) | 0.3/1.3 | 0.3/1.3 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [14 empty] | WATER (LTR)
pH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | RIG STORAGE | 627212
MAX SHIELD % | 2 | 2 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [14 empty] | CAMP STORAGE | 73000
KCl (%) | 4.5 | 4.5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CONSUMED | 40450
KCl (mg/l) | 45761 | 46142 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | RECEIVED | 31500
CHLORIDES (mg/l) | 90000 | 90500 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | DRL WASTE
HARDNESS (mg/l) | 600 | 400 | 3 1/2" HWDPS | 19.89 | STAB - 2 |  | TFA (IN²) | [14 empty] | POB
PENETRAX % | 1 | 1 | 4 3/4" DCS | 20.13 | SPSA |  | HSI |  |  |  | TOTAL LENGTH (M) | [7 empty] | 381.67 |  |  | MPCL | 3
MAX GUARD % | 2 | 2 | DAILY BHA ROT. HRS |  | 15.6 |  | MOTOR REV/GAL |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 20
SOLIDS % | 20.29 | 20.26 | DAILY ON BOTTOM HRS |  | 9.65 |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 3.8 | 3.8 | DAILY CIRC. HRS |  | 17.54 |  | BIT NO. |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 65
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 27
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  | 579 | 4870.72/4846.41 |  | 23.39 |  | 287.64 |  |  | 2.08 |  | MWD |  | TOTAL | 120
DAILY WELL COST (US$) |  | 130765 | SHAKER-2 | 3 x 140 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  | 2419 | 4900.74/4874.24 |  | 20.54 |  | 288.18 |  |  | 2.86 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 24135887 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  | 4549 / 4391 (WND) | 4916.03/4888.58 |  | 20.21 |  | 285.21 |  |  | 2.13 |  | MWD |  | LAST CSG SIZE
% OF AFE SPENT |  | 121.2% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  | 4815 / 3397 (TOL) | 4934.58/4905.93 |  | 20.45 |  | 288.74 |  |  | 0.31 |  | MWD |  | FIT (EMW)
[7 empty] | ST-2 IN 7'' LINER |  |  | 4759 (WND) | 4962.88/4932.45 |  | 20.39 |  | 287.81 |  |  | 0.35 |  | MWD |  | MAASP (PSI)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | HANGU | 4740/4726.58
FIRE DRILL | 2020-03-20 | 2020-04-19 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 | [7 empty] | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-04-10 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 23 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK
STRETCHER DRILL | 2020-03-20 | 2020-04-19 | NEXT BOP TEST DATE |  | 2020-04-24 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-17
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43938 | 43938.0625 | 1.5 | EVAL | NPT-UP | RIH | CONT'D RIH FROM 2879M TO 3369M.
43938.0625 | 43938.0729 | 0.25 | EVAL | NPT-UP | CIR | BROKE CIRCULATION.
43938.0729 | 43938.25 | 4.25 | EVAL | NPT-UP | RIH | CONT'D RIH FROM 3369M TO 4742M.
43938.25 | 43938.2917 | 1 | EVAL | NPT-UP | RW | CONNECTED TDS, RECORDED STRING WT(UP/DOWN). WASHED DOWN FROM 4742M TO TAG BTM AT 4761M.
43938.2917 | 43938.3542 | 1.5 | EVAL | NPT-UP | OTH | P/UP STRING, ORIENTED TOOL FACE AT DESIRED DIRECTION. APPLIED COMPRESSION = 3 TON TO SHEAR WHIPSTOCK ANCHOR BOLTS (OBSERVED INDICATION AT WT. INDICATOR). FURTHER COMPRESSED = 17 TONS TO SHEAR LEAD & WHIPSTOCK BOLT (OBSERVED INDICATION AT WT. INDICATOR). SET DOWN WT 23 TONS TO CONFIRM WHIPSTOCK SETTING. P/UP STRING & RETAG WHIPSTOCK.
43938.3542 | 43938.6146 | 6.25 | DRL | PT-P | MIL | COMMENCED MILLING WINDOW IN 7'' LINER. MILLED TO ESTABLISH SIDETRACK FROM 4756.18M TO 4759M. MEANWHILE CIRCULATED HV PILLS INTERMITTENTLY. INCREASED MUD SP. GR FROM 1.63SG TO 1.65SG. (RECEIVED METAL SHAVINGS DURING MILLING OPERATION).
43938.6146 | 43938.9062 | 7 | DRL | PT-P | MIL | MILLED DOWN 6'' HOLE FROM 4759M TO 4761M. (OBSERVED CMT + FORMATION SAMPLES AT BTM UP).
43938.9062 | 43939 | 2.25 | DRL | PT-P | CIR | PUMPED 30 BBL HV PILL MEANWHILE REAMED AND SMOOTHEN ACROSS WINDOW. PASSED THROUGH SEVERAL TIMES FROM 4755M TO 4761M WITH AND WITHOUT ROTATION
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-18
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43939 | 43939.0417 | 1 | DRL | PT-P | CIR | CONT'D CIRCULATION TO CLEAN HOLE. MEANWHILE CHECKED SMOOTHNESS OF WINDOW WITH & WITHOUT PUMP. OK.
43939.0417 | 43939.0521 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43939.0521 | 43939.1667 | 2.75 | DRL | PT-P | RIH | PUMPED SLUG, POOH FROM 4761M TO 3419M.
43939.1667 | 43939.1771 | 0.25 | DRL | PT-P | CIR | CONNECTED TDS & FLUSHED ACROSS 7'' TOL AT 3397M.
43939.1771 | 43939.25 | 1.75 | DRL | PT-P | POOH | POOH FROM 3397M TO 2581M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | DANDOT/TOBRA : SANDSTONE, CLAYSTONE.
OPERATIONS AT 06:00 HRS |  |  | POOH WITH W/F MILLING ASSEMBLY IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH WHIPSTOCK TO 4761M, ORIENTED WHIPSTOCK, SET SAME, MILLED WINDOW TO ESTABLISH SIDETRACK AT 4759M MEANWHILE INCREASED MUD SP GR FROM 1.63SG TO 1.65SG. MILLED DOWN 6'' HOLE FROM 4759M TO 4761M. CIRCULATION IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CIRCULATION, FLOW CHECK, POOH TO SURFACE. L/DOWN W/F MILLING ASSEMBLY, RIH WITH DIRECTIONAL ASSEMBLY.
REMARKS
Formulas:
MIRAJ-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14