## DDR # 352
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 352
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-04-20
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4995 / 4945 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | S. KHALID AZIM / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4774 | 4757.25 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 351.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JEELANI |  |  | MD/TVD @ 06:00HRS: |  | 4775 | 4758.16 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 13
2020-04-19 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | RUN NO. |  |  | 70 |  | BHA NO. |  |  | 88 | IN (M) |  | 4761 |  | OUT (M) |  |  | STRING (BBL) | 202
CHECK TIME | 14:00 | 23:59 | MD @ 00:00HR (M) |  | 4774 |  | BIT NO. |  |  | 29 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 667.4
DEPTH, MD (M) | 4767 | 4774 | TVD @ 00:00HR (M) |  | 4757.25 |  | SIZE (IN) |  |  | 6 |  | TRICONE BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.18 |  |  | PITS (BBL) | 476
MW IN (SG) | 1.65 | 1.65 | DAILY PROGRESS (M) |  | 13 |  | MANUFACTURER |  |  | SMITH |  | MUD MOTOR |  |  | 5.875 | 3.75 |  | 3 1/2 IF |  | 7.2 |  |  | ACT. SYS (BBL) | 1345.4
MW OUT (SG) | 1.65 | 1.65 | INST. ROP (M/HR) |  | 0.7 |  | TYPE |  |  | XR50Y |  | ST. STAB |  |  | 5.875 | 2.2 |  | 3 1/2 IF |  | 1.37 |  |  | RESV. SYS (BBL) | 549
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 0.74 |  | SERIAL NO. |  |  | RJ5617 |  | FLOAT SUB |  |  | 4.75 | 2.125 |  | 3 1/2 IF |  | 0.83 |  |  | KILL MUD (BBL)
FL TEMP. °F |  | 117 | AVG. WOB (TON) |  | 4 |  | IADC CODE |  |  | 637 |  | L. SAVER SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.46 |  |  | KILL MW (SG)
µ FUNNEL (SEC) | 54 | 52 | AVG. RPM SURFACE |  | 30 |  | NOZZLES (1/32") |  |  | 2 X 12 + 1 X 14 |  | SPSA (MWD) |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 9.45 |  |  | TOTAL | 1894.4
PV | 31 | 30 | AVG. RPM DOWNHOLE |  | 157 |  | DEPTH IN (M) |  |  | 4761 |  | NMDC |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.12 |  |  | DIESEL (LTR)
YIELD POINT | 29 | 28 | FLOWRATE (GPM) |  | 220 |  | DEPTH OUT (M) |  |  |  |  | 18 X HWDP's |  |  | 3.5 | 2.1875 |  | 3 1/2 IF |  | 169.84 |  |  | RIG TANK | 117715
GEL ST. | 13/18 | 11/16 | PRESSURE (PSI) |  | 3000-3200 |  | METERAGE (M) |  |  | 13 |  | D. JAR |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 8.99 |  |  | CAMP TANK | 24114
WL (ml/30 min) | 4.2 | 4.2 | TORQ. ON-BTM (KLB-FT) |  | 1-3 |  | RPM SURF. |  |  | 30 |  | 9 X HWDP's |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 85.05 |  |  | CONSUMED | 3607
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 1-2 |  | RPM BTM. |  |  | 127 + 30 | [12 empty] | RECEIVED
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  | 142 |  | WOB (TON) |  |  | 2-6 | [12 empty] | TOTAL | 141829
ALK (FILT.) | 0.2/1.2 | 0.2/1.2 | PICK-UP WT. (TON) |  | 145 |  | AVG. ROP (M/HR) |  |  | 0.73822 | [12 empty] | WATER (LTR)
pH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 140 |  | BIT ROT HRS. |  |  | 17.61 | [12 empty] | RIG STORAGE | 600776
MAX SHIELD % | 2.6 | 2.6 | SLIMPULSE D & I OFF BIT - (M) |  | 11.6 |  | K-REVS IN 24 HRS |  |  | 146.79 | [12 empty] | CAMP STORAGE | 80000
KCl (%) | 5 | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  | 146.79 | [12 empty] | CONSUMED | 82499
KCl (mg/l) | 48620.8 | 49192.9 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  | 63.2 | [12 empty] | RECEIVED | 58600
CHLORIDES (mg/l) | 100000 | 100500 | JAR | 5.42 | STAB - 1 | 5.42 | JET VELOCITY (M/SEC) |  |  | 57.71 | [12 empty] | DRL WASTE
HARDNESS (mg/l) | 360 | 360 | 3 1/2" HWDPS | 26.16 | STAB - 2 |  | TFA (IN²) |  |  | 0.371 | [12 empty] | POB
PENETRAX % | 2 | 2 | 4 3/4" DCS |  | SPSA |  | HSI |  |  | 1.99 |  | TOTAL LENGTH (M) | [7 empty] | 292.49 |  |  | MPCL | 3
MAX GUARD % | 2 | 2 | DAILY BHA ROT. HRS |  | 5.42 |  | MOTOR REV/GAL |  |  | 0.58 |  | BHA WT. IN MUD (TON) | [7 empty] | 8 |  |  | MPCL SERV | 19
SOLIDS % | 20.38 | 19.96 | DAILY ON BOTTOM HRS |  | 17.61 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 6 |  |  | SECURITY
M.B.T. (lb/bbl) | 3.8 | 3.8 | DAILY CIRC. HRS |  | 20.91 |  | BIT NO. |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 3
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [11 empty] | TOTAL | 104
DAILY WELL COST (US$) |  | 63440 | SHAKER-2 | 3 x 140 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 24234177 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | [11 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 121.7% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | [11 empty] | FIT (EMW)
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | [11 empty] | MAASP (PSI)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4772 | 1300 /1280 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4772 | 1800 /1780 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-03-20 | 2020-04-19 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4772 | 2380 /2300 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-04-10 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 22 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK
STRETCHER DRILL | 2020-03-20 | 2020-04-19 | NEXT BOP TEST DATE |  | 2020-04-24 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-19
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43940 | 43940.1354 | 3.25 | DRL | PT-P | RIH | CONT'D RIH FROM 3394M TO 4740M, MEANWHILE FILLED UP STRING EVERY 15 STDS.
43940.1354 | 43940.1562 | 0.5 | DRL | PT-P | RW | CONNECTED TDS, PRECAUTIONARY WASHED DOWN FROM 4740M TO 4761M. MEANWHILE RECORDED SCR & CHECKSHOT.
43940.1562 | 43940.7812 | 15 | DRL | PT-P | DM | COMMENCED DRILLING. DRILLED 6'' HOLE FROM 4761M TO 4770M IN SLIDE MODE.
43940.7812 | 43941 | 5.25 | DRL | PT-P | DM | SWITCHED OVER TO ROTARY MODE. DRILLED 6'' HOLE FROM 4770M TO 4774M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-20
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43941 | 43941.0417 | 1 | DRL | PT-P | DM | DRILLED 6'' HOLE FROM 4774M TO 4775M. WHILE DRILLING AT 4775M, OBSERVED DECREMENT OF 800- 900 PSI IN SPP.
43941.0417 | 43941.0625 | 0.5 | DRL | PT-P | RW | P/UP STRING & SWITCHED OVER PUMP. NO IMPROVEMENT OBSERVED IN SPP. CHECKED SURFACE SYTEM. WASHED DOWN TO BTM AT 4775M. TAGGED BTM WITH & WITHOUT ROTATION, OBSERVED DIFFERENTIAL P, TQ : STEADY & MWD SIGNALS.
43941.0625 | 43941.0833 | 0.5 | DRL | PT-P | RW | PUMPED OUT FROM 4775M TO 4749M (INSIDE 7'' LINER). INSPECTED SURFACE SYSTEM THOROUGHLY. TURNED ON PUMP, NO CHANGE IN SPP OBSERVED. DECIDED TO POOH.
43941.0833 | 43941.0938 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43941.0938 | 43941.25 | 3.75 | DRL | PT-P | POOH | PUMPED SLUG. POOH FROM 4749M TO 3193M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | DANDOT/TOBRA : SANDSTONE, CLAYSTONE.
OPERATIONS AT 06:00 HRS |  |  | POOH MOTOR BHA IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH TO BTM AT 4761M, ORIENTED TF, COMMENCED DRILLING, DRILLED AHEAD 6'' HOLE IN SLIDE/ROTARY MODE FROM 4761M TO 4774M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL DOWN TO +/- 4775M, RECORD CHECK SHOT AND POOH FOR BHA CHANGE, RIH TO BTM & RESUME DRILLING WITH RSS BHA.
REMARKS |  |  | RELEASED W.FORD ENGR's & EQP, 2 X PD ORBIT ARRIVED ON LOCATION.
Formulas:
MIRAJ-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14