## DDR # 353
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 353
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-04-21
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4995 / 4945 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | S. KHALID AZIM / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4775 | 4758.16 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 352.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JEELANI |  |  | MD/TVD @ 06:00HRS: |  | 4775 | 4758.16 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 1
2020-04-20 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | RUN NO. |  |  |  |  | BHA NO. |  |  | 89 | IN (M) |  | 4765 |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME |  | 19:00 | MD @ 00:00HR (M) |  | 4775 |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 936.6
DEPTH, MD (M) |  | 4775 | TVD @ 00:00HR (M) |  | 4758.16 |  | SIZE (IN) |  |  |  |  | WFD OVERSHOT |  |  | 5.75 | 4.75 |  | 3 1/2 IF |  | 1.12 |  |  | PITS (BBL) | 410
MW IN (SG) |  | 1.65 | DAILY PROGRESS (M) |  | 1 |  | MANUFACTURER |  |  |  |  | 3 X HWDP's |  |  | 3.5 | 2.1875 |  | 3 1/2 IF |  | 28.33 |  |  | ACT. SYS (BBL) | 1346.6
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  |  |  | DRILLING JAR |  |  | 5.875 | 2.2 |  | 3 1/2 IF |  | 8.99 |  |  | RESV. SYS (BBL) | 526
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  |  | 6 X HWDP's |  |  | 4.75 | 2.125 |  | 3 1/2 IF |  | 56.72 |  |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE | [15 empty] | KILL MW (SG)
µ FUNNEL (SEC) |  | 58 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") | [15 empty] | TOTAL | 1872.6
PV |  | 30 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [15 empty] | DIESEL (LTR)
YIELD POINT |  | 27 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 112707
GEL ST. |  | 12/16 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 23578
WL (ml/30 min) |  | 4.2 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 5544
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 136285
ALK (FILT.) |  | 0.2/1.2 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 596006
MAX SHIELD % |  | 2.6 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 75000
KCl (%) |  | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 41270
KCl (mg/l) |  | 48620.8 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 31500
CHLORIDES (mg/l) |  | 100200 | JAR | 6.58 | STAB - 1 | 6.58 | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) |  | 360 | 3 1/2" HWDPS | 27.32 | STAB - 2 |  | TFA (IN²) | [15 empty] | POB
PENETRAX % |  | 1.7 | 4 3/4" DCS |  | SPSA |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 95.16 |  |  | MPCL | 3
MAX GUARD % |  | 2 | DAILY BHA ROT. HRS |  | 1.16 |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 1.5 |  |  | MPCL SERV | 22
SOLIDS % |  | 19.97 | DAILY ON BOTTOM HRS |  | 1.03 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 0.5 |  |  | SECURITY
M.B.T. (lb/bbl) |  | 3.8 | DAILY CIRC. HRS |  | 1.94 |  | BIT NO. 29 |  |  | LEFT IN HOLE |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [11 empty] | TOTAL | 109
DAILY WELL COST (US$) |  | 35356 | SHAKER-2 | 3 x 140 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 24269533 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | [11 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 121.9% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | [11 empty] | FIT (EMW)
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | [11 empty] | MAASP (PSI)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4772 | 1300 /1280 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4772 | 1800 /1780 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-03-20 | 2020-04-19 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4772 | 2380 /2300 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-04-20 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK
STRETCHER DRILL | 2020-03-20 | 2020-04-19 | NEXT BOP TEST DATE |  | 2020-05-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-20
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43941 | 43941.0417 | 1 | DRL | PT-P | DM | DRILLED 6'' HOLE FROM 4774M TO 4775M. WHILE DRILLING AT 4775M, OBSERVED DECREMENT OF 800- 900 PSI IN SPP.
43941.0417 | 43941.0625 | 0.5 | DRL | PT-P | RW | P/UP STRING & SWITCHED OVER PUMP. NO IMPROVEMENT OBSERVED IN SPP. CHECKED SURFACE SYTEM. WASHED DOWN TO BTM AT 4775M. TAGGED BTM WITH & WITHOUT ROTATION, OBSERVED DIFFERENTIAL P, TQ : STEADY & MWD SIGNALS.
43941.0625 | 43941.0833 | 0.5 | DRL | PT-P | RW | PUMPED OUT FROM 4775M TO 4749M (INSIDE 7'' LINER). INSPECTED SURFACE SYSTEM THOROUGHLY. TURNED ON PUMP, NO CHANGE IN SPP OBSERVED. DECIDED TO POOH.
43941.0833 | 43941.0938 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43941.0938 | 43941.5104 | 10 | DRL | PT-P | POOH | PUMPED SLUG. POOH FROM 4749M TO 292M.
43941.5104 | 43941.5208 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43941.5208 | 43941.625 | 2.5 | DRL | PT-P | BHA | POOH FROM 292M TO SURFACE. FOUND BHA COMPONENTS MISSING. FISH (6'' TCI BIT + 5 7/8'' MUD MOTOR + 5 7/8''S.STAB + 4 3/4''FLOAT SUB = 9.58M) LIH. OBSERVED CONNECTION BETWEEN FLOAT SUB AND LOWER SAVER SUB FAILED. L/DOWN NMDC & SPSA (RETRIEVED MWD) WITH SAVER SUB ALONG.
43941.625 | 43941.6667 | 1 | DRL | NPT-UP | DP | SHIFTED 19 STDS OF 3 1/2'' DP's FROM ONE SIDE OF DERRICK TO ANOTHER. MEANWHILE ARRANGED FISHING TOOLS AND ENGR.
43941.6667 | 43941.8333 | 4 | DRL | PT-UP | BOPT | HELD PJSM, M/U COMBINATION TOOL ASSY & RETRIEVED WEAR BUSHING. M/U TEST PLUG ASSEMBLY, SET TEST PLUG INSIDE 11'' THS. FLUSHED BOP STACK WITH WATER. P/T ANNULAR BOP @ 500/4500 PSI FOR 5/10 MIN - OK. P/T ROTARY HOSE & STANDPIPE MANIFOLD @ 500/6000 PSI FOR 5/10 MIN - OK. P/T UPPER VARIABLE PIPE RAMS (2 7/8" - 5"), LOWER PIPE RAMS, BLIND RAMS, HYD & MANUAL IBOP, FOSV, HCR & MANUAL VALVES @ KILL & CHOKE LINE, CHOKE MANIFOLD MASTER VALVE, CO-FLEXIP HOSE @ 500/9000 PSI FOR 5/10 MIN - OK. INSTALLED WEAR BUSHING & L/D TEST PLUG ASSEMBLY.
43941.8333 | 43941.8958 | 1.5 | DRL | NPT-UP | BHA | P/UP AND M/UP WFD 5 3/4'' OVERSHOT (DRESSED WITH SPIRAL GRAPPLE) + 3 1/2'' HWDP. RIH AS PER BHA TO 95M.
43941.8958 | 43942 | 2.5 | DRL | NPT-UP | RIH | RIH FROM 95M TO 1525M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-21
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43942 | 43942.1354 | 3.25 | DRL | NPT-UP | RIH | CONT'D RIH FROM 1525M TO 3397M (TOL).
43942.1354 | 43942.1458 | 0.25 | DRL | NPT-UP | CIR | BROKE CIRCULATION.
43942.1458 | 43942.25 | 2.5 | DRL | NPT-UP | RIH | CONT'D RIH FROM 3397M TO 4544M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | DANDOT/TOBRA : SANDSTONE, CLAYSTONE.
OPERATIONS AT 06:00 HRS |  |  | RIH WITH OVERSHOT IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 6'' HOLE DOWN TO 4775M, WHILE DRILLING OBSERVED SIGNIFICANT SPP DROPPED, CHECKED SURFACE SYSTEM & DECIDED TO POOH, POOH TO SURFACE, FOUND BHA COMPONENTS MISSING, PERFORMED BOPT AS PER POLICY, RIH WITH OVERSHOT TO 1525M AND IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH WITH OVERSHOT TO ENGAGE FISH @ +/- 4765M, POOH TO SURFACE, RIH WITH DIRECTIONAL ASSEMBLY TO RESUME DRILLING.
REMARKS |  |  | WFD FISHING ENGR. ON LOCATION, PBL SUB RECEIVED ON LOCATION.
Formulas:
MIRAJ-1-ST-2 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14