## DDR#354
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 354
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-12-10
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4943 / 4590 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4770 / 4472.09 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 137.13
RIG REP. (TP): |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4770 / 4472.09 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2018-12-09 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | POTASSIUM FORMATE BRINE |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME |  | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 870.1
DEPTH, MD (M) |  | 4770 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER | [14 empty] | PITS (BBL) | 310
MW IN (SG) |  | 1.5 | DAILY PROGRESS (M) |  |  |  | TYPE | [14 empty] | ACT. SYS (BBL) | 1180.1
MW OUT (SG) |  | - | INST. ROP (M/HR) |  |  |  | SERIAL NO. | [14 empty] | RESV. SYS (BBL) | 271
ECD (SG) |  | - | AVG. ROP (M/HR) |  |  |  | IADC CODE | [14 empty] | KILL MUD (BBL) | -
FL TEMP. °F |  | - | AVG. WOB (TON) |  |  |  | NOZZLES (1/32") | [14 empty] | KILL MW (SG) | -
µ FUNNEL (SEC) |  | - | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) | [14 empty] | TOTAL | 1451.1
PV |  | - | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT |  | - | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 91159
GEL ST. |  | - | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 29432
WL (ml/30 min.) |  | - | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 4632
CT ( in/32) |  | - | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  | - | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 120591
ALK (FILT.) |  | - | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 10.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 350000
HTHP WL |  | - | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 35000
HTHP CT |  | - | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 52200
NaCl (mg/l) |  | 825 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 52200
CHLORIDES |  | 500 | 3 1/8" DCS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 385000
CALCIUM |  | - | 2 7/8" DPS |  | NMDC |  | HSI | [14 empty] | POB
OIL % |  | - | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 0 |  |  | MPCL | 5
LUBE % |  | - | BHA ROT. HRS |  |  |  | BIT NO. |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 27
SOLIDS % |  | - | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. |  | - | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 52
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 15
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD (M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 x 120 | 2 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | [11 empty] | TOTAL | 127
DAILY WELL COST (US$) |  | 48430 | SHAKER-2 | 1 x 120 | 2 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 22153453 | SHAKER-3 | 1 x 120 | 2 x 120 |  | 7" LINER |  |  | 4446.0 (TOL @ 3253) | [11 empty] | LAST CSG SIZE | 5"
% OF AFE SPENT |  | 122.7% | MUD CLEANER | 1 x 140 | 2 x 170 |  | 5" LINER |  |  | 4766.0 (TOL @ 4367) | [11 empty] | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P3) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 5" |  | 12" | 6725 PSI | 97% |  | 0.07 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6" |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | HANGU | 4571/4323.65
FIRE DRILL | 2018-11-14 | 2018-12-14 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 5" |  | 12" | 6725PSI | 97% |  | 0.07 | [7 empty] | DANDOT-TOBRA | 4587/4333.72
PIT DRILL | 2018-11-14 | 2018-11-29 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BHAGANWALA | 4608/4354.35
KICK DRILL | 2018-11-28 | 2018-12-28 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | JUTANA | 4627/4367.58
TRIP DRILL | 2018-11-28 | 2018-12-28 | LAST BOP TEST DATE |  | 2018-12-07 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK | 4657/4390.03
STRETCHER DRILL | 2018-11-08 | 2018-12-08 | NEXT BOP TEST DATE |  | 2018-12-21 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4724/4438.61
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-12-09
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43443 | 43443.2396 | 5.75 | EVAL | PT-P | POOH | CONT'D POOH OEDP FROM 3024M TO TOP OF BHA @ 423M.
43443.2396 | 43443.25 | 0.25 | EVAL | PT-P | RU | R/U WELLSERVE POWER TONG.
43443.25 | 43443.3958 | 3.5 | EVAL | PT-P | DP | POOH AND L/D SGL BY SGL 30 x 2 7/8" DP + 15 x 3 1/8" DC.
43443.3958 | 43443.4167 | 0.5 | TEST | PT-P | RD | R/D WELLSERVE POWER TONGS.
43443.4167 | 43443.4583 | 1 | TEST | PT-P | R/U | WELL HANDED OVER TO PRODUCTION DEPT. AT 10:00 HRS. RIG UP WELLSERVE TRS EQUIPMENT.
43443.4583 | 43443.6667 | 5 | TEST | PT-P | DST | P/U AND RIH 2 7/8" TUBING HMS + 1 x 2 7/8" PERFORATED JNT + 33 x 2 7/8" TBG JNTS + 1 x 2 7/8" PERF JNT. PICK UP AND RIH FLEX TRIP BHA. P/U & RIH 3 x 4 3/4" DC. M/U 01 x RUPTURE DISK CIRC VALVE. P/U & RIH 03 x 4 3/4" DC TO 408M.
43443.6667 | 43443.7083 | 1 | TEST | PT-P | P/T | FILLED UP STRING WITH 1.5 SG BRINE. CONNECTED SCHL CMT UNIT LINE AND P/T SAME @ 9000 PSI. P/T BHA AT 500/9000 PSI FOR 10 MIN EACH LOW/HIGH - OK
43443.7083 | 43443.7604 | 1.25 | TEST | PT-P | DST | CONT'D P/U AND RIH 12 x 4 3/4" DC. FILLED UP STRING WITH 1.5 SG BRINE.
43443.7604 | 43443.7917 | 0.75 | TEST | PT-P | P/T | CONNECTED SCHL CMT UNIT LINE AND P/T BHA AT 500/9000 PSI FOR 10 MIN EACH LOW/HIGH - OK
43443.7917 | 43443.875 | 2 | TEST | PT-P | DST | CONT'D P/U AND RIH REMAINING 12 x 4 3/4" DC TO 628M.
43443.875 | 43443.9167 | 1 | TEST | PT-P | P/T | FILLED UP STRING WITH 1.5 SG BRINE. CONNECTED SCHL CMT UNIT LINE AND P/T FLEX TRIP BHA @ 500/9000 PSI FOR 10 MIN EACH LOW/HIGH - OK
43443.9167 | 43444 | 2 | TEST | PT-P | DST | CONT'D P/UP 3 1/2'' TBG JNT FROM CATWALK AND RIH TO 810M. FILLED UP STRING WITH 1.50 SG BRINE EVERY 15 JOINTS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-12-10
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43444 | 43444.25 | 6 | TEST | PT-P | DST | CONT'D P/UP 3 1/2'' TBG JNT's AND RIH FROM 810M TO 1387M, MEANWHILE FILLED UP STRING WITH 1.50 SG BRINE EVERY 15 JOINTS. CONNECTED SCHL CMT UNIT LINE AND P/T SAME @ 9000 PSI. P/T FLEX STRING AT 500/9000 PSI FOR 10 MIN EACH LOW/HIGH - OK
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 07:00 HRS |  |  | FLEX TRIP IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH OEDP FROM 3024M TO SURFACE, MEANWHILE L/DOWN 2 7/8'' DP's & 3 1/8'' DC's, WELL HANDED OVER TO PRODUCTION DEPT. PREPARED RIG FLOOR, P/UP AND RIH FLEX ASSY TO 810M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | PERFORM FLEX TRIP AS PER PROGRAM, MEANWHILE PRESSURE TEST FLEX STRING.
REMARKS |  |  | SCHL TCP SERVICES + EQP ARRIVED ON 09-12-18.
Formulas:
DHARIAN-1-ST-3 = [POTASSIUM FORMATE BRINE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14