## DDR # 355
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 355
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-04-23
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4995 / 4945 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | S. KHALID AZIM / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4775 | 4758.16 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 354.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JEELANI |  |  | MD/TVD @ 06:00HRS: |  | 4775 | 4758.16 | [5 empty] | DAILY PROGRESS @ 00:00HRS:
2020-04-22 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | RUN NO. |  |  | 71 |  | BHA NO. |  |  | 90 | IN (M) |  | 4775 |  | OUT (M) |  |  | STRING (BBL) | 37
CHECK TIME |  | 20:00 | MD @ 00:00HR (M) |  | 4775 |  | BIT NO. |  |  | 30 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 900
DEPTH, MD (M) |  | 4775 | TVD @ 00:00HR (M) |  | 4758.16 |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 |  |  | PITS (BBL) | 383
MW IN (SG) |  | 1.65 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | MUD MOTOR |  |  | 5.875 | 3.75 |  | 3 1/2 IF |  | 7.11 |  |  | ACT. SYS (BBL) | 1320
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MDSi613 |  | ST. STAB |  |  | 5.875 | 3.75 |  | 3 1/2 IF |  | 1.57 |  |  | RESV. SYS (BBL) | 499
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | Q43638 |  | FLOAT SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.83 |  |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | L. SAVER SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.61 |  |  | KILL MW (SG)
µ FUNNEL (SEC) |  | 60 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3 X 12 |  | SPSA (MWD) |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 9.45 |  |  | TOTAL | 1819
PV |  | 30 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4775 |  | NMDC |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 4.51 |  |  | DIESEL (LTR)
YIELD POINT |  | 28 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | 15 X HWDP's |  |  | 3.5 | 2.1875 |  | 3 1/2 IF |  | 141.58 |  |  | RIG TANK | 127290
GEL ST. |  | 12/16 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | D. JAR |  |  | 4.875 | 2.25 |  | 3 1/2 IF |  | 9.02 |  |  | CAMP TANK | 22574
WL (ml/30 min) |  | 4.2 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | 3 X HWDP's |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 28.26 |  |  | CONSUMED | 5229
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED | 28000
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 149864
ALK (FILT.) |  | 0.2/1.2 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 537757
MAX SHIELD % |  | 3 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 80000
KCl (%) |  | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 64000
KCl (mg/l) |  | 48239.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 52500
CHLORIDES (mg/l) |  | 100000 | JAR | 0 | STAB - 1 | 0 | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | 92800
HARDNESS (mg/l) |  | 360 | 3 1/2" HWDPS | 27.32 | STAB - 2 |  | TFA (IN²) |  |  | 0.331 | [12 empty] | POB
PENETRAX % |  | 1.7 | 4 3/4" DCS |  | SPSA |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 203.14 |  |  | MPCL | 6
MAX GUARD % |  | 2 | DAILY BHA ROT. HRS |  | 0 |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 7 |  |  | MPCL SERV | 23
SOLIDS % |  | 20.45 | DAILY ON BOTTOM HRS |  | 0 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 6 |  |  | SECURITY
M.B.T. (lb/bbl) |  | 3.8 | DAILY CIRC. HRS |  | 0.57 |  | BIT NO. 29 |  |  | 2-3-FC-A-E-I-BT-LIH |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 27
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [11 empty] | TOTAL | 114
DAILY WELL COST (US$) |  | 34963 | SHAKER-2 | 3 x 140 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 24345307 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | [11 empty] | LAST CSG SIZE
% OF AFE SPENT |  | 122.3% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | [11 empty] | FIT (EMW)
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | [11 empty] | MAASP (PSI)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4772 | 1300 /1280 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4772 | 1800 /1780 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-03-20 | 2020-04-19 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4772 | 2380 /2300 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-04-20 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK
STRETCHER DRILL | 2020-03-20 | 2020-04-19 | NEXT BOP TEST DATE |  | 2020-05-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-22
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43943 | 43943.5104 | 12.25 | DRL | NPT-UP | POOH | CONT'D POOH FROM 3779M TO 95M (TOP OF BHA).
43943.5104 | 43943.5208 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43943.5208 | 43943.6042 | 2 | DRL | NPT-UP | BHA | CONT'D POOH OVERSHOT ASSEMBLY FROM 95M TO SURFACE. RECOVERED 100 % FISH ALHAMDULILLAH (TC BIT + MUD MOTOR + ST. STAB + F/SUB = 9.58M). L/DOWN SAME SGL BY SGL FROM CATWALK.
43943.6042 | 43943.6458 | 1 | DRL | NPT-UP | BHA | L/DOWN 9 x 3.5'' HWDP's & JAR USED IN FISHING BHA.
43943.6458 | 43943.7396 | 2.25 | DRL | PT-P | BHA | P/UP & M/UP 6'' NEW PDC (SMITH, MDSi613, SR # Q43638, 3 x 12/32'') + MUD MOTOR + 5 7/8'' ST. STAB + F.SUB + L.SAVER SUB + SPSA (INSTALLED MWD) + NMDC. ADJUSTED MOTOR BEND AT 0.78˚. SCRIBED MOTOR TF WITH MWD. RIH TO 24M.
43943.7396 | 43943.7812 | 1 | DRL | PT-P | E / C | SHALLOW FUNCTION TESTED SLB DIRECTIONAL TOOLS @ 230 GPM, SPP 1200 PSI, OK.
43943.7812 | 43943.8438 | 1.5 | DRL | PT-P | BHA | RIH AS PER BHA FROM 24M TO 203M. FLUSHED BHA.
43943.8438 | 43943.9688 | 3 | DRL | PT-P | RIH | CONT'D RIH FROM 203M TO 1435M. FILLED UP STRING EVERY 15 STANDS.
43943.9688 | 43944 | 0.75 | DRL | NPT-P | RS | CUT AND SLIPPED 38M D.LINE (IN PROGRESS)
TOTAL |  | 23.25
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-23
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43944 | 43944.0208 | 0.5 | DRL | NPT-P | RS | CONCLUDED CUT & SLIPPED D.LINE. ADJUSTED CROWN O MATIC & ACS.
43944.0208 | 43944.1771 | 3.75 | DRL | PT-P | RIH | RIH FROM 1435M TO 2933M. FILLED UP STRING EVERY 15 STDS.
43944.1771 | 43944.2083 | 0.75 | DRL | NPT-P | RR | CHANGED WASHPIPE, P/TESTED SAME AT 2600 PSI, HELD FOR 10 MINS, OK.
43944.2083 | 43944.25 | 1 | DRL | PT-P | RIH | CONT'D RIH FROM 2933M TO 3333M. FILLED UP STRING EVERY 15 STDS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | DANDOT/TOBRA : SANDSTONE, CLAYSTONE.
OPERATIONS AT 06:00 HRS |  |  | RIH WITH MOTOR BHA IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D POOH FROM 3779M TO SURFACE, RECOVERED 100 % FISH ALHAMDULILLAH, L/DOWN SAME, P/UP AND M/UP 6'' PDC BIT + SLB MOTOR BHA, ADJUSTED MOTOR BEND, SHALLOW TESTED DIRECTIONAL TOOL, RIH TO 1435M, CUT AND SLIP D.LINE IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONCLUDE CUT AND SLIP, CONTINUE RIH TO TOL @ 3397M, REPLACE WASHPIPE, RIH TO BTM AT 4775M, RESUME DRILLING AHEAD 6'' HOLE.
REMARKS
Formulas:
MIRAJ-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14