## DDR # 356
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [16 empty] | Report No. |  | 356
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [7 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-04-24
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [7 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4995 / 4945 METER | [7 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | S. KHALID AZIM / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4789 | 4769.78 | [6 empty] | DAYS SINCE SPUD: | [6 empty] | 355.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JEELANI |  |  | MD/TVD @ 06:00HRS: |  | 4800 | 4779.3 | [6 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 14
2020-04-23 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [11 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | RUN NO. |  |  | 71 |  | BHA NO. |  |  |  | 90 | IN (M) |  | 4775 |  | OUT (M) |  |  | STRING (BBL) | 223
CHECK TIME | 11:00 | 23:59 | MD @ 00:00HR (M) |  | 4775 |  | BIT NO. |  |  | 30 |  | COMPONENT DETAILS |  |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 644.8
DEPTH, MD (M) | 4775 | 4789 | TVD @ 00:00HR (M) |  | 4758.16 |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 |  |  | PITS (BBL) | 535
MW IN (SG) | 1.65 | 1.65 | DAILY PROGRESS (M) |  | 14 |  | MANUFACTURER |  |  | SMITH |  | MUD MOTOR |  |  |  | 5.875 | 3.75 |  | 3 1/2 IF |  | 7.11 |  |  | ACT. SYS (BBL) | 1402.8
MW OUT (SG) | 1.65 | 1.65 | INST. ROP (M/HR) |  | 2.02 |  | TYPE |  |  | MDSi613 |  | ST. STAB |  |  |  | 5.75 | 3.75 |  | 3 1/2 IF |  | 1.57 |  |  | RESV. SYS (BBL) | 505
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 1.46 |  | SERIAL NO. |  |  | QF3438 |  | FLOAT SUB |  |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.83 |  |  | KILL MUD (BBL)
FL TEMP. °F | 115 | 118 | AVG. WOB (TON) |  | 5 |  | IADC CODE |  |  |  |  | L. SAVER SUB |  |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.61 |  |  | KILL MW (SG)
µ FUNNEL (SEC) | 55 | 57 | AVG. RPM SURFACE |  | 20 |  | NOZZLES (1/32") |  |  | 3 X 12 |  | SPSA (MWD) |  |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 9.45 |  |  | TOTAL | 1907.8
PV | 30 | 30 | AVG. RPM DOWNHOLE |  | 131 |  | DEPTH IN (M) |  |  | 4775 |  | NMDC |  |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 4.51 |  |  | DIESEL (LTR)
YIELD POINT | 27 | 29 | FLOWRATE (GPM) |  | 226 |  | DEPTH OUT (M) |  |  |  |  | 15 X HWDP's |  |  |  | 3.5 | 2.1875 |  | 3 1/2 IF |  | 141.58 |  |  | RIG TANK | 124059
GEL ST. | 11/14 | 13/16 | PRESSURE (PSI) |  | 3000-3250 |  | METERAGE (M) |  |  | 14 |  | D. JAR |  |  |  | 4.875 | 2.25 |  | 3 1/2 IF |  | 9.02 |  |  | CAMP TANK | 22029
WL (ml/30 min) | 4 | 4 | TORQ. ON-BTM (KLB-FT) |  | 2-3 |  | RPM SURF. |  |  | 20 |  | 3 X HWDP's |  |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 28.26 |  |  | CONSUMED | 4396
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 1-2 |  | RPM BTM. |  |  | 131 + 20 | [13 empty] | RECEIVED
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  | 147 |  | WOB (TON) |  |  | 4-6 | [13 empty] | TOTAL | 146088
ALK (FILT.) | 0.2/1.2 | 0.2/1.2 | PICK-UP WT. (TON) |  | 150 |  | AVG. ROP (M/HR) |  |  | 1.4568 | [13 empty] | WATER (LTR)
pH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 145 |  | BIT ROT HRS. |  |  | 9.61 | [13 empty] | RIG STORAGE | 581989
MAX SHIELD % | 3 | 3 | SLIMPULSE D & I OFF BIT - (M) |  | 11.91 |  | K-REVS IN 24 HRS |  |  | 82.41 | [13 empty] | CAMP STORAGE | 82000
KCl (%) | 5 | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  | 82.41 | [13 empty] | CONSUMED | 48268
KCl (mg/l) | 47667.5 | 52434.2 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  | 65.2 | [13 empty] | RECEIVED | 94500
CHLORIDES (mg/l) | 100000 | 100800 | JAR | 6.16 | STAB - 1 | 6.16 | JET VELOCITY (M/SEC) |  |  | 66.77 | [13 empty] | DRL WASTE
HARDNESS (mg/l) | 360 | 360 | 3 1/2" HWDPS | 33.48 | STAB - 2 |  | TFA (IN²) |  |  | 0.331 | [13 empty] | POB
PENETRAX % | 1.9 | 1.9 | 4 3/4" DCS |  | SPSA |  | HSI |  |  | 2.75 |  | TOTAL LENGTH (M) | [8 empty] | 203.14 |  |  | MPCL | 6
MAX GUARD % | 2 | 2 | DAILY BHA ROT. HRS |  | 6.16 |  | MOTOR REV/GAL |  |  | 0.58 |  | BHA WT. IN MUD (TON) | [8 empty] | 7 |  |  | MPCL SERV | 22
SOLIDS % | 20.45 | 20.47 | DAILY ON BOTTOM HRS |  | 9.61 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [8 empty] | 6 |  |  | SECURITY
M.B.T. (lb/bbl) | 3.8 | 3.8 | DAILY CIRC. HRS |  | 14.65 |  | BIT NO. |  |  |  |  | MARGIN OF OVERPULL (TON) | [11 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [11 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4761.00 / 4745.84 | 4761.00 / 4745.84 | 4761.00 / 4745.84 | 26.4 | 26.4 | 290 | 290 | 290 | 20.7014 | 20.7014 |  |  | TOTAL | 112
DAILY WELL COST (US$) |  | 71221 | SHAKER-2 | 3 x 140 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4770.54 / 4754.19 | 4770.54 / 4754.19 | 4770.54 / 4754.19 | 31.29 | 31.29 | 295.64 | 295.64 | 295.64 | 17.5826 | 17.5826 |  |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 24416528 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4780.60 / 4762.72 | 4780.60 / 4762.72 | 4780.60 / 4762.72 | 32.56 | 32.56 | 303.56 | 303.56 | 303.56 | 3.126 | 3.126 |  |  | LAST CSG SIZE
% OF AFE SPENT |  | 122.7% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | [12 empty] | FIT (EMW)
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | [12 empty] | MAASP (PSI)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [10 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING |  | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 |  | 97% |  | 0.0855 |  | 30 |  | 4782 | 1200 /1250 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 |  | 97% |  | 0.0855 |  | 40 |  | 4782 | 1600 /1750 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-03-20 | 2020-04-19 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 |  | 97% |  | 0.0855 |  | 50 |  | 4782 | 2200 /2200 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [11 empty] | BAGHANWALA | 4775/4758.16
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS | [5 empty] | LOSSES IN SECTION | [5 empty] | JUTANA | 4787 / 4768
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-04-20 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS | [5 empty] | MUD LOSSES | [5 empty] | KUSSAK
STRETCHER DRILL | 2020-03-20 | 2020-04-19 | NEXT BOP TEST DATE |  | 2020-05-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS | [5 empty] | CMT LOSSES | [5 empty] | KHEWRA
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-23
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43944 | 43944.0208 | 0.5 | DRL | NPT-P | RS | CONCLUDED CUT & SLIPPED D.LINE. ADJUSTED CROWN O MATIC & ACS.
43944.0208 | 43944.1771 | 3.75 | DRL | PT-P | RIH | RIH FROM 1435M TO 2933M. FILLED UP STRING EVERY 15 STDS.
43944.1771 | 43944.2083 | 0.75 | DRL | NPT-P | RR | CHANGED WASHPIPE, P/TESTED SAME AT 2600 PSI, HELD FOR 10 MINS, OK.
43944.2083 | 43944.3958 | 4.5 | DRL | PT-P | RIH | CONT'D RIH FROM 2933M TO 4737M. FILLED UP STRING EVERY 15 STDS.
43944.3958 | 43944.4896 | 2.25 | DRL | PT-P | RW | PRECAUTIONARY WASHED DOWN FROM 4737M TO 4775M (PASSED THROUGH WINDOW WITHOUT PUMPS). MEANWHILE RECORDED CHECKSHOT AT DIFFERENT STATIONS (4752, 4756.5, 4759 & 4761M)
43944.4896 | 43944.5625 | 1.75 | DRL | PT-P | DM | COMMENCED DRILLING AFTER SETTING TF/ BROKE IN THE BIT. DRILLED 6'' HOLE FROM 4775M TO 4776M IN SLIDE MODE. (OBSERVED FREQUENT TF DISTURBANCE, SPP FLUCTUATION)
43944.5625 | 43944.6667 | 2.5 | DRL | PT-P | DM | SWITCHED OVER TO ROTARY MODE. DRILLED 6'' HOLE FROM 4776M TO 4779M.
43944.6667 | 43944.8438 | 4.25 | DRL | PT-P | DM | SWITCHED OVER TO SLIDE MODE. DRILLED 6'' HOLE FROM 4779M TO 4783M. (OBSERVED WT. HANGING ISSUES, SPP FLUCTUATIONS)
43944.8438 | 43945 | 3.75 | DRL | PT-P | DM | SWITCHED OVER TO ROTARY MODE, DRILLED 6'' HOLE FROM 4783M TO 4789M. MEANWHILE PUMPED AND DISPLACED 15 BBL BRIDGE PILL. RECORDED CHECKSHOT AT 4770 & 4776M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-24
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43945 | 43945.25 | 6 | DRL | PT-P | DM | CONT'D DRILLING 6'' HOLE IN ROTARY MODE FROM 4789M TO 4800M. WASHED/REAMED DRILLED INTERVAL & RECORDED MWD SURVEY AT CONNECTION.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | BHAGANWALA : SANDSTONE, CLAYSTONE.
OPERATIONS AT 06:00 HRS |  |  | DRILLING 6'' DIRECTIONAL HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONCLUDED CUT AND SLIP, CONT'D RIH TO 2933M, REPLACED WASHPIPE, P/TESTED SAME, RIH TO BTM AT 4775M MEANWHILE RECORDED CHECKSHOTS, RESUME DRILLING AHEAD 6'' HOLE IN SLIDE/ROTARY MODE FROM 4775M TO 4789.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 6'' HOLE IN ROTARY /SLIDE MODE.
REMARKS
Formulas:
MIRAJ-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14