## DDR # 358
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 358
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-04-26
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4995 / 4945 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | S. KHALID AZIM / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4818 | 4793.39 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 357.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JEELANI |  |  | MD/TVD @ 06:00HRS: |  | 4836 | 4808 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 2
2020-04-25 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | RUN NO. |  |  | 72 |  | BHA NO. |  |  | 91 | IN (M) |  | 4816 |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME |  | 20:00 | MD @ 00:00HR (M) |  | 4818 |  | BIT NO. |  |  | 30RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 854.3
DEPTH, MD (M) |  | 4816 | TVD @ 00:00HR (M) |  | 4793.39 |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 |  |  | PITS (BBL) | 575
MW IN (SG) |  | 1.65 | DAILY PROGRESS (M) |  | 2 |  | MANUFACTURER |  |  | SMITH |  | SLB PD |  |  | 5.375 | 3.625 |  | 3 1/2 REG |  | 4.43 |  |  | ACT. SYS (BBL) | 1429.3
MW OUT (SG) |  |  | INST. ROP (M/HR) |  | 2.5 |  | TYPE |  |  | MDSi613 |  | X/O |  |  | 4.625 | 1.5 |  | 3 1/2 REG |  | 0.62 |  |  | RESV. SYS (BBL) | 459
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | QF3438 |  | MUD MOTOR |  |  | 4.75 | 3.75 |  | 3 1/2 IF |  | 7.12 |  |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  | 4 |  | IADC CODE |  |  |  |  | ST. STAB |  |  | 5.75 | 3.75 |  | 3 1/2 IF |  | 1.57 |  |  | KILL MW (SG)
µ FUNNEL (SEC) |  | 57 | AVG. RPM SURFACE |  | 20 |  | NOZZLES (1/32") |  |  | 3 X 12 |  | FLOAT SUB |  |  | 4.75 | 2.5 |  | 3 1/2 IF |  | 0.78 |  |  | TOTAL | 1888.3
PV |  | 31 | AVG. RPM DOWNHOLE |  | 151 |  | DEPTH IN (M) |  |  | 4816 |  | L. SAVER SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.45 |  |  | DIESEL (LTR)
YIELD POINT |  | 28 | FLOWRATE (GPM) |  | 226 |  | DEPTH OUT (M) |  |  |  |  | SPSA (MWD) |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 9.45 |  |  | RIG TANK | 111837
GEL ST. |  | 11/15 | PRESSURE (PSI) |  | 3800-3900 |  | METERAGE (M) |  |  | 2 |  | PBL SUB |  |  | 4.75 | 2.75 |  | 3 1/2 IF |  | 3.09 |  |  | CAMP TANK | 21077
WL (ml/30 min) |  | 4 | TORQ. ON-BTM (KLB-FT) |  | 2.5 |  | RPM SURF. |  |  | 20 |  | 18 X HWDP's |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.92 |  |  | CONSUMED | 4857
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  | 1-2 |  | RPM BTM. |  |  | 131+20 |  | D. JAR |  |  | 4.875 | 2.25 |  | 3 1/2 IF |  | 9.02 |  |  | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  | 146 |  | WOB (TON) |  |  | 3-4 |  | 9 X HWDP's |  |  | 3.5 | 2.1875 |  | 3 1/2 IF |  | 84.89 |  |  | TOTAL | 132914
ALK (FILT.) |  | 0.2/1.2 | PICK-UP WT. (TON) |  | 148 |  | AVG. ROP (M/HR) |  |  | 4 | [12 empty] | WATER (LTR)
pH |  | 9.5 | SLACK-OFF WT. (TON) |  | 142 |  | BIT ROT HRS. |  |  | 0.5 | [12 empty] | RIG STORAGE | 594614
MAX SHIELD % |  | 3 | SLIMPULSE D & I OFF BIT - (M) |  | 19.93 |  | K-REVS IN 24 HRS |  |  | 4.5 | [12 empty] | CAMP STORAGE | 75000
KCl (%) |  | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  | 104 | [12 empty] | CONSUMED | 42625
KCl (mg/l) |  | 50909 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  | 65.3 | [12 empty] | RECEIVED | 39800
CHLORIDES (mg/l) |  | 101000 | JAR | 22.16 | STAB - 1 | 22.16 | JET VELOCITY (M/SEC) |  |  | 66.78 | [12 empty] | DRL WASTE
HARDNESS (mg/l) |  | 360 | 18 X 3 1/2" HWDPS | 49.48 | MOTOR & PD | 2.16 | TFA (IN²) |  |  | 0.33 | [12 empty] | POB
PENETRAX % |  | 1.8 | 9 x 3 1/2" HWDP | 2.16 | SPSA | 2.16 | HSI |  |  | 2.76 |  | TOTAL LENGTH (M) | [7 empty] | 291.54 |  |  | MPCL | 5
MAX GUARD % |  | 2 | DAILY BHA ROT. HRS |  | 2.16 |  | MOTOR REV/GAL |  |  | 0.58 |  | BHA WT. IN MUD (TON) | [7 empty] | 8 |  |  | MPCL SERV | 25
SOLIDS % |  | 20.86 | DAILY ON BOTTOM HRS |  | 0.5 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 6 |  |  | SECURITY
M.B.T. (lb/bbl) |  | 3.8 | DAILY CIRC. HRS |  | 3.33 |  | BIT NO. |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 4
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4770.54 /4754.19 |  | 31.29 |  | 295.64 |  |  | 17.58 |  | MWD |  | TOTAL | 113
DAILY WELL COST (US$) |  | 35111 | SHAKER-2 | 3 x 140 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4802 / 4780.44 |  | 35.67 |  | 304.26 |  |  | 4.36 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 24496260 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | [11 empty] | LAST CSG SIZE | 7''
% OF AFE SPENT |  | 123.1% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | [11 empty] | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | [11 empty] | MAASP (PSI) | 2360
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4815 | 1240 /1340 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4815 | 1860 /1940 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4815 | 2200 /2200 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4775/4758.16
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4787 / 4768
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-04-20 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK | 4821 / 4796
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-05-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-25
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43946 | 43946.125 | 3 | DRL | PT-P | DM | CONT'D POOH FROM 1376M TO 203M.
43946.125 | 43946.1354 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC
43946.1354 | 43946.1771 | 1 | DRL | PT-P | BHA | POOH BHA FROM 203M TO SURFACE. L/DOWN D. JAR + NMDC + ST. STAB + MOTOR + PDC BIT.
43946.1771 | 43946.1875 | 0.25 | DRL | PT-P | SM | HELD PJSM, DISCUSSED SAFETY PRECAUTIONS WITH CREW FOR VORTEX BHA.
43946.1875 | 43946.2083 | 0.5 | DRL | PT-P | BHA | P/UP & M/UP 6'' RR PDC BIT (SMITH, MDSi613, SR # QF3438, 3 x 12/32'') + SLB PD ORBIT + 1 SGL.
43946.2083 | 43946.2292 | 0.5 | DRL | PT-P | E/C | RIH TO 9M, FUNCTION TESTED / DOWNLINKED PD. OK.
43946.2292 | 43946.25 | 0.5 | DRL | PT-P | BHA | P/UP & M/UP MUD MOTOR + STAB + SPSA (INSTALLED MWD INSIDE).
43946.25 | 43946.2812 | 0.75 | DRL | PT-P | E / C | SHALLOW FUNCTION TESTED MUD MOTOR AND MWD @ 200 GPM, SPP = 1450 PSI.
43946.2812 | 43946.3333 | 1.25 | DRL | PT-P | E / C | P/UP & M/UP 4 3/4'' PBL SUB. RIH ON 1 X 3 1/2'' DP TO 32M. FUNCTION TESTED SAME. OK. P/BACK & B/OUT PBL CATCHER TO RETRIEVE ACTIVATION DART & DEACTIVATION BALLS.
43946.3333 | 43946.4375 | 2.5 | DRL | PT-P | BHA | RIH AS PER BHA TO 291M, MEANWHILE ADDED D.JAR AND 9 X 3 1/2'' HWDP's FROM CATWALK. FLUSHED BHA.
43946.4375 | 43946.7604 | 7.75 | DRL | PT-P | RIH | CONT'D RIH FROM 291M TO 3397M. FILLED UP STRING EVERY 15 STDS.
43946.7604 | 43946.7708 | 0.25 | DRL | PT-P | CIR | BROKE CIRCULATION & WASHED ACROSS 7'' TOL.
43946.7708 | 43946.9375 | 4 | DRL | PT-P | RIH | CONT'D RIH FROM 3397M TO 4768M. FILLED UP STRING EVERY 15 STDS.
43946.9375 | 43946.9479 | 0.25 | DRL | PT-P | RW | PRECAUTIONARY WASHED DOWN FROM 4768M TO BTM AT 4816M.
43946.9479 | 43946.9792 | 0.75 | DRL | PT-P | CIR | RECORDED CHECKSHOT, DOWNLINKED SLB PD & RECORDED SCR PRIOR DRILLING AHEAD.
43946.9792 | 43947 | 0.5 | DRL | PT-P | DM | DRILLED 6'' HOLE FROM 4816M TO 4818M
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-26
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43947 | 43947.25 | 6 | DRL | PT-P | DM | CONT'D DRILLING 6'' HOLE FROM 4818M TO 4836M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KUSSAK : SANDSTONE, CLAYSTONE & SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | DRILLING 6'' DIRECTIONAL HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE, L/DOWN SLB MOTOR BHA, P/UP AND M/UP SLB VORTEX BHA, PERFORMED NECESSARY SURFACE CHECKS, OK. RIH TO 4768M MEANWHILE FILLED UP STRING, PRECAUTIONARY WASHED DOWN TO BTM AT 4816M, DOWNLINKED PD AND DRILLED AHEAD 6'' HOLE FROM 4816M TO 4818M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 6'' HOLE TILL WELL TD.
REMARKS
Formulas:
MIRAJ-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14