## DDR # 359
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 359
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-04-27
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4995 / 4945 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | S. KHALID AZIM / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4866 | 4831.57 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 358.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JEELANI |  |  | MD/TVD @ 06:00HRS: |  | 4866 | 4831.57 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 48
2020-04-26 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | RUN NO. |  |  | 72 |  | BHA NO. |  |  | 91 | IN (M) |  | 4816 |  | OUT (M) |  |  | STRING (BBL) | 215
CHECK TIME | 8:00 | 19:00 | MD @ 00:00HR (M) |  | 4866 |  | BIT NO. |  |  | 30RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 650.1
DEPTH, MD (M) | 4842 | 4866 | TVD @ 00:00HR (M) |  | 4831.57 |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 |  |  | PITS (BBL) | 505
MW IN (SG) | 1.65 | 1.65 | DAILY PROGRESS (M) |  | 48 |  | MANUFACTURER |  |  | SMITH |  | SLB PD |  |  | 5.375 | 3.625 |  | 3 1/2 REG |  | 4.43 |  |  | ACT. SYS (BBL) | 1370.1
MW OUT (SG) | 1.65 | 1.65 | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MDSi613 |  | X/O |  |  | 4.625 | 1.5 |  | 3 1/2 REG |  | 0.62 |  |  | RESV. SYS (BBL) | 346
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 2.86 |  | SERIAL NO. |  |  | QF3438 |  | MUD MOTOR |  |  | 4.75 | 3.75 |  | 3 1/2 IF |  | 7.12 |  |  | KILL MUD (BBL)
FL TEMP. °F | 125 | 125 | AVG. WOB (TON) |  | 5 |  | IADC CODE |  |  |  |  | ST. STAB |  |  | 5.75 | 3.75 |  | 3 1/2 IF |  | 1.57 |  |  | KILL MW (SG)
µ FUNNEL (SEC) | 56 | 54 | AVG. RPM SURFACE |  | 26 |  | NOZZLES (1/32") |  |  | 3 X 12 |  | FLOAT SUB |  |  | 4.75 | 2.5 |  | 3 1/2 IF |  | 0.78 |  |  | TOTAL | 1716.1
PV | 30 | 29 | AVG. RPM DOWNHOLE |  | 26 + 135 |  | DEPTH IN (M) |  |  | 4816 |  | L. SAVER SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.45 |  |  | DIESEL (LTR)
YIELD POINT | 27 | 24 | FLOWRATE (GPM) |  | 233 |  | DEPTH OUT (M) |  |  |  |  | SPSA (MWD) |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 9.45 |  |  | RIG TANK | 106177
GEL ST. | 12/15 | 09/13 | PRESSURE (PSI) |  | 3800-4000 |  | METERAGE (M) |  |  | 50 |  | PBL SUB |  |  | 4.75 | 2.75 |  | 3 1/2 IF |  | 3.09 |  |  | CAMP TANK | 20525
WL (ml/30 min) | 4.2 | 4.8 | TORQ. ON-BTM (KLB-FT) |  | 2.5 |  | RPM SURF. |  |  | 20 |  | 18 X HWDP's |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.92 |  |  | CONSUMED | 6212
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 1-2 |  | RPM BTM. |  |  | 131+20 |  | D. JAR |  |  | 4.875 | 2.25 |  | 3 1/2 IF |  | 9.02 |  |  | RECEIVED
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  | 146 |  | WOB (TON) |  |  | 2-6 |  | 9 X HWDP's |  |  | 3.5 | 2.1875 |  | 3 1/2 IF |  | 84.89 |  |  | TOTAL | 126702
ALK (FILT.) | 0.2/1.1 | 0.2/1.1 | PICK-UP WT. (TON) |  | 148 |  | AVG. ROP (M/HR) |  |  | 2.7996 | [12 empty] | WATER (LTR)
pH | 9 | 9 | SLACK-OFF WT. (TON) |  | 142 |  | BIT ROT HRS. |  |  | 17.86 | [12 empty] | RIG STORAGE | 658074
MAX SHIELD % | 3 | 2.4 | SLIMPULSE D & I OFF BIT - (M) |  | 19.93 |  | K-REVS IN 24 HRS |  |  | 163.55 | [12 empty] | CAMP STORAGE | 75000
KCl (%) | 5 | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  | 267.55 | [12 empty] | CONSUMED | 42040
KCl (mg/l) | 49955 | 45760.8 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  | 65.6 | [12 empty] | RECEIVED | 74000
CHLORIDES (mg/l) | 100000 | 98000 | JAR | 40.7 | STAB - 1 | 40.7 | JET VELOCITY (M/SEC) |  |  | 67.19 | [12 empty] | DRL WASTE
HARDNESS (mg/l) | 320 | 320 | 18 X 3 1/2" HWDPS | 49.48 | MOTOR & PD | 20.7 | TFA (IN²) |  |  | 0.33 | [12 empty] | POB
PENETRAX % | 1.8 | 1.2 | 9 x 3 1/2" HWDP | 20.7 | SPSA | 20.7 | HSI |  |  | 2.8 |  | TOTAL LENGTH (M) | [7 empty] | 291.54 |  |  | MPCL | 5
MAX GUARD % | 2 | 1.5 | DAILY BHA ROT. HRS |  | 18.54 |  | MOTOR REV/GAL |  |  | 0.58 |  | BHA WT. IN MUD (TON) | [7 empty] | 8 |  |  | MPCL SERV | 25
SOLIDS % | 20.81 | 20.18 | DAILY ON BOTTOM HRS |  | 17.86 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 6 |  |  | SECURITY
M.B.T. (lb/bbl) | 3.8 | 3.8 | DAILY CIRC. HRS |  | 17.9 |  | BIT NO. |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 4
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4770.54 /4754.19 |  | 31.29 |  | 295.64 |  |  | 17.58 |  | MWD |  | TOTAL | 112
DAILY WELL COST (US$) |  | 56005 | SHAKER-2 | 3 x 140 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4802 / 4780.44 |  | 35.67 |  | 304.26 |  |  | 4.36 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 24552265 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4829 / 4802.39 |  | 38.08 |  | 302.21 |  |  | 2.69 |  | MWD |  | LAST CSG SIZE | 7''
% OF AFE SPENT |  | 123.3% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | [11 empty] | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | [11 empty] | MAASP (PSI) | 2360
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4815 | 1240 /1340 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4815 | 1860 /1940 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4815 | 2200 /2200 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4775/4758.16
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4787 / 4768
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-04-20 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  | 365 BBL |  | MUD LOSSES | [5 empty] | KUSSAK | 4821 / 4796
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-05-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4857 / 4825
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-26
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43947 | 43947.8438 | 20.25 | DRL | PT-P | DM | CONT'D DRILLING 6'' HOLE FROM 4818M TO 4866M. (WASHED/REAMED DRILLED INTERVAL & RECORDED MWD SURVEY AT CONNECTION). WHILE DRILLING AT 4866.89M, OBSERVED MUD FLOW OUT % DROPPED INSTANTLY FOLLOWED BY RETURN SEIZE (COMPLETE LOSS). P/UP STRING TO 4853M.
43947.8438 | 43947.8646 | 0.5 | DRL | NPT-UP | FC | FLOW CHECKED - OBSERVED LEVEL DROPPING. MONITORED WELL ON TRIP TANK, OBSERVED STATIC LOSSES @ 150 BBL/HR. PREPARED LCM PILL MEANWHILE FILLED HOLE THROUGH TRIP TANK.
43947.8646 | 43947.9062 | 1 | DRL | NPT-UP | SP | PUMPED AND DISPLACED 50 BBL ND LCM PILL (40 PPB). OBSERVED PARTIAL RETURNS DURING DISPLACEMENT.
43947.9062 | 43947.9271 | 0.5 | DRL | NPT-UP | POOH | POOH FROM 4853M TO 4742M (INSIDE LINER).
43947.9271 | 43947.9688 | 1 | DRL | NPT-UP | OTH /FC | ALLOWED SOAKING TIME MEANWHILE MONITORED WELL ON TRIP TANK, OBSERVED STATIC LOSSES @ 65 BBL/HR.
43947.9688 | 43948 | 0.75 | DRL | NPT-UP | OTH | DECIDED TO ACTIVATE PBL SUB AND SPOT HIGH CONC. LCM. B/OUT STRING, DROPPED ACTIVATION DART & WAITED TO SEAT. CIRCULATED @ 30 SPM TO CHASE DART. OBSERVED DART SEATED/PBL ACTIVATION FOLLOWED BY DECREASE IN SPP = 300 PSI. (MEANWHILE PREPARED HIGH CONC. ND LCM PILL)
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-27
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43948 | 43948.0938 | 2.25 | DRL | NPT-UP | SP | SPOTTED 60 BBL ND LCM PILL (100 PPB) THROUGH PBL. OBSERVED PARTIAL RETURNS DURING DISPLACEMENT.
43948.0938 | 43948.1458 | 1.25 | DRL | NPT-UP | POOH | POOH FROM 4742M TO 4243M.
43948.1458 | 43948.1771 | 0.75 | DRL | NPT-UP | OTH / FC | ALLOWED SOAKING TIME, MEANWHILE MONITORED WELL ON TRIP TANK, OBSERVED STATIC LOSS @ 65 BBL/HR.
43948.1771 | 43948.2396 | 1.5 | DRL | NPT-UP | RIH | RIH FROM 4243M TO 4739M MEANWHILE FILLED HOLE WITH WATER THROUGH KILL LINE.
43948.2396 | 43948.25 | 0.25 | DRL | NPT-UP | OTH | PREPARING HIGH CONC. ND PILL MEANWHILE FILLING HOLE WITH WATER IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA : SANDSTONE, CLAYSTONE.
OPERATIONS AT 06:00 HRS |  |  | PREPARING LCM PILL MEANWHILE FILLING HOLE WITH WATER.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 6'' HOLE FROM 4818M TO 4866M, OBSERVED LOSSES WHILE DRILLING, ATTEMPT TO CURE LOSSES IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CURE LOSSES, MONITOR WELL, DRILL AHEAD 6'' HOLE TILL TD.
REMARKS |  |  | DECREASING MUD WT. FROM 1.65SG TO 1.63SG AT SURFACE.
Formulas:
MIRAJ-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14