## DDR#36
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 36
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-01-26
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | SAIFULLAH TURK / HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 2307 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 35.5833
RIG REP.: |  | SARDAR NAEEM / IMRAN JAWAD |  |  | MD/TVD @ 06:00HRS: |  | 2316 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 28
2018-01-25 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 17.5 |  | BIT No. |  | 3RR2 | 3RR1 | BHA No. |  |  | 6 | IN (M) |  | 2201 |  | OUT (M) |  |  | STRING (BBL) | 127
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 2307 |  | SIZE (IN) |  | 17.5 | 17.5 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 2157
DEPTH, MD (M) | 2295 | 2307 | TVD @ 00:00HR (M) |  | 2307 |  | MANUFACTURER |  | NOV | NOV | 17 1/2" PDC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.36 | 0.35 |  | PITS (BBL) | 879
MW IN (SG) | 1.52 | 1.52 | DAILY PROGRESS (M) |  | 28 |  | TYPE |  | TFH519 | TFH519 | MUD MOTOR |  |  | 9.75 | 7.85 |  | 7 5/8 REG |  | 9.87 | 2.9 |  | ACT. SYS (BBL) | 3163
MW OUT (SG) | 1.52 | 1.52 | INST. ROP (M/HR) |  | 3.1 |  | SERIAL NO. |  | E244694 | E244694 | FLOAT SUB |  |  | 9.5 | 2.5 |  | 7 5/8 REG |  | 0.47 | 0.2 |  | RESV. SYS (BBL) | 500
ECD (SG) | 1.53 | 1.53 | AVG. ROP (M/HR) |  | 1.61 |  | IADC CODE |  | S422 | S422 | STRING STAB |  |  | 17.375 | 2.9375 |  | 7 5/8 REG |  | 2.44 | 0.8 |  | KILL MUD (BBL) | 400
FL TEMP. °F | 143.6 | 143.6 | AVG. WOB (TON) |  | 7.5 |  | NOZZLES |  | 5 X 18/32" | 5X18/32" | LOWER SAVER SUB |  |  | 9.5 | 3.5 |  | 7 5/8 REG |  | 0.62 | 0.2 |  | KILL MW (SG) | 1.8
µ FUNNEL (SEC) | 59 | 63 | AVG. RPM SURFACE |  | 45 |  | DEPTH IN (M) |  | 2201 | 1654 | SLIM PULSE |  |  | 9.375 | 5 |  | 7 5/8 REG |  | 9.43 | 2.7 |  | TOTAL | 4063
PV | 33 | 35 | AVG. RPM DOWNHOLE |  | 135 |  | DEPTH OUT (M) |  | - |  | UPPER SAVER SUB |  |  | 9.375 | 3 |  | 7 5/8 REG |  | 0.47 | 0.1 |  | DIESEL (LTR)
YIELD POINT | 31 | 30 | FLOWRATE (GPM) |  | 800 |  | METERAGE (M) |  | 106 |  | NMDC |  |  | 8.875 | 3.5 |  | 7 5/8 REG |  | 9.4 | 2.4 |  | RIG TANK | 123500
GEL ST. | 9/32 | 10/34 | PRESSURE (PSI) |  | 3000-3200 |  | RPM SURF. |  | 30-45 |  | 3 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 27.68 | 8.9417 |  | CAMP TANK | 11000
WL (ml/30 min.) | 4.8 | 4.8 | TORQ. ON-BTM (KLB-FT) |  | 5-8 |  | RPM BTM. |  | 70-90 |  | X/O |  |  | 9.375 | 3 |  | 7 5/8 REG |  | 0.94 | 0.30366 |  | CONSUMED | 12500
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 2-3 |  | WOB (TON) |  | 2-10 |  | 2 X 8" DC'S |  |  | 8 | 2.75 |  | 7 5/8 REG |  | 18.5 | 5.9762 |  | RECEIVED | 50000
ALK (MUD) | 0.8 | 0.8 | STRING WT. (TON) - ROT |  | 120 |  | AVG. ROP (M/HR) |  | 1.439 |  | D.JAR |  |  | 8 | 3.25 |  | 6 5/8 REG |  | 5.15 | 1.15 |  | TOTAL | 134500
ALK (FILT.) | 0.6 | 0.6 | PICK-UP WT. (TON) |  | 122 |  | BIT ROT HRS. |  | 73.66 |  | 2 X 8" DC'S |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.63 | 4.1601 |  | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 121 |  | K-REVS IN 24 HRS |  | 125 |  | X/O |  |  | 8.25 | 3 |  | 6 5/8 REG |  | 0.9 | 0.20097 |  | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 512 |  | 6 X 5" HWDPS |  |  | 5 | 3 |  | 6 5/8 REG |  | 56.25 | 12.5605 |  | CAMP STORAGE | 35000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 22.21 | [12 empty] | CONSUMED | 140000
KCl (mg/l) | 53387.8 | 53387.6 | JAR | 60.54 | NMDC | 60.54 | JET VELOCITY (M/SEC) |  | 61.9 | [12 empty] | RECEIVED | 136740
CHLORIDES | 25000 | 25000 | 5" HWDPS | 60.54 | STAB - 1 | 60.54 | TFA (IN²) |  | 1.24 | [12 empty] | TOTAL | 435000
CALCIUM | 140 | 160 | 8" DCS | 60.54 | STAB - 2 |  | HSI |  | 0.9 | [12 empty] | POB
OIL% | 2 | 2 | 9 1/2" DCS | 60.54 | SPSA | 60.54 | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 161.11 |  |  | MPCL | 3
DIESEL % | 2 | 2 | BHA ROT. HRS |  | 60.54 |  | BIT No. 3RR2 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 27 |  |  | MPCL SERV | 19
SOLIDS % | 16.82 | 16.82 | ON BOTTOM HRS |  | 73.68 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 19 |  |  | SECURITY | 5
M.B.T. | 10 | 10 | CIRC. HRS |  | 89.45 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 20" SURFACE CASING |  |  | 594 | 2191 |  | 1.85 |  | 104.11 |  |  | 0.17 |  | MWD |  | TOTAL | 111
DAILY WELL COST (US$) |  | 47554 | SHAKER-2 | 2 X 120 | 1 X 120 |  | 13 3/8" INTERMEDIATE CSG |  |  |  | 2220 |  | 2.32 |  | 107.69 |  |  | 0.74 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 3550770 | SHAKER-3 | 1 X 100 | 2 X 80 |  | 9 5/8" PRODUCTION CSG |  |  |  | 2248 |  | 2.52 |  | 109.3 |  |  | 0.23 |  | MWD |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 19.67% | MUD CLEANER | 3 X 170 |  |  | 7" LINER |  |  |  | 2277 |  | 2.47 |  | 105.15 |  |  | 0.8 |  | MWD |  | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | 0 | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 236
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-01-09 | 2018-01-23 | ANNULAR | RONGSHENG | 20.75 | 3000 | P-1 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | RONGSHENG | 20.75 | 3000 | P-2 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 2248 |  | 290 / 380 |  | CHINJI | 342
FIRE DRILL | 2018-01-03 | 2018-01-17 | BLIND RAMS | RONGSHENG | 20.75 | 3000 | P-3 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 2248 |  | 300 / 380 |  | KAMLIAL | 1255
PIT DRILL | 2018-01-16 | 2018-01-30 | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-01-09 | 2018-01-23 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-01-21 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 10 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-01-03 | 2018-01-17 | NEXT BOP TEST DATE |  | 2018-02-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-01-25
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43125 | 43125.1875 | 4.5 | DRL | PT-P | DM | CONT'D DRILLING 17.5'' HOLE FROM 2279 M TO 2289 M IN ROTARY MODE. RECORDED CHECKSHOT SURVEY AT DEPTH 2268 M.
43125.1875 | 43125.375 | 4.5 | DRL | PT-P | DM | SWITCHED OVER TO SLIDE MODE. DRILLED 17.5'' HOLE FROM 2289 M TO 2290.70 M. UNABLE TO SLIDE DUE TO STRING HANGING / TOOL FACE CHANGING.
43125.375 | 43125.6354 | 6.25 | DRL | PT-P | DM | SWITCHED OVER TO ROTARY DRILLING. DRILLED IN ROTARY MODE FROM 2290.7 M TO 2301 M. STOPPED DRILLING FOR SHORT TRIP. REAMED, CIRCULATED & RECORDED MWD SURVEY AT CONNECTION.
43125.6354 | 43125.7292 | 2.25 | DRL | PT-P | CIR | CIRCULATED FOR BOTTOM UP PRIOR TO SHORT TRIP.
43125.7292 | 43125.7396 | 0.25 | DRL | PT-P | FC | FLOW CHECKED. WELL STATIC.
43125.7396 | 43125.8021 | 1.5 | DRL | PT-P | WT | POOH UP TO 2012 M. HOLE CONDITION, GOOD.
43125.8021 | 43125.8438 | 1 | DRL | PT-P | WT | RIH DOWN TO 2268 M & PRECAUTIONARY WASHED DOWN TO 2301 M.
43125.8438 | 43126 | 3.75 | DRL | PT-P | DM | RESUMED DRILLING IN ROTARY MODE. DRILLED 17.5" HOLE FROM 2301 M TO 2307 M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-01-26
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43126 | 43126.25 | 6 | DRL | PT-P | DM | CONT'D DRILLING 17.5'' HOLE FROM 2307 M TO 2316 M. RECORDED CHECKSHOT SURVEY AT DEPTH 2287 M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE (CLAYSTONE, SANDSTONE)
OPERATIONS AT 06:00 HRS |  |  | DRILLING 17.5'' HOLE IN ROTARY MODE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 17.5'' HOLE FROM 2279 M TO 2301 M IN ROTARY / SLIDE MODE. CIRCULATED BTM UP. FLOW CHECKED, OK. POOH TO 2012 M. RIH TO BTM AT 2301 M. RESUMED DRILLING 17.5'' HOLE FROM 2301 M TO 2307 M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 17.5'' HOLE IN ROTARY/SLIDE MODE.
REMARKS
Formulas:
DHARIAN - 1 = [DATE]+14
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14