## DDR#36
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 36
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-06-09
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | IKRAMULLAH / AHSEN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 2305 / 2305 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 35.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 2305 / 2305 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 83
2019-06-08 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 17.5 |  | BIT NO. |  | 4RR1 |  | BHA NO. |  |  | 7 | IN (M) |  | 2101 |  | OUT (M) |  |  | STRING (BBL) | 151
CHECK TIME | 14:00 | 23:59 | MD @ 00:00HR (M) |  | 2305 |  | SIZE (IN) |  | 17.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 2098
DEPTH, MD (M) | 2272 | 2305 | TVD @ 00:00HR (M) |  | 2305 |  | MANUFACTURER |  | NOV |  | PDC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.36 | 0.11629 |  | PITS (BBL) | 829
MW IN (SG) | 2.06 | 2.06 | DAILY PROGRESS (M) |  | 83 |  | TYPE |  | TFH519S |  | BIT SUB (F.V) |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 1.07 | 0.34565 |  | ACT. SYS (BBL) | 3078
MW OUT (SG) | 2.06 | 2.06 | INST. ROP (M/HR) |  | 3.1 |  | SERIAL NO. |  | E260745 |  | STRING STAB |  |  | 17.375 | 3.0625 |  | 7 5/8 REG |  | 2.43 | 0.78498 |  | RESV. SYS (BBL) | 1670
ECD (SG) | 2.07 | 2.07 | AVG. ROP (M/HR) |  | 3.72 |  | IADC CODE |  | S422 |  | 1 X 9 1/2" DC |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 9.23 | 2.9816 |  | KILL MUD (BBL)
FL TEMP. °F | 160 | 160 | AVG. WOB (TON) |  | 13 |  | NOZZLES (1/32") |  | 5 X 16 |  | STRING STAB |  |  | 17.375 | 3 |  | 7 5/8 REG |  | 2.37 | 0.7656 |  | KILL MW (SG)
µ FUNNEL (SEC) | 58 | 60 | AVG. RPM SURFACE |  | 140 |  | DEPTH IN (M) |  | 2101 |  | 2 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 18.3 | 5.9116 |  | TOTAL | 4748
PV | 41 | 39 | AVG. RPM DOWNHOLE |  | 140 |  | DEPTH OUT (M) |  | 2305 |  | STRING STAB |  |  | 17.375 | 3 |  | 7 5/8 REG |  | 2.14 | 0.6913 |  | DIESEL (LTR)
YIELD POINT | 31 | 33 | FLOWRATE (GPM) |  | 790 |  | METERAGE (M) |  | 204 |  | 4 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 36.91 | 11.9234 |  | RIG TANK | 72631
GEL ST. | 11/13 | 12/14 | PRESSURE (PSI) |  | 3650 - 3750 |  | RPM SURF. |  | 80 - 150 |  | X/OVER |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.93 | 0.30043 |  | CAMP TANK | 18466
WL (ml/30 min) | 6.6 | 6.7 | TORQ. ON-BTM (KLB-FT) |  | 7 - 13 |  | RPM BTM. |  | 80 - 150 |  | 2 X 8" DCS |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.34 | 4.0953 |  | CONSUMED | 15821
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 5 - 6 |  | WOB (TON) |  | 5 - 15 |  | DRILLING JAR |  |  | 7.9375 | 3 |  | 6 5/8 REG |  | 9.53 | 2.128 |  | RECEIVED
ALK (MUD) | 0.3 | 0.3 | STRING WT. (TON) - ROT |  | 130 |  | AVG. ROP (M/HR) |  | 3.4234 |  | 2 X 8" DCS |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.43 | 4.1154 |  | TOTAL | 91097
ALK (FILT.) | 0.4 | 0.4 | PICK-UP WT. (TON) |  | 135 |  | BIT ROT HRS. |  | 59.59 |  | X/OVER |  |  | 7.625 | 2.8125 |  | 5 1/2 FH |  | 0.81 | 0.18087 |  | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 125 |  | K-REVS IN 24 HRS |  | 193.14 |  | 10 X 5 1/2" HWDPS |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 94.38 | 8.4468 |  | RIG STORAGE | 480000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 504.6 | [12 empty] | CAMP STORAGE | 81000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 18.6 | [12 empty] | CONSUMED | 282400
KCl (mg/l) | 51862.2 | 51862.2 | JAR | 94.56 | STAB - 1 | 293.06 | JET VELOCITY (M/SEC) |  | 79.4 | [12 empty] | RECEIVED | 282400
CHLORIDES (mg/l) | 25000 | 25000 | MOTOR |  | STAB - 2 | 293.06 | TFA (IN²) |  | 0.98 | [12 empty] | TOTAL | 561000
HARDNESS (mg/l) | 400 | 400 | 9 1/2" DCS | 303.06 | STAB - 3 | 94.56 | HSI |  | 2.008 | [12 empty] | POB
SAND % | 0.2 | 0.2 | 8" DCS | 303.06 | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 215.23 |  |  | MPCL | 5
LUBRICANT % | 1 | 1 | BHA ROT. HRS |  | 303.06 |  | BIT NO. 4RR1 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 33 |  |  | MPCL SERV | 25
SOLIDS % | 34.54 | 34.54 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 22 |  |  | SECURITY
M.B.T. (lb/bbl) | 7.5 | 7.5 | CIRC. HRS |  | 23.2 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 47
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 7
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 30" CONDUCTOR |  |  | 37 | 1953/1953 |  | 0.08 | [6 empty] | MWD |  | TOTAL | 108
DAILY WELL COST (US$) |  | 62924.21 | SHAKER-2 | 1 X 100 | 2 X 100 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 1981/1981 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 3701481.1567 | SHAKER-3 | 1 X 100 | 2 X 100 | [5 empty] | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 18.59% | MUD CLEANER | 3 X 140 | [6 empty] | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | LOT (EMW) | 2.16
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 82
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PRESS PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | JX CHINA | 21.25 | 5000 | P-1 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 30 |  | 2218 | 250 / 230 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JX CHINA | 21.25 | 5000 | P-2 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 40 |  | 2218 | 300 / 300 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-05-09 | 2019-06-08 | BLIND RAMS | JX CHINA | 21.25 | 5000 | P-3 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 50 |  | 2218 | 400 / 400 |  |  | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-06-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  | 2019-06-17 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-08
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43624 | 43625 | 24 | DRL | PT-P | D | DRILLED 17 1/2" HOLE FROM 2222M TO 2305M & ADJUSTED DRILLING PARAMETERS TO OPTIMIZE ROP. REAMED / WASHED DRILLED INTERVAL AT EACH CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-09
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43625 | 43625.1146 | 2.75 | DRL | PT-P | CIR | CIRCULATED & CLEANED HOLE.
43625.1146 | 43625.125 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43625.125 | 43625.1562 | 0.75 | DRL | PT-P | S | DROPPED TOTCO & CHASED WITH MUD. P/BACK TO 2286M & ALLOWED TIME TO RECORD DEVIATION SURVEY.
43625.1562 | 43625.25 | 2.25 | DRL | PT-P | POOH | POOH FROM 2286M TO 1854M ON ELEVATORS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | PUMPING SLUG
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 17 1/2" HOLE FROM 2222M TO 2305M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE & L/DOWN BHA FOR INSPECTION. M/UP & RIH 17 1/2" BIT WITH INSPECTED BHA TO BTM.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14