## DDR # 360
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 360
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-04-28
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4995 / 4945 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | S. KHALID AZIM / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4866 | 4831.57 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 359.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JEELANI |  |  | MD/TVD @ 06:00HRS: |  | 4866 | 4831.57 | [5 empty] | DAILY PROGRESS @ 00:00HRS:
2020-04-27 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | RUN NO. |  |  | 72 |  | BHA NO. |  |  | 91 | IN (M) |  | 4816 |  | OUT (M) | 4866 |  | STRING (BBL) | 200
CHECK TIME |  | 18:00 | MD @ 00:00HR (M) |  | 4866 |  | BIT NO. |  |  | 30RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 726.4
DEPTH, MD (M) |  | 4866 | TVD @ 00:00HR (M) |  | 4831.57 |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 |  |  | PITS (BBL) | 321
MW IN (SG) |  | 1.63 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | SLB PD |  |  | 5.375 | 3.625 |  | 3 1/2 REG |  | 4.43 |  |  | ACT. SYS (BBL) | 1247.4
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MDSi613 |  | X/O |  |  | 4.625 | 1.5 |  | 3 1/2 REG |  | 0.62 |  |  | RESV. SYS (BBL) | 531
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | QF3438 |  | MUD MOTOR |  |  | 4.75 | 3.75 |  | 3 1/2 IF |  | 7.12 |  |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | ST. STAB |  |  | 5.75 | 3.75 |  | 3 1/2 IF |  | 1.57 |  |  | KILL MW (SG)
µ FUNNEL (SEC) |  | 50 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3 X 12 |  | FLOAT SUB |  |  | 4.75 | 2.5 |  | 3 1/2 IF |  | 0.78 |  |  | TOTAL | 1778.4
PV |  | 28 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4816 |  | L. SAVER SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.45 |  |  | DIESEL (LTR)
YIELD POINT |  | 24 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  | 4866 |  | SPSA (MWD) |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 9.45 |  |  | RIG TANK | 100025
GEL ST. |  | 10/14 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  | 50 |  | PBL SUB |  |  | 4.75 | 2.75 |  | 3 1/2 IF |  | 3.09 |  |  | CAMP TANK | 20051
WL (ml/30 min) |  | 4.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  | 20 |  | 18 X HWDP's |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.92 |  |  | CONSUMED | 6626
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  | 131+20 |  | D. JAR |  |  | 4.875 | 2.25 |  | 3 1/2 IF |  | 9.02 |  |  | RECEIVED
ALK (MUD) |  | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) |  |  | 2-6 |  | 9 X HWDP's |  |  | 3.5 | 2.1875 |  | 3 1/2 IF |  | 84.89 |  |  | TOTAL | 120076
ALK (FILT.) |  | 0.3/1.2 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) |  |  | 2.7996 | [12 empty] | WATER (LTR)
pH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. |  |  | 17.86 | [12 empty] | RIG STORAGE | 536824
MAX SHIELD % |  | 1.8 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS |  |  | 163.55 | [12 empty] | CAMP STORAGE | 73000
KCl (%) |  | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  | 267.55 | [12 empty] | CONSUMED | 137500
KCl (mg/l) |  | 49574 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  | 65.6 | [12 empty] | RECEIVED | 118800
CHLORIDES (mg/l) |  | 122933 | JAR | 40.98 | STAB - 1 | 40.98 | JET VELOCITY (M/SEC) |  |  | 67.19 | [12 empty] | DRL WASTE
HARDNESS (mg/l) |  | 280 | 18 X 3 1/2" HWDPS | 49.76 | MOTOR & PD | 20.98 | TFA (IN²) |  |  | 0.33 | [12 empty] | POB
PENETRAX % |  | 0.8 | 9 x 3 1/2" HWDP | 20.98 | SPSA | 20.98 | HSI |  |  | 2.8 |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 7
MAX GUARD % |  | 1.2 | DAILY BHA ROT. HRS |  | 0.28 |  | MOTOR REV/GAL |  |  | 0.58 |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 31
SOLIDS % |  | 19.71 | DAILY ON BOTTOM HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) |  | 3.8 | DAILY CIRC. HRS |  | 7.36 |  | BIT NO. 30RR |  |  | 2-1-BT-A-X-I-WT-BHA |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 4
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4770.54 /4754.19 |  | 31.29 |  | 295.64 |  |  | 17.58 |  | MWD |  | TOTAL | 120
DAILY WELL COST (US$) |  | 62935 | SHAKER-2 | 3 x 140 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4802 / 4780.44 |  | 35.67 |  | 304.26 |  |  | 4.36 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 24615200 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4829 / 4802.39 |  | 38.08 |  | 302.21 |  |  | 2.69 |  | MWD |  | LAST CSG SIZE | 7''
% OF AFE SPENT |  | 123.7% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | [11 empty] | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | [11 empty] | MAASP (PSI) | 2360
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4815 | 1240 /1340 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4815 | 1860 /1940 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4815 | 2200 /2200 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4775/4758.16
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4787 / 4768
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-04-20 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  | 385 |  | MUD LOSSES |  |  |  | 750 |  | KUSSAK | 4821 / 4796
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-05-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4857 / 4825
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-27
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43948 | 43948.0938 | 2.25 | DRL | NPT-UP | OTH | SPOTTED 60 BBL ND LCM PILL (100 PPB) THROUGH PBL. OBSERVED PARTIAL RETURNS DURING DISPLACEMENT.
43948.0938 | 43948.1458 | 1.25 | DRL | NPT-UP | POOH | POOH FROM 4742M TO 4243M.
43948.1458 | 43948.1771 | 0.75 | DRL | NPT-UP | OTH | ALLOWED SOAKING TIME, MEANWHILE MONITORED WELL ON TRIP TANK, OBSERVED STATIC LOSS @ 65 BBL/HR.
43948.1771 | 43948.2396 | 1.5 | DRL | NPT-UP | RIH | RIH FROM 4243M TO 4739M MEANWHILE FILLED HOLE WITH WATER THROUGH KILL LINE.
43948.2396 | 43948.375 | 3.25 | DRL | NPT-UP | OTH | PREPARED HIGH CONC ND PILL MEANWHILE FILLED HOLE WITH WATER THROUGH KILL LINE.
43948.375 | 43948.5 | 3 | DRL | NPT-UP | SP | SPOTTED 140 BBL HIGH CONC. (140PPB) ND LCM PILL (UNDERDISPLACED 30 BBL). OBSERVED PARTIAL RETURNS DURING DISPLACEMENT.
43948.5 | 43948.5312 | 0.75 | DRL | NPT-UP | RW | PUMPED OUT FROM 4739M TO 4623M. MEANWHILE DISPLACED REMAINING PILL IN STRING. OBSERVED RETURNS AT SHAKERS.
43948.5312 | 43948.5938 | 1.5 | DRL | NPT-UP | POOH | POOH FROM 4623M TO 4134M.
43948.5938 | 43948.6354 | 1 | DRL | NPT-UP | OTH | ALLOWED SOAKING TIME, MEANWHILE MONITORED WELL ON TRIP TANK, OBSERVED NO STATIC LOSS - WELL STABLE.
43948.6354 | 43948.7188 | 2 | DRL | NPT-UP | CIR | CIRCULATED TO CONDITION MUD, KEPT CIRCULATING TO HOMOGENIZE MUD COLUMN AT 1.63SG IN/OUT. CIRCULATION RATE WAS INCREASED GRADUALLY FROM 200 GPM TO 280 GPM, OBSERVED NO DYNAMIC LOSSES.
43948.7188 | 43948.7292 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43948.7292 | 43949 | 6.5 | DRL | NPT-UP | POOH | POOH FROM 4134M TO 1666M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-28
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43949 | 43949.1458 | 3.5 | DRL | NPT-UP | POOH | POOH FROM 1666M TO 291M.
43949.1458 | 43949.1562 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED- WELL STATIC.
43949.1562 | 43949.1875 | 0.75 | DRL | NPT-UP | BHA | POOH BHA FROM 291M TO 55M. MEANWHILE L/DOWN D. JAR.
43949.1875 | 43949.2083 | 0.5 | DRL | NPT-UP | E / C | B/OUT STRING, DROPPED BALLS TO DEACTIVATE PBL. TURNED ON PUMP & OBSERVED DEACTIVATION AT 2400 PSI. POOH PBL SUB TO SURFACE AND RECOVERED BALLS & DART FROM CATCHER SUB.
43949.2083 | 43949.25 | 1 | DRL | NPT-UP | BHA | POOH REMAINING BHA COMPONENTS TO SURFACE. B/OUT AND L/DOWN 6'' PDC BIT & SLB PD. L/DOWN SPSA & MWD TOOL IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA : SANDSTONE, CLAYSTONE.
OPERATIONS AT 06:00 HRS |  |  | L/DOWN SPSA & MWD TOOL IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | SPOTTED 60BBL LCM PILL, POOH TO 4243M, OBSERVED WELL, STATIC LOSSES, RIH TO 4739M AND PUMPED ANOTHER 140 BBL HIGH CONC. LCM PILL, POOH TO 4134M, OBSERVED WELL, OBSERVED NO LOSSES, CIRCULATED AND CHECKED FOR DYNAMIC LOSSES, NO LOSSES. CIRCULATED TO HOMOGENIZE MUD IN OUT 1.63SG, POOH TO 1666M AND IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE, L/DOWN SLB POWER DRIVE AND MWD TOOLS, P/UP MOTOR BHA WITH 2 X ST. STABS AND RIH TO BTM AT 4866M, RESUME DRILLING 6'' HOLE AHEAD.
REMARKS |  |  | PREPARED 440 BBL FRESH MUD.
Formulas:
MIRAJ-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14