## DDR # 361
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 361
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-04-29
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4995 / 4945 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | S. KHALID AZIM / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4867 | 4832.3 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 360.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JEELANI |  |  | MD/TVD @ 06:00HRS: |  | 4875 | 4838.32 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 1
2020-04-28 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | RUN NO. |  |  | 73 |  | BHA NO. |  |  | 92 | IN (M) |  | 4866 |  | OUT (M) |  |  | STRING (BBL) | 215
CHECK TIME |  | 20:00 | MD @ 00:00HR (M) |  | 4867 |  | BIT NO. |  |  | 30RR1 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 643.9
DEPTH, MD (M) |  | 4866 | TVD @ 00:00HR (M) |  | 4832.3 |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 |  |  | PITS (BBL) | 450
MW IN (SG) |  | 1.63 | DAILY PROGRESS (M) |  | 1 |  | MANUFACTURER |  |  | SMITH |  | MUD MOTOR |  |  | 4.75 | 3.75 |  | 3 1/2 REG |  | 7.12 |  |  | ACT. SYS (BBL) | 1308.9
MW OUT (SG) |  |  | INST. ROP (M/HR) |  | 2 |  | TYPE |  |  | MDSi613 |  | ST. STAB |  |  | 5.75 | 3.75 |  | 3 1/2 REG |  | 1.57 |  |  | RESV. SYS (BBL) | 513
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | QF3438 |  | FLOAT SUB |  |  | 4.75 | 2.5 |  | 3 1/2 IF |  | 0.78 |  |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  | 3 |  | IADC CODE |  |  |  |  | 1 X DC |  |  | 4.75 | 2.125 |  | 3 1/2 IF |  | 9.27 |  |  | KILL MW (SG)
µ FUNNEL (SEC) |  | 53 | AVG. RPM SURFACE |  | 30 |  | NOZZLES (1/32") |  |  | 3 X 12 |  | ST. STAB |  |  | 5.875 | 2 |  | 3 1/2 IF |  | 1.31 |  |  | TOTAL | 1821.9
PV |  | 29 | AVG. RPM DOWNHOLE |  | 135 |  | DEPTH IN (M) |  |  | 4866 |  | PBL SUB |  |  | 4.75 | 2.75 |  | 3 1/2 IF |  | 3.09 |  |  | DIESEL (LTR)
YIELD POINT |  | 25 | FLOWRATE (GPM) |  | 180 |  | DEPTH OUT (M) |  |  |  |  | NMDC |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 4.51 |  |  | RIG TANK | 97152
GEL ST. |  | 11/15 | PRESSURE (PSI) |  | 1800-2000 |  | METERAGE (M) |  |  | 1 |  | 18 X HWDP's |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.92 |  |  | CAMP TANK | 19497
WL (ml/30 min) |  | 4.8 | TORQ. ON-BTM (KLB-FT) |  | 2-3 |  | RPM SURF. |  |  | 30 |  | D. JAR |  |  | 4.875 | 2.25 |  | 3 1/2 IF |  | 9.02 |  |  | CONSUMED | 3427
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  | 1-2 |  | RPM BTM. |  |  | 105 +30 |  | 9 X HWDP's |  |  | 3.5 | 2.1875 |  | 3 1/2 IF |  | 84.89 |  |  | RECEIVED
ALK (MUD) |  | 0.4 | STRING WT. (TON) - ROT |  | 152 |  | WOB (TON) |  |  | 2-4 | [12 empty] | TOTAL | 116649
ALK (FILT.) |  | 0.3/1.2 | PICK-UP WT. (TON) |  | 155 |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH |  | 9.5 | SLACK-OFF WT. (TON) |  | 140 |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 554040
MAX SHIELD % |  | 1.7 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 68000
KCl (%) |  | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  | 267.55 | [12 empty] | CONSUMED | 73224
KCl (mg/l) |  | 50527.6 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 112800
CHLORIDES (mg/l) |  | 98800 | JAR | 43.93 | STAB - 1 | 43.93 | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) |  | 280 | 18 X 3 1/2" HWDPS | 52.71 | MOTOR | 23.93 | TFA (IN²) |  |  | 0.33 | [12 empty] | POB
PENETRAX % |  | 0.8 | 9 x 3 1/2" HWDP | 23.93 | STAB-2 | 2.95 | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 291.68 |  |  | MPCL | 7
MAX GUARD % |  | 1.2 | DAILY BHA ROT. HRS |  | 2.95 |  | MOTOR REV/GAL |  |  | 0.58 |  | BHA WT. IN MUD (TON) | [7 empty] | 8 |  |  | MPCL SERV | 31
SOLIDS % |  | 19.71 | DAILY ON BOTTOM HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 6 |  |  | SECURITY
M.B.T. (lb/bbl) |  | 3.8 | DAILY CIRC. HRS |  | 4.63 |  | BIT NO. |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 4
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4770.54 /4754.19 |  | 31.29 |  | 295.64 |  |  | 17.58 |  | MWD |  | TOTAL | 120
DAILY WELL COST (US$) |  | 44771 | SHAKER-2 | 3 x 60 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4802 / 4780.44 |  | 35.67 |  | 304.26 |  |  | 4.36 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 24659971 | SHAKER-3 | 3 x 60 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4829 / 4802.39 |  | 38.08 |  | 302.21 |  |  | 2.69 |  | MWD |  | LAST CSG SIZE | 7''
% OF AFE SPENT |  | 123.9% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | [11 empty] | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | [11 empty] | MAASP (PSI) | 2490
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4815 | 1240 /1340 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4815 | 1860 /1940 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4815 | 2200 /2200 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4775/4758.16
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4787 / 4768
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-04-20 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 750 |  | KUSSAK | 4821 / 4796
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-05-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4857 / 4825
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-28
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43949 | 43949.1458 | 3.5 | DRL | NPT-UP | POOH | POOH FROM 1666M TO 291M.
43949.1458 | 43949.1562 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED- WELL STATIC.
43949.1562 | 43949.1875 | 0.75 | DRL | NPT-UP | BHA | POOH BHA FROM 291M TO 55M. MEANWHILE L/DOWN D. JAR.
43949.1875 | 43949.2083 | 0.5 | DRL | NPT-UP | E / C | B/OUT STRING, DROPPED BALLS TO DEACTIVATE PBL. TURNED ON PUMP & OBSERVED DEACTIVATION AT 2400 PSI. POOH PBL SUB TO SURFACE AND RECOVERED BALLS & DART FROM CATCHER SUB.
43949.2083 | 43949.2604 | 1.25 | DRL | NPT-UP | BHA | POOH REMAINING BHA COMPONENTS TO SURFACE. B/OUT AND L/DOWN 6'' PDC BIT & SLB PD. RETRIEVED MWD TOOL & L/DOWN SPSA.
43949.2604 | 43949.3542 | 2.25 | DRL | NPT-UP | BHA | P/UP & M/UP RR PDC BIT + MUD MOTOR. RIH AS PER BHA TO 291M. FLUSHED SAME.
43949.3542 | 43949.6562 | 7.25 | DRL | NPT-UP | RIH | RIH FROM 291M TO 3397M. MEANWHILE FILLED UP STRING EVERY 15 STDS.
43949.6562 | 43949.6667 | 0.25 | DRL | NPT-UP | CIR | BROKE CIRCULATION.
43949.6667 | 43949.8229 | 3.75 | DRL | NPT-UP | RIH | CONT'D RIH FROM 3397M TO 4541M. MEANWHILE FILLED UP STRING EVERY 15 STDS.
43949.8229 | 43949.8646 | 1 | DRL | NPT-UP | RW | PRECAUTIONARY WASHED DOWN FROM 4541M TO 4719M, OBSERVED OBSTRUCTION AT 4719M.
43949.8646 | 43949.9167 | 1.25 | DRL | NPT-UP | RW | REAMED DOWN FROM 4719M TO 4761M (PASSED THROUGH WINDOW W/OUT ROTATION).
43949.9167 | 43949.9896 | 1.75 | DRL | NPT-UP | RW | WASHED/ REAMED DOWN FROM 4761M TO BTM AT 4866M. MEANWHILE INCREASED FLOW RATE GRADUALLY FROM 150 TO 180 GPM, MONITORED RETURNS / PIT LEVELS, NO LOSSES OBSERVED.
43949.9896 | 43950 | 0.25 | DRL | PT-P | DM | DRILLED 6'' HOLE FROM 4866M TO 4867M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-04-29
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43950 | 43950.0625 | 1.5 | DRL | PT-P | DM | DRILLED 6'' HOLE FROM 4867M TO 4868M, OBSERVED DYNAMIC LOSSES, PUMPED AND DISPLACED 25 BBL ND LCM PILL (40 PPB).
43950.0625 | 43950.0729 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, MEANWHILE ALLOWED SOAKING TIME TO LCM PILL. OBSERVED STATIC LOSSES = 40 BBL/HR.
43950.0729 | 43950.1771 | 2.5 | DRL | PT-P | DM | CONT'D DRILLING FROM 4868M TO 4873M WITH REDUCED FLOW RATE. MEANWHILE KEPT RETAINING LCM (F, M) IN SYSTEM AND CUT MUD DENSITY FROM 1.63SG TO 1.62SG. OBSERVED DYNAMIC LOSS RATE REDUCED FROM 50 BBL/HR TO 15 BBL/HR.
43950.1771 | 43950.1875 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - OBSERVED STATIC LOSS = 10 BBL/HR
43950.1875 | 43950.2188 | 0.75 | DRL | PT-P | DM | RESUMED DRILLING 6'' HOLE FROM 4873M TO 4874M, MEANWHILE PUMPED AND DISPLACED 25 BBL ND LCM PILL (40PPB). OBSERVED DYNAMIC LOSS REDUCED TO 10 BBL/HR.
43950.2188 | 43950.2292 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, MEANWHILE ALLOWED SOAKING TIME TO LCM PILL. OBSERVED STATIC LOSSES = 3 BBL/HR.
43950.2292 | 43950.25 | 0.5 | DRL | PT-P | DM | DRILLED 6'' HOLE FROM 4874M TO 4875M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA : SANDSTONE, CLAYSTONE.
OPERATIONS AT 06:00 HRS |  |  | DRILLING 6'' HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE, L/DOWN SLB POWER DRIVE AND MWD TOOLS, P/UP MOTOR BHA WITH 2 X ST. STABS AND RIH TO 3397M, FILLED UP STRING EVERY 15 STDS, RIH TO 4549M, WASHED DOWN FROM 4549M TO 4719M, REAMED DOWN FROM 4719M TO BTM AT 4866M, NO LOSSES OBSERVED WHILE REAMING DOWN, DRILLED 6'' HOLE FROM 4866M TO 4867M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 6'' HOLE TILL WELL TD.
REMARKS
Formulas:
MIRAJ-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14