## DDR # 366
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 366
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-05-04
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4995 / 4945 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | S. KHALID AZIM / HAMZA / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4949 | 4896.53 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 365.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JEELANI |  |  | MD/TVD @ 06:00HRS: |  | 4949 | 4896.53 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 16
2020-05-03 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | RUN NO. |  |  | 74 |  | BHA NO. |  |  | 93 | IN (M) |  | 4889 |  | OUT (M) |  |  | STRING (BBL) | 208.6
CHECK TIME | 8:00 | 23:59 | MD @ 00:00HR (M) |  | 4949 |  | BIT NO. |  |  | 31 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 657.6
DEPTH, MD (M) | 4939 | 4949 | TVD @ 00:00HR (M) |  | 4896.53 |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.16 |  |  | PITS (BBL) | 470
MW IN (SG) | 1.6 | 1.6 | DAILY PROGRESS (M) |  | 16 |  | MANUFACTURER |  |  | SMITH |  | MUD MOTOR |  |  | 4.75 | 3.75 |  | 3 1/2 REG |  | 7.11 |  |  | ACT. SYS (BBL) | 1336.2
MW OUT (SG) | 1.6 | 1.6 | INST. ROP (M/HR) |  | 0.56 |  | TYPE |  |  | MDSi713 |  | ST. STAB |  |  | 5.75 | 3.75 |  | 3 1/2 REG |  | 1.57 |  |  | RESV. SYS (BBL) | 435
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 0.83 |  | SERIAL NO. |  |  | JM9761 |  | FLOAT SUB |  |  | 4.75 | 2.5 |  | 3 1/2 IF |  | 0.78 |  |  | KILL MUD (BBL)
FL TEMP. °F |  | 138 | AVG. WOB (TON) |  | 4 |  | IADC CODE |  |  |  |  | 1 X DC |  |  | 4.75 | 2.125 |  | 3 1/2 IF |  | 9.27 |  |  | KILL MW (SG)
µ FUNNEL (SEC) | 58 | 57 | AVG. RPM SURFACE |  | 30 |  | NOZZLES (1/32") |  |  | 2 x 10 + 2 x 11 |  | ST. STAB |  |  | 5.875 | 2 |  | 3 1/2 IF |  | 1.31 |  |  | TOTAL | 1771.2
PV | 28 | 30 | AVG. RPM DOWNHOLE |  | 108+30 |  | DEPTH IN (M) |  |  | 4889 |  | PBL SUB |  |  | 4.75 | 2.75 |  | 3 1/2 IF |  | 3.09 |  |  | DIESEL (LTR)
YIELD POINT | 25 | 25 | FLOWRATE (GPM) |  | 187 |  | DEPTH OUT (M) |  |  |  |  | NMDC |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 4.51 |  |  | RIG TANK | 94399
GEL ST. | 11/14 | 12/16 | PRESSURE (PSI) |  | 2300-2500 |  | METERAGE (M) |  |  | 60 |  | 18 X HWDP's |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.92 |  |  | CAMP TANK | 16779
WL (ml/30 min) | 3.8 | 3.6 | TORQ. ON-BTM (KLB-FT) |  | 2-4 |  | RPM SURF. |  |  | 30 |  | D. JAR |  |  | 4.875 | 2.25 |  | 3 1/2 IF |  | 9.02 |  |  | CONSUMED | 8198
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 1-2 |  | RPM BTM. |  |  | 107+30 |  | 9 X HWDP's |  |  | 3.5 | 2.1875 |  | 3 1/2 IF |  | 84.89 |  |  | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  | 150 |  | WOB (TON) |  |  | 2-6 | [12 empty] | TOTAL | 111178
ALK (FILT.) | 0.4/1.2 | 0.4/1.2 | PICK-UP WT. (TON) |  | 155 |  | AVG. ROP (M/HR) |  |  | 1.0256 | [12 empty] | WATER (LTR)
pH | 10.5 | 10.5 | SLACK-OFF WT. (TON) |  | 140 |  | BIT ROT HRS. |  |  | 58.5 | [12 empty] | RIG STORAGE | 569400
MAX SHIELD % | 1.5 | 1.3 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS |  |  | 158.69 | [12 empty] | CAMP STORAGE | 73000
KCl (%) | 5 | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  | 332.45 | [12 empty] | CONSUMED | 102280
KCl (mg/l) | 47286.2 | 46714.2 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  | 53.8 | [12 empty] | RECEIVED | 75200
CHLORIDES (mg/l) | 79500 | 79000 | JAR | 135.11 | STAB - 1 | 135.11 | JET VELOCITY (M/SEC) |  |  | 53.81 | [12 empty] | DRL WASTE
HARDNESS (mg/l) | 280 | 280 | 18 X 3 1/2" HWDPS | 143.89 | MOTOR | 95.47 | TFA (IN²) |  |  | 0.338 | [12 empty] | POB
PENETRAX % | 0.6 | 0.8 | 9 x 3 1/2" HWDP | 115.11 | STAB-2 | 94.13 | HSI |  |  | 1.43 |  | TOTAL LENGTH (M) | [7 empty] | 291.63 |  |  | MPCL | 9
MAX GUARD % | 1.5 | 1.3 | DAILY BHA ROT. HRS |  | 23.21 |  | MOTOR REV/GAL |  |  | 0.58 |  | BHA WT. IN MUD (TON) | [7 empty] | 8 |  |  | MPCL SERV | 27
SOLIDS % | 23.4 | 23.1 | DAILY ON BOTTOM HRS |  | 19.2 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 6 |  |  | SECURITY
M.B.T. (lb/bbl) | 3.8 | 3.8 | DAILY CIRC. HRS |  | 23.78 |  | BIT NO. |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 64
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 27
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 2 x 50 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4770.54 /4754.19 |  | 31.29 |  | 295.64 |  |  | 17.58 |  | MWD |  | TOTAL | 132
DAILY WELL COST (US$) |  | 58973.252 | SHAKER-2 | 2 X 40 + 1 x 60 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4802 / 4780.44 |  | 35.67 |  | 304.26 |  |  | 4.36 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 24929502.0954 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4829 / 4802.39 |  | 38.08 |  | 302.21 |  |  | 2.69 |  | MWD |  | LAST CSG SIZE | 7''
% OF AFE SPENT |  | 125.2% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | [11 empty] | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | [11 empty] | MAASP (PSI) | 2706
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4889 | 1000/1000 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4889 | 1450/1400 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4889 | 1550/1600 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4775/4758.16
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4787 / 4768
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-04-20 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  | 270 |  | MUD LOSSES |  |  |  | 2034 |  | KUSSAK | 4821 / 4796
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-05-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4857 / 4825
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-03
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43954 | 43954.0208 | 0.5 | DRL | NPT-UP | RR | WHILE DRILLING BELOW 4933M, OBSERVED SPP DROPPED 100 PSI, P/UP STRING AND CHECKED PUMP, OK. CHECKED PRESSURE SENSOR ON STAND PIPE MANIFOLD.
43954.0208 | 43955 | 23.5 | DRL | PT-P | DM | RESUMED DRILLING, DRILLED 6'' HOLE FROM 4933M TO 4949M. MEANWHILE PUMPED AND DISPLACED 15 BBL ND LCM PILL(s). OBSERVED DYNAMIC LOSSES @ 10-12 BBL/HR.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-04
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43955 | 43955.0833 | 2 | DRL | PT-P | CIR | CIRCULATED TILL SHAKERS CLEAN.
43955.0833 | 43955.125 | 1 | DRL | PT-P | SP | SPOTTED 30 BBL, (UNDERDISPLACED 10 BBL) ND LCM PILL (40PPB).
43955.125 | 43955.1771 | 1.25 | DRL | PT-P | RW | PUMPED OUT FROM 4949M TO 4739M (INSIDE 7" LINER).
43955.1771 | 43955.1875 | 0.25 | DRL | PT-P | FC | FLOW CHECKED. OBSERVED STATIC LOSSES @ 2 BBL/HR.
43955.1875 | 43955.25 | 1.5 | DRL | PT-P | POOH | PUMPED SLUG & POOH FROM 4739M TO 4251M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA : SANDSTONE, CLAYSTONE.
OPERATIONS AT 06:00 HRS |  |  | POOH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 6'' HOLE FROM 4933M TO 4949M. MEANWHILE PUMPED & DISPLACED 15 BBL ND LCM PILL(S) INTERMITTENTLY TO OVERCOME LOSSES. OBSERVED DYNAMIC LOSSES @ 10 BBL/HR.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CIRCULATION FOR BTM UP, PUMP OUT OF HOLE TO 4750M, POOH TO SURFACE, L/DOWN BOP COMPONENTS, PERFORM BOPT, P/UP & M/UP NEW MUD MOTOR + PDC BIT, RIH TO BTM AND RESUME DRILLING.
REMARKS
Formulas:
MIRAJ-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14