## DDR # 367
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 366.9792
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-05-05
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4995 / 4945 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | ADNAN OMER / M. MOHSIN ALI |  |  | MD/TVD @ 00:00HRS: |  | 4949 | 4896.53 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 366.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JEELANI |  |  | MD/TVD @ 06:00HRS: |  | 4949 | 4896.53 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2020-05-04 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | RUN NO. |  |  | 75 |  | BHA NO. |  |  | 94 | IN (M) |  | 4949 |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME |  | 20:00 | MD @ 00:00HR (M) |  | 4949 |  | BIT NO. |  |  | 32 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 980
DEPTH, MD (M) |  | 4949 | TVD @ 00:00HR (M) |  | 4896.53 |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 |  |  | PITS (BBL) | 338
MW IN (SG) |  | 1.6 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | MUD MOTOR |  |  | 4.75 | 2.875 |  | 3 1/2 IF |  | 7.11 |  |  | ACT. SYS (BBL) | 1318
MW OUT (SG) |  | 1.6 | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MDi616LNBPX |  | ST. STAB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 1.57 |  |  | RESV. SYS (BBL) | 379
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | JM9761 |  | FLOAT SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.82 |  |  | KILL MUD (BBL)
FL TEMP. °F |  | 138 | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | LOWER SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.45 |  |  | KILL MW (SG)
µ FUNNEL (SEC) |  | 65 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3 x 10 |  | SLIM PULSE |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.44 |  |  | TOTAL | 1697
PV |  | 31 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4949 |  | ST. STAB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 1.97 |  |  | DIESEL (LTR)
YIELD POINT |  | 26 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | PBL SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 3.08 |  |  | RIG TANK | 89437
GEL ST. |  | 13/16 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | PONY NMDC |  |  | 4.75 | 2.3125 |  | 3 1/2 IF |  | 4.52 |  |  | CAMP TANK | 16245
WL (ml/30 min) |  | 3.6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | 15 X HWDP's |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 141.59 |  |  | CONSUMED | 5496
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | D. JAR |  |  | 4.75 | 2.1875 |  | 3 1/2 IF |  | 9.21 |  |  | RECEIVED
ALK (MUD) |  | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) |  |  |  |  | 12 X HWDP's |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 113.14 |  |  | TOTAL | 105682
ALK (FILT.) |  | 0.4/1.2 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH |  | 10.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 589650
MAX SHIELD % |  | 1.2 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 75000
KCl (%) |  | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 111250
KCl (mg/l) |  | 47095.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 133800
CHLORIDES (mg/l) |  | 79600 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) |  | 280 | 18 X 3 1/2" HWDPS |  | MOTOR |  | TFA (IN²) |  |  | 0.23 | [12 empty] | POB
PENETRAX % |  | 0.6 | 9 x 3 1/2" HWDP |  | STAB-2 |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 293.1 |  |  | MPCL | 7
MAX GUARD % |  | 1.4 | DAILY BHA ROT. HRS |  |  |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 8 |  |  | MPCL SERV | 27
SOLIDS % |  | 19.72 | DAILY ON BOTTOM HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 5 |  |  | SECURITY
M.B.T. (lb/bbl) |  | 3.8 | DAILY CIRC. HRS |  |  |  | BIT NO. 31 |  |  | 1-1-WT-A-X-I-NO-PR |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 64
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 27
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 2 x 50 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4770.54 /4754.19 |  | 31.29 |  | 295.64 |  |  | 17.58 |  | MWD |  | TOTAL | 130
DAILY WELL COST (US$) |  | 36734.1675 | SHAKER-2 | 2 X 40 + 1 x 60 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4802 / 4780.44 |  | 35.67 |  | 304.26 |  |  | 4.36 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 24966236.2629 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4829 / 4802.39 |  | 38.08 |  | 302.21 |  |  | 2.69 |  | MWD |  | LAST CSG SIZE | 7''
% OF AFE SPENT |  | 125.4% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | [11 empty] | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | [11 empty] | MAASP (PSI) | 2706
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4889 | 1000/1000 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4889 | 1450/1400 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | BLIND SHEAR RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4889 | 1550/1600 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4775/4758.16
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4787 / 4768
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-04-20 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  | 195 |  | MUD LOSSES |  |  |  | 2229 |  | KUSSAK | 4821 / 4796
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-05-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4857 / 4825
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-04
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43955 | 43955.0833 | 2 | DRL | PT-P | CIR | CIRCULATED TILL SHAKERS CLEAN.
43955.0833 | 43955.125 | 1 | DRL | PT-P | SP | SPOTTED 30 BBL, (UNDERDISPLACED 10 BBL) ND LCM PILL (40PPB).
43955.125 | 43955.1771 | 1.25 | DRL | PT-P | RW | PUMPED OUT FROM 4949M TO 4739M (INSIDE 7" LINER).
43955.1771 | 43955.1875 | 0.25 | DRL | PT-P | FC | FLOW CHECKED. OBSERVED STATIC LOSSES @ 2 BBL/HR.
43955.1875 | 43955.5 | 7.5 | DRL | PT-P | POOH | PUMPED SLUG & POOH FROM 4739M TO 1812M.
43955.5 | 43955.5104 | 0.25 | DRL | PT-P | FC | FLOW CHECKED. OBSERVED STATIC LOSSES @ 8 BBL/HR.
43955.5104 | 43955.6354 | 3 | DRL | PT-P | POOH | POOH FROM 1812M TO 292M (TOP OF BHA).
43955.6354 | 43955.6458 | 0.25 | DRL | PT-P | FC | FLOW CHECKED. OBSERVED STATIC LOSSES @ 8 BBL/HR.
43955.6458 | 43955.7604 | 2.75 | DRL | PT-P | BHA | POOH BHA FROM 292M TO SURFACE. L/D BHA FOR INSPECTION.
43955.7604 | 43955.9167 | 3.75 | DRL | PT-P | BOPT | HELD PJSM, M/U COMBINATION TOOL ASSY & RETRIEVED WEAR BUSHING. M/U TEST PLUG ASSEMBLY, SET TEST PLUG INSIDE 11'' THS. FLUSHED BOP STACK WITH WATER. P/T ANNULAR BOP @ 500/4500 PSI FOR 5/10 MIN - OK. P/T ROTARY HOSE & STANDPIPE MANIFOLD @ 500/6000 PSI FOR 5/10 MIN - OK. P/T UPPER VARIABLE PIPE RAMS (2 7/8" - 5"), LOWER PIPE RAMS, BLIND RAMS, HYD & MANUAL IBOP, FOSV, HCR & MANUAL VALVES @ KILL & CHOKE LINE, CHOKE MANIFOLD MASTER VALVE, CO-FLEXIP HOSE @ 500/9000 PSI FOR 5/10 MIN - OK. INSTALLED WEAR BUSHING & L/D TEST PLUG ASSEMBLY.
43955.9167 | 43955.9583 | 1 | DRL | PT-P | BHA | P/UP & M/UP 6'' NEW PDC (SMITH, MDi616LNBPX, SR # JM4653, 3 x 10/32'') + MUD MOTOR + 5 3/4'' ST. STAB + F.SUB + L.SAVER SUB + SPSA (INSTALLED MWD). SCRIBED MOTOR TF WITH MWD. RIH TO 21M.
43955.9583 | 43956 | 1 | DRL | NPT-UP | BHA | WHILE P/U PBL SUB OBSERVED WATER NOT DRAINING FROM PBL SUB. INSPECTED PBL SUB - OBSERVED ACTIVATION BALL ALREADY SEATED IN SLEEVE SEAT (AS RECEIVED FROM WELL SERVE). B/OUT PBL CATCHER.
TOTAL |  | 3
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-05
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43956 | 43956.0208 | 0.5 | DRL | NPT-UP | BHA | REMOVED ACTIVATION BALL FROM SLEAVE SEAT.
43956.0208 | 43956.0417 | 0.5 | DRL | PT-P | BHA | P/U 5 7/8" S. STAB + 4 3/4" PONY NMDC & M/U 5 7/8" S. STAB + 4 3/4" PBL SUB + 4 3/4" PONY NMDC. RIH TO 29M.
43956.0417 | 43956.0625 | 0.5 | DRL | PT-P | E / C | SHALLOW FUNCTION TESTED MUD MOTOR AND MWD @ 200 GPM, SPP = 1200 PSI.
43956.0625 | 43956.1146 | 1.25 | DRL | PT-P | E / C | FUNCTION TESTED PBL SUB - OK. P/BACK & B/OUT PBL CATCHER TO RETRIEVE ACTIVATION DART & DEACTIVATION BALLS.
43956.1146 | 43956.1979 | 2 | DRL | PT-P | BHA | RIH BHA FROM 29M TO 293M. P/U BHA SINGLE BY SINGLE.
43956.1979 | 43956.25 | 1.25 | DRL | PT-P | RIH | RIH FROM 293M TO 824M. FILL UP STRING EVERY 15 STANDS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA : SANDSTONE, CLAYSTONE.
OPERATIONS AT 06:00 HRS |  |  | RIH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CIRCULATED TO CLEAN HOLE. POOH TO SURFACE. PERFORMED BOP PRESSURE TEST. RIH FROM SURFACE TO 21M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH TO BOTTOM. DRILL AHEAD TO WELL TD.
REMARKS
Formulas:
MIRAJ-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14