## DDR # 370
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 369.9792
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-05-08
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4995 / 4945 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | ADNAN OMER / M. MOHSIN ALI |  |  | MD/TVD @ 00:00HRS: |  | 4969 | 4914.78 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 369.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JEELANI |  |  | MD/TVD @ 06:00HRS: |  | 4969 | 4914.78 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 2
2020-05-07 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | RUN NO. |  |  | 76 |  | BHA NO. |  |  | 95 | IN (M) |  | 4967 |  | OUT (M) |  |  | STRING (BBL) | 225.5
CHECK TIME | 8:00 | 13:00 | MD @ 00:00HR (M) |  | 4969 |  | BIT NO. |  |  | 32RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 658.7
DEPTH, MD (M) | 4967 | 4969 | TVD @ 00:00HR (M) |  | 4914.78 |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 |  |  | PITS (BBL) | 458
MW IN (SG) | 1.6 | 1.6 | DAILY PROGRESS (M) |  | 2 |  | MANUFACTURER |  |  | SMITH |  | MUD MOTOR |  |  | 4.75 | 2.875 |  | 3 1/2 IF |  | 6.89 |  |  | ACT. SYS (BBL) | 1342.2
MW OUT (SG) | 1.6 | 1.6 | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MDi616LNBPX |  | ST. STAB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 1.57 |  |  | RESV. SYS (BBL) | 343
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 7.41 |  | SERIAL NO. |  |  | JM9761 |  | FLOAT SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.82 |  |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  | 3-4 |  | IADC CODE |  |  |  |  | 1 X DC |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.29 |  |  | KILL MW (SG)
µ FUNNEL (SEC) | 70 | 80 | AVG. RPM SURFACE |  | 30-40 |  | NOZZLES (1/32") |  |  | 3 x 10 |  | ST. STAB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 1.97 |  |  | TOTAL | 1685.2
PV | 32 | 34 | AVG. RPM DOWNHOLE |  | 210 |  | DEPTH IN (M) |  |  | 4967 |  | PBL SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 3.07 |  |  | DIESEL (LTR)
YIELD POINT | 24 | 26 | FLOWRATE (GPM) |  | 165-170 |  | DEPTH OUT (M) |  |  |  |  | PONY NMDC |  |  | 4.75 | 2.3125 |  | 3 1/2 IF |  | 4.52 |  |  | RIG TANK | 139704
GEL ST. | 12/15 | 13/16 | PRESSURE (PSI) |  | 1750-2200 |  | METERAGE (M) |  |  | 2 |  | 15 X HWDP's |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 141.59 |  |  | CAMP TANK | 28825
WL (ml/30 min) | 4.3 | 4.5 | TORQ. ON-BTM (KLB-FT) |  | 4-5 |  | RPM SURF. |  |  | 30-40 |  | D. JAR |  |  | 3.5 | 2.1875 |  | 3 1/2 IF |  | 9.21 |  |  | CONSUMED | 5105
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 0-1 |  | RPM BTM. |  |  | 210 |  | 12 X HWDP's |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 113.14 |  |  | RECEIVED | 21000
ALK (MUD) | 0.5 | 0.4 | STRING WT. (TON) - ROT |  | 153 |  | WOB (TON) |  |  | 3-4 | [12 empty] | TOTAL | 168529
ALK (FILT.) | 0.4/1.2 | 1.3/1.1 | PICK-UP WT. (TON) |  | 154 |  | AVG. ROP (M/HR) |  |  | 7.4074 | [12 empty] | WATER (LTR)
pH | 10.5 | 10 | SLACK-OFF WT. (TON) |  | 143 |  | BIT ROT HRS. |  |  | 0.27 | [12 empty] | RIG STORAGE | 588525
MAX SHIELD % | 0.6 | 0.4 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS |  |  | 3.4 | [12 empty] | CAMP STORAGE | 75000
KCl (%) | 5 | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  | 51.7 | [12 empty] | CONSUMED | 123018
KCl (mg/l) | 45379.5 | 44235.4 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  | 48.5 | [12 empty] | RECEIVED | 140500
CHLORIDES (mg/l) | 78000 | 77500 | JAR | 8.71 | STAB - 1 | 8.71 | JET VELOCITY (M/SEC) |  |  | 76.25 | [12 empty] | DRL WASTE
HARDNESS (mg/l) | 280 | 280 | 3 1/2" HWDPS | 8.71 | MOTOR | 2.51 | TFA (IN²) |  |  | 0.23 | [12 empty] | POB
PENETRAX % | 0.6 | 0.2 | PBL SUB | 2.51 | STAB-2 | 8.71 | HSI |  |  | 1.93 |  | TOTAL LENGTH (M) | [7 empty] | 292.27 |  |  | MPCL | 8
MAX GUARD % | 0.4 | 0.2 | DAILY BHA ROT. HRS |  | 2.51 |  | MOTOR REV/GAL |  |  | 1.04 |  | BHA WT. IN MUD (TON) | [7 empty] | 8 |  |  | MPCL SERV | 28
SOLIDS % | 19.76 | 19.87 | DAILY ON BOTTOM HRS |  | 0.27 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 5 |  |  | SECURITY
M.B.T. (lb/bbl) | 3.8 | 3.8 | DAILY CIRC. HRS |  | 10.7 |  | BIT NO. 32 |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 50
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 3
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 28
APPROVED AFE (US$) |  | 25942000 | SHAKER-1 | 2 x 50 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4802 / 4780.44 |  | 35.67 |  | 301.77 |  |  | 4.39 |  | MWD |  | TOTAL | 117
DAILY WELL COST (US$) |  | 72115.155 | SHAKER-2 | 2 X 40 + 1 x 60 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4831 / 4804.02 |  | 37.9 |  | 301.51 |  |  | 2.31 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 25128648.2879 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4866 / 4831.86 |  | 36.7 |  | 304.06 |  |  | 1.68 |  | MWD |  | LAST CSG SIZE | 7''
% OF AFE SPENT |  | 96.86% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | 4895 / 4855.15 |  | 36.46 |  | 301.51 |  |  | 1.59 |  | MWD |  | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | 4923 / 4877.80 |  | 35.58 |  | 299.15 |  |  | 1.76 |  | MWD |  | MAASP (PSI) | 2706
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4889 | 1000/1000 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4889 | 1450/1400 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | SHEAR BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4889 | 1550/1600 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4775/4758.16
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4787 / 4768
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-05-04 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  | 326 |  | MUD LOSSES |  |  |  | 3275 |  | KUSSAK | 4821 / 4796
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-05-18 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4857 / 4825
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-07
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43958 | 43958.4375 | 10.5 | DRL | NPT-UP | RIH | RIH FROM 385M TO 4394M. FILL UP STRING EVERY 15 STANDS.
43958.4375 | 43958.5833 | 3.5 | DRL | NPT-UP | RW/RIH | WASHED DOWN FROM 4394M TO 4967M. OBSERVED NO LOSSES WHILE WASHING DOWN OF HOLE.
43958.5833 | 43958.6042 | 0.5 | DRL | PT-P | DM | DRILLED 6" HOLE FROM 4967M TO 4969M. OBSERVED TOTAL LOSSES WHILE DRILLING AT 4969M. TRIED TO P/U STRING. OBSERVED STRING STUCK.
43958.6042 | 43958.6875 | 2 | DRL | NPT-UP | STK | WORKED ON STRING WITH COMBINATION OF VARIOUS PARAMETERS - NO SUCCESS. ALSO OBSERVED NO RETURNS.
43958.6875 | 43959 | 7.5 | DRL | NPT-UP | STK | ACTIVATED PBL. ESTABLISHED CIRCULATION & OBSERVED NO LOSSES. WORK ON STRING WITH COMBINATION OF VARIOUS PARAMETERS IN PROGRESS. WHILE WORKING ON STRING PUMPED 50 BBL, 8% LUBE PILL.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-08
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43959 | 43959.25 | 6 | DRL | NPT-UP | STK | WORK ON STRING WITH COMBINATION OF VARIOUS PARAMETERS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA : SANDSTONE, CLAYSTONE.
OPERATIONS AT 06:00 HRS |  |  | WORK ON STRING IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH FROM 385M TO 4394M. WASHED DOWN FROM 4394M TO 4967M. DRILLED 6" HOLE FROM 4967M TO 4969M. OBSERVED LOSSES WHILE DRILLING AT 4969M. TRIED TO P/U STRING. OBSERVED STRING STUCK. WORK ON STRING WITH COMBINATION OF VARIOUS PARAMETERS IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RELEASE STRING.
REMARKS
Formulas:
MIRAJ-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14