## DDR # 373
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 372.9792
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-05-11
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4995 / 4945 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | ADNAN OMER / M. MOHSIN ALI / ADNAN |  |  | MD/TVD @ 00:00HRS: |  | 4969 | 4914.78 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 372.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JEELANI |  |  | MD/TVD @ 06:00HRS: |  | 4969 | 4914.78 | [5 empty] | DAILY PROGRESS @ 00:00HRS:
2020-05-10 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | RUN NO. |  |  | 76 |  | BHA NO. |  |  | 95 | IN (M) |  | 4967 |  | OUT (M) |  |  | STRING (BBL) | 225.6
CHECK TIME |  | 17:00 | MD @ 00:00HR (M) |  | 4969 |  | BIT NO. |  |  | 32RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 658.6
DEPTH, MD (M) |  | 4969 | TVD @ 00:00HR (M) |  | 4914.78 |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 |  |  | PITS (BBL) | 545
MW IN (SG) |  | 1.55 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | MUD MOTOR |  |  | 4.75 | 2.875 |  | 3 1/2 IF |  | 6.89 |  |  | ACT. SYS (BBL) | 1429.2
MW OUT (SG) |  | 1.55 | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MDi616LNBPX |  | ST. STAB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 1.57 |  |  | RESV. SYS (BBL) | 573
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | JM9761 |  | FLOAT SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.82 |  |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 1 X DC |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.29 |  |  | KILL MW (SG)
µ FUNNEL (SEC) |  | 58 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3 x 10 |  | ST. STAB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 1.97 |  |  | TOTAL | 2002.2
PV |  | 30 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4967 |  | PBL SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 3.07 |  |  | DIESEL (LTR)
YIELD POINT |  | 24 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | PONY NMDC |  |  | 4.75 | 2.3125 |  | 3 1/2 IF |  | 4.52 |  |  | RIG TANK | 117572
GEL ST. |  | 11/15 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  | 2 |  | 15 X HWDP's |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 141.59 |  |  | CAMP TANK | 27144
WL (ml/30 min) |  | 5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  | 30-40 |  | D. JAR |  |  | 4.75 | 2.1875 |  | 3 1/2 IF |  | 9.21 |  |  | CONSUMED | 4724
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  | 210 |  | 12 X HWDP's |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 113.14 |  |  | RECEIVED
ALK (MUD) |  | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) |  |  | 3-4 | [12 empty] | TOTAL | 144716
ALK (FILT.) |  | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) |  |  | 7.4074 | [12 empty] | WATER (LTR)
pH |  | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. |  |  | 0.27 | [12 empty] | RIG STORAGE | 610630
MAX SHIELD % |  |  | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 75000
KCl (%) |  | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  | 51.7 | [12 empty] | CONSUMED | 128970
KCl (mg/l) |  | 42519.4 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 139200
CHLORIDES (mg/l) |  | 76000 | JAR | 8.71 | STAB - 1 | 8.71 | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) |  | 200 | 3 1/2" HWDPS | 8.71 | MOTOR | 2.51 | TFA (IN²) |  |  | 0.23 | [12 empty] | POB
PENETRAX % |  |  | PBL SUB | 2.51 | STAB-2 | 8.71 | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 292.27 |  |  | MPCL | 8
MAX GUARD % |  |  | DAILY BHA ROT. HRS |  | 0 |  | MOTOR REV/GAL |  |  | 1.04 |  | BHA WT. IN MUD (TON) | [7 empty] | 8 |  |  | MPCL SERV | 37
SOLIDS % |  | 20.1 | DAILY ON BOTTOM HRS |  | 0 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 5 |  |  | SECURITY
M.B.T. (lb/bbl) |  | 3.8 | DAILY CIRC. HRS |  | 4.5 |  | BIT NO. 32 |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 3
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 27
APPROVED AFE (US$) |  | 25942000 | SHAKER-1 | 2 x 50 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4802 / 4780.44 |  | 35.67 |  | 301.77 |  |  | 4.39 |  | MWD |  | TOTAL | 124
DAILY WELL COST (US$) |  | 46550.845 | SHAKER-2 | 2 X 40 + 1 x 60 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4831 / 4804.02 |  | 37.9 |  | 301.51 |  |  | 2.31 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 25271460.4129 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4866 / 4831.86 |  | 36.7 |  | 304.06 |  |  | 1.68 |  | MWD |  | LAST CSG SIZE | 7''
% OF AFE SPENT |  | 97.42% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | 4895 / 4855.15 |  | 36.46 |  | 301.51 |  |  | 1.59 |  | MWD |  | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | 4923 / 4877.80 |  | 35.58 |  | 299.15 |  |  | 1.76 |  | MWD |  | MAASP (PSI) | 2706
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4889 | 1000/1000 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4889 | 1450/1400 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | SHEAR BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4889 | 1550/1600 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4775/4758.16
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4787 / 4768
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-05-04 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  | 482 |  | MUD LOSSES |  |  |  | 4029 |  | KUSSAK | 4821 / 4796
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-05-18 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4857 / 4825
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-10
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43961 | 43961.0312 | 0.75 | DRL | NPT-UP | STK | MONITERED WELL THRU TRIP TANK. MEANWHILE PREPARED LCM PILL.
43961.0312 | 43961.0521 | 0.5 | DRL | NPT-UP | STK | DROPPED & CHASED DEACTIVATION BALLS TO DEACTIVATE PBL. OBSERVED NO PRESSURE INDICATION OF PBL DEACTIVATION.
43961.0521 | 43961.1562 | 2.5 | DRL | NPT-UP | STK | PUMPED 20 BBL LCM PILL (45 PPB), 20 BBL MUD & 20 BBL LCM PILL (45 PPB). DISPLACED THE LCM PILLS WITH MUD AND NOZZLED OUT.
43961.1562 | 43961.2188 | 1.5 | DRL | NPT-UP | STK | PROVIDED SOAKING TIME TO LCM PILL.
43961.2188 | 43961.2396 | 0.5 | DRL | NPT-UP | STK | CIRCULATED TO MONITOR LOSSES. OBSERVED TOTAL LOSS.
43961.2396 | 43961.2812 | 1 | DRL | NPT-UP | STK | DROPPED SOLID ACTIVATION DART FOR PBL ACTIVATION. OBSERVED INCREASE IN PRESSURE. ATTEMPTED TO INCREASE IN PRESSURE WITH 2000 PSI, 3000 PSI & 3500 PSI, BUT NO SUCCESS.
43961.2812 | 43961.3229 | 1 | DRL | NPT-UP | STK | MONITERED WELL THRU TRIP TANK.
43961.3229 | 43961.3646 | 1 | DRL | NPT-UP | STK | ATTEMPTED TO RESUME CIRCULATION, OBSEREVED TOTAL LOSS.(ANNULUS LEVEL STATIC).
43961.3646 | 43961.7708 | 9.75 | DRL | NPT-UP | STK | PREPARED 500 BBL FRESH MUD MEANWHILE MONITERED WELL THRU TRIP TANK. ATTEMPTED TO RESUME CIRCULATION, OBSEREVED TOTAL LOSS. WORKED ON STRING WITH DOWNWARD & UPWWARD JARRING, BUT NO SUCCESS. LOSSES THROUGH STRING REDUCED, POSSIBILITY OF PLUGGING OF BIT. (STATIC LOSS @ 0.5 BBL/HR)
43961.7708 | 43961.7917 | 0.5 | DRL | NPT-UP | RU | R/U W/L GEARS.
43961.7917 | 43961.9375 | 3.5 | DRL | NPT-UP | W/L | RIH DUMMY TOOL, OBSERVED OBSTRUCTION INSIDE 5" DP STRING AT 283M. ATTEMPTED TO PASS THRU BUT NO SUCCESS.
43961.9375 | 43961.9583 | 0.5 | DRL | NPT-UP | STK | PUMPED 32 BBL MUD TRHOUGH STRING TO CLEAR OBSTRUCTION.
43961.9583 | 43962 | 1 | DRL | NPT-UP | W/L | RIH DUMMY TOOL AGAIN, OBSERVED OBSTRUCTION INSIDE 5" DP STRING AT 283M. POOH W/L TO SURFACE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-11
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43962 | 43962.0208 | 0.5 | DRL | NPT-UP | RD | R/D W/L GEARS.
43962.0208 | 43962.25 | 5.5 | DRL | NPT-UP | WOE | WAIT ON SLICK LINE / COILED TUBING & IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA : SANDSTONE, CLAYSTONE.
OPERATIONS AT 06:00 HRS |  |  | WAIT ON SLICK LINE / COILED TUBING IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | PUMPED LCM PILLS. PROVIDED SOAKING TIME. DROPPED SOLID ACTIVATION DART FOR PBL ACTIVATION. OBSERVED INCREASE IN PRESSURE. ATTEMPTED TO INCREASE IN PRESSURE. BUT NO SUCCESS. OBSERVED TOTAL LOSS. WORKED ON STRING WITH DOWNWARD & UPWWARD JARRING. RIH DUMMY TOOL, OBSERVED OBSTRUCTION INSIDE 5" DP STRING AT 283M. ATTEMPTED TO PASS THRU TWICE BUT NO SUCCESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CLEAR DRILL STRING ID THROUGH SLICK LINE / COILED TUBING.
REMARKS
Formulas:
MIRAJ-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14