## DDR # 375
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 375
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-05-13
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4995 / 4945 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | M. ISHAQ / ADNAN OMER / ADNAN |  |  | MD/TVD @ 00:00HRS: |  | 4969 | 4914.78 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 374.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JEELANI |  |  | MD/TVD @ 06:00HRS: |  | 4969 | 4914.78 | [5 empty] | DAILY PROGRESS @ 00:00HRS:
2020-05-12 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 76 |  | BHA NO. |  |  | 95 | IN (M) |  | 4967 |  | OUT (M) |  |  | STRING (BBL) | 225.3
CHECK TIME |  | 20:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 32RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 659
DEPTH, MD (M) |  | 4969 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 |  |  | PITS (BBL) | 699
MW IN (SG) |  | 1.55 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | MUD MOTOR |  |  | 4.75 | 2.875 |  | 3 1/2 IF |  | 6.89 |  |  | ACT. SYS (BBL) | 1583.3
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MDi616LNBPX |  | ST. STAB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 1.57 |  |  | RESV. SYS (BBL) | 707
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | JM9761 |  | FLOAT SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.82 |  |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 1 X DC |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.29 |  |  | KILL MW (SG)
µ FUNNEL (SEC) |  | 60 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3 x 10 |  | ST. STAB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 1.97 |  |  | TOTAL | 2290.3
PV |  | 28 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4967 |  | PBL SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 3.07 |  |  | DIESEL (LTR)
YIELD POINT |  | 23 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | PONY NMDC |  |  | 4.75 | 2.3125 |  | 3 1/2 IF |  | 4.52 |  |  | RIG TANK | 111726
GEL ST. |  | 11/13 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | 15 X HWDP's |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 141.59 |  |  | CAMP TANK | 25831
WL (ml/30 min) |  | 5.2 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | D. JAR |  |  | 4.75 | 2.1875 |  | 3 1/2 IF |  | 9.21 |  |  | CONSUMED | 2656
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | 12 X HWDP's |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 113.14 |  |  | RECEIVED
ALK (MUD) |  | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 137557
ALK (FILT.) |  | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH |  | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 660025
MAX SHIELD % |  |  | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 72000
KCl (%) |  | 4 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 90835
KCl (mg/l) |  | 41947.4 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 148100
CHLORIDES (mg/l) |  | 76000 | JAR | 8.71 | STAB - 1 | 8.71 | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | 92800
HARDNESS (mg/l) |  | 200 | 3 1/2" HWDPS | 8.71 | MOTOR | 2.51 | TFA (IN²) |  |  | 0.23 | [12 empty] | POB
PENETRAX % |  |  | PBL SUB | 2.51 | STAB-2 | 8.71 | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 292.27 |  |  | MPCL | 9
MAX GUARD % |  |  | DAILY BHA ROT. HRS |  | 0 |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 8 |  |  | MPCL SERV | 50
SOLIDS % |  | 19.04 | DAILY ON BOTTOM HRS |  | 0 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 5 |  |  | SECURITY
M.B.T. (lb/bbl) |  | 3.8 | DAILY CIRC. HRS |  | 0.2 |  | BIT NO. 32 |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 4
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 28
APPROVED AFE (US$) |  | 25942000 | SHAKER-1 | 2 x 40 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4802 / 4780.44 |  | 35.67 |  | 301.77 |  |  | 4.39 |  | MWD |  | TOTAL | 140
DAILY WELL COST (US$) |  | 39397.4167 | SHAKER-2 | 2 x 50 + 1 x 60 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4831 / 4804.02 |  | 37.9 |  | 301.51 |  |  | 2.31 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 25368135.2696 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4866 / 4831.86 |  | 36.7 |  | 304.06 |  |  | 1.68 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 97.79% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | 4895 / 4855.15 |  | 36.46 |  | 301.51 |  |  | 1.59 |  | MWD |  | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | 4923 / 4877.80 |  | 35.58 |  | 299.15 |  |  | 1.76 |  | MWD |  | MAASP (PSI) | 3042.4423
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4889 | 1000/1000 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4889 | 1450/1400 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | SHEAR BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4889 | 1550/1600 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4775/4758.16
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4787 / 4768
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-05-04 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  | 7 |  | MUD LOSSES |  |  |  | 4062 |  | KUSSAK | 4821 / 4796
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-05-18 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4857 / 4825
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-12
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43963 | 43963.0521 | 1.25 | DRL | NPT-UP | WOE | WAIT ON EQUIPMENT (MAGNET).
43963.0521 | 43963.1146 | 1.5 | DRL | NPT-UP | F | HELD PJSM. RIH 2.5" MAGNET ON SLICK LINE & RETRIEVED SOLID PBL ACTIVATION DART.
43963.1146 | 43963.2917 | 4.25 | DRL | NPT-UP | F | RIH 2.5" MAGNET ON SLICK LINE & RETRIEVED PBL DEACTIVATION BALLS. RIH 2.50” OD MAGNET ON SLICKLINE & RETRIEVED 2ND PBL ACTIVATION DART.
43963.2917 | 43963.3333 | 1 | DRL | NPT-UP | F | RIH 2" MAGNET ON SLICK LINE DOWN TO 3156M & POOH TO SURFACE.
43963.3333 | 43963.375 | 1 | DRL | NPT-UP | W/L | RIH 2" GUAGE CUTTER ON SLICK LINE DOWN TO 3156M. TOOL STUCK IN 5"x 3 1/2" DP X-OVER. ATTEMPTED TO RELEASE IT, BUT NO SUCCESS.
43963.375 | 43963.8542 | 11.5 | DRL | NPT-UP | W/L | WORKED ON SLICK LINE INTERMITTENTLY (WITHIN MAXIMUM ALLOWABLE LIMIT) TO RELEASE - NO SUCCESS. MEANWHILE OBSERVED WELL AT TRIP TANK.
43963.8542 | 43963.9167 | 1.5 | DRL | NPT-UP | W/L | HELD PJSM. DROPPED GO DEVIL TOOL & CUT SLICK LINE SUCCESSFULLY ABOVE THE STUCK TOOL. POOH SLICK LINE & R/D SLICK LINE GEARS.
43963.9167 | 43963.9583 | 1 | DRL | NPT-UP | FC | M/U TDS & PUMPED MUD. OBSERVED DYNAMIC LOSS. MONITORED WELL & OBSERVED 1 BBL/HR STATIC LOSS.
43963.9583 | 43964 | 1 | DRL | NPT-UP | WOE | WAIT ON SERVICES (FISHING ENGINEER) FOR MECHANICAL BACK OFF.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-13
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43964 | 43964.25 | 6 | DRL | NPT-UP | WOE | WAIT ON SERVICES (FISHING ENGINEER) FOR MECHANICAL BACK OFF.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA : SANDSTONE, CLAYSTONE.
OPERATIONS AT 06:00 HRS |  |  | WAIT ON SERVICES (FISHING ENGINEER)
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | WAIT ON EQUIPMENT (MAGNET). RETRIEVED 2x DARTS & 2x BALLS WITH 2.5" MAGNET ON SLICK LINE. CONDUCTED 2" MAGNET TRIP WITH SLICK LINE DOWN TO 3156M. RIH 2" GUAGE CUTTER ON SLICK LINE DOWN TO 3156M. TOOL STUCK IN 5"x 3 1/2" DP X-OVER. ATTEMPTED TO RELEASE IT, BUT NO SUCCESS. CUT SLICK LINE ABOVE THE STUCK TOOL & POOH TO SURFACE. OBSERVED DYNAMIC LOSSES & 1 BBL/HR STATIC LOSS. WAIT ON SERVICES (FISHING ENGINEER) FOR MECHANICAL BACK OFF.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | PERFORM MECHANICAL BACK OFF TENTATIVELY AT ± 4000M. POOH DRILL STRING TO SURFACE.
REMARKS
Formulas:
MIRAJ-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14