## DDR#38
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 38
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-06-11
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | IKRAMULLAH / AHSEN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 2377 / 2377 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 37.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 2397 / 2397 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 72
2019-06-10 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 17.5 |  | BIT NO. |  | 4RR2 |  | BHA NO. |  |  | 8 | IN (M) |  | 2305 |  | OUT (M) |  |  | STRING (BBL) | 157
CHECK TIME | 16:00 | 23:59 | MD @ 00:00HR (M) |  | 2377 |  | SIZE (IN) |  | 17.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 2160
DEPTH, MD (M) | 2347 | 2377 | TVD @ 00:00HR (M) |  | 2377 |  | MANUFACTURER |  | NOV |  | PDC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.36 | 0.11629 |  | PITS (BBL) | 882
MW IN (SG) | 2.06 | 2.06 | DAILY PROGRESS (M) |  | 72 |  | TYPE |  | TFH519S |  | BIT SUB (F.V) |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 1.08 | 0.34888 |  | ACT. SYS (BBL) | 3199
MW OUT (SG) | 2.06 | 2.06 | INST. ROP (M/HR) |  | 4.5 |  | SERIAL NO. |  | E260745 |  | STRING STAB |  |  | 17.375 | 3.0625 |  | 7 5/8 REG |  | 2.31 | 0.74622 |  | RESV. SYS (BBL) | 543
ECD (SG) | 2.07 | 2.07 | AVG. ROP (M/HR) |  | 3.95 |  | IADC CODE |  | S422 |  | 1 X 9 1/2" DC |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 9.23 | 2.9816 |  | KILL MUD (BBL) | 1000
FL TEMP. °F | 160 | 163.4 | AVG. WOB (TON) |  | 14 |  | NOZZLES (1/32") |  | 5 X 16 |  | STRING STAB |  |  | 17.375 | 3.1875 |  | 7 5/8 REG |  | 2.36 | 0.76237 |  | KILL MW (SG) | 2.15
µ FUNNEL (SEC) | 70 | 65 | AVG. RPM SURFACE |  | 150 |  | DEPTH IN (M) |  | 2305 |  | 2 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 18.54 | 5.9891 |  | TOTAL | 3742
PV | 41 | 40 | AVG. RPM DOWNHOLE |  | 150 |  | DEPTH OUT (M) |  |  |  | STRING STAB |  |  | 17.375 | 3 |  | 7 5/8 REG |  | 2.19 | 0.70745 |  | DIESEL (LTR)
YIELD POINT | 35 | 35 | FLOWRATE (GPM) |  | 770 - 780 |  | METERAGE (M) |  | 72 |  | 4 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 36.78 | 11.8814 |  | RIG TANK | 52777
GEL ST. | 13/15 | 14/16 | PRESSURE (PSI) |  | 3750 - 3900 |  | RPM SURF. |  | 140 - 150 |  | X/OVER |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.95 | 0.30689 |  | CAMP TANK | 17196
WL (ml/30 min) | 6.8 | 6.7 | TORQ. ON-BTM (KLB-FT) |  | 9 - 14 |  | RPM BTM. |  | 140 - 150 |  | 2 X 8" DCS |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 18.49 | 4.1288 |  | CONSUMED | 12918
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  | 6 - 7 |  | WOB (TON) |  | 12 - 15 |  | DRILLING JAR |  |  | 8 | 2.9375 |  | 6 5/8 REG |  | 9.58 | 2.1392 |  | RECEIVED
ALK (MUD) | 0.2 | 0.3 | STRING WT. (TON) - ROT |  | 132 |  | AVG. ROP (M/HR) |  | 3.9517 |  | 2 X 8" DCS |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.42 | 4.1132 |  | TOTAL | 69973
ALK (FILT.) | 0.3 | 0.4 | PICK-UP WT. (TON) |  | 139 |  | BIT ROT HRS. |  | 18.22 |  | X/OVER |  |  | 7.75 | 2.8125 |  | 5 1/2 FH |  | 0.76 | 0.16971 |  | WATER (LTR)
PH | 9.3 | 9.4 | SLACK-OFF WT. (TON) |  | 125 |  | K-REVS IN 24 HRS |  | 164.13 |  | 10 X 5 1/2" HWDPS |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 94.4 | 8.4486 |  | RIG STORAGE | 470000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 164.13 | [12 empty] | CAMP STORAGE | 80000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 18.1 | [12 empty] | CONSUMED | 95500
KCl (mg/l) | 51862.2 | 51862.2 | JAR | 20.7 | STAB - 1 | 20.7 | JET VELOCITY (M/SEC) |  | 77.56 | [12 empty] | RECEIVED | 94500
CHLORIDES (mg/l) | 25000 | 25000 | 5 1/2" HWDPS | 20.7 | STAB - 2 | 20.7 | TFA (IN²) |  | 0.98 | [12 empty] | TOTAL | 550000
HARDNESS (mg/l) | 420 | 460 | 9 1/2" DCS | 20.7 | STAB - 3 | 20.7 | HSI |  | 1.87 | [12 empty] | POB
SAND % | 0.2 | 0.2 | 8" DCS | 20.7 | SPSA |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | TOTAL LENGTH (M) | [7 empty] | 215.45 |  |  | MPCL | 5
LUBRICANT % | 1 | 1 | BHA ROT. HRS |  | 20.7 |  | BIT NO. 4RR2 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 33 |  |  | MPCL SERV | 23
SOLIDS % | 34.54 | 34.79 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 22 |  |  | SECURITY
M.B.T. (lb/bbl) | 7.5 | 7.5 | CIRC. HRS |  | 20.95 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 45
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 30" CONDUCTOR |  |  | 37 | 1981/1981 |  | 0.11 | [6 empty] | MWD |  | TOTAL | 106
DAILY WELL COST (US$) |  | 43057.23 | SHAKER-2 | 1 X 100 | 2 X 100 |  | 20" SURFACE / K-55, 133# |  |  | 579 | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 3778582.4742 | SHAKER-3 | 1 X 100 | 2 X 100 | [5 empty] | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 18.98% | MUD CLEANER | 3 X 170 | [6 empty] | 2286/2286 |  | 0.75 | [6 empty] | TOTCO |  | LOT (EMW) | 2.16
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 82
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | JX CHINA | 21.25 | 5000 | P-1 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 30 |  | 2372 | 720 / 700 / 720 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JX CHINA | 21.25 | 5000 | P-2 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 40 |  | 2372 | 750 / 750 / 750 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-05-09 | 2019-06-08 | BLIND RAMS | JX CHINA | 21.25 | 5000 | P-3 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 50 |  | 2372 | 800 / 800 / 820 |  |  | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-06-05 | 2019-06-19 | LAST BOP TEST DATE |  | 2019-06-03 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  | 2019-06-17 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-10
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43626 | 43626.125 | 3 | DRL | PT-P | RIH | RIH BIT FROM 1388M TO 2277M ON ELEVATORS. WHILE RIH FILLED UP STRING WITH MUD.
43626.125 | 43626.1458 | 0.5 | DRL | PT-P | RW | PRECAUTIONARY REAMED / WASHED DOWN FROM 2277M TO BTM @ 2305M.
43626.1458 | 43627 | 20.5 | DRL | PT-P | D | DRILLED 17 1/2" HOLE FROM 2305M TO 2377M & ADJUSTED DRILLING PARAMETERS TO OPTIMIZE ROP. REAMED / WASHED DRILLED INTERVAL AT EACH CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-06-11
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43627 | 43627.25 | 6 | DRL | PT-P | D | DRILLED 17 1/2" HOLE FROM 2377M TO 2397M & ADJUSTED DRILLING PARAMETERS TO OPTIMIZE ROP. REAMED / WASHED DRILLED INTERVAL AT CONNECTION.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH BIT FROM 1388M TO BTM @ 2305M. DRILLED 17 1/2" HOLE FROM 2305M TO 2377M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 17 1/2" HOLE.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14