## DDR # 383
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 383
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-05-21
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4995 / 4945 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MUHAMMAD ISHAQ / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4969 | 4914.78 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 382.9792
RIG REP.: |  | JAVED MUGHAL / TARIQ BUTT / KHALID |  |  | MD/TVD @ 06:00HRS: |  | 4969 | 4914.78 | [5 empty] | DAILY PROGRESS @ 00:00HRS:
2020-05-20 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 76 |  | BHA NO. |  |  | 95 | IN (M) |  | 4967 |  | OUT (M) |  |  | STRING (BBL) | 159.8
CHECK TIME | 9:00 | 23:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 32RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 748.6
DEPTH, MD (M) | 4969 | 4969 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 |  |  | PITS (BBL) | 670
MW IN (SG) | 1.57 | 1.57 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | MUD MOTOR |  |  | 4.75 | 2.875 |  | 3 1/2 IF |  | 6.89 |  |  | ACT. SYS (BBL) | 1578.4
MW OUT (SG) | 1.57 |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MDi616LNBPX |  | ST. STAB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 1.57 |  |  | RESV. SYS (BBL) | 508
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | JM4653 |  | FLOAT SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.82 |  |  | KILL MUD (BBL)
FL TEMP. °F | 115 |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 1 X DC |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.29 |  |  | KILL MW (SG)
µ FUNNEL (SEC) | 57 | 66 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3 x 10 |  | ST. STAB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 1.97 |  |  | TOTAL | 2086.4
PV | 32 | 30 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4967 |  | PBL SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 3.07 |  |  | DIESEL (LTR)
YIELD POINT | 25 | 24 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | PONY NMDC |  |  | 4.75 | 2.3125 |  | 3 1/2 IF |  | 4.52 |  |  | RIG TANK | 107610
GEL ST. | 12/15 | 10/14 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | 15 X HWDP's |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 141.59 |  |  | CAMP TANK | 20525
WL (ml/30 min) | 5 | 5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | D. JAR |  |  | 4.75 | 2.1875 |  | 3 1/2 IF |  | 9.21 |  |  | CONSUMED | 4664
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | 12 X HWDP's |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 113.14 |  |  | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 128135
ALK (FILT.) | 0.3/1.1 | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 604400
DIESEL % | 0.8 | 0.8 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 80000
KCl (%) | 4 | 4 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 68624
KCl (mg/l) | 40040.7 | 40040.7 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 31500
CHLORIDES (mg/l) | 74000 | 74000 | JAR | 8.71 | STAB - 1 | 8.71 | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) | 160 | 160 | 3 1/2" HWDPS | 8.71 | MOTOR | 2.51 | TFA (IN²) |  |  | 0.23 | [12 empty] | POB
PENETRAX % |  |  | PBL SUB | 2.51 | STAB-2 | 8.71 | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 292.27 |  |  | MPCL | 8
MAX GUARD % |  |  | DAILY BHA ROT. HRS |  | 0 |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 8 |  |  | MPCL SERV | 27
SOLIDS % | 19.03 | 19.03 | DAILY ON BOTTOM HRS |  | 0 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 5 |  |  | SECURITY
M.B.T. (lb/bbl) | 3.8 | 3.8 | DAILY CIRC. HRS |  | 15.95 |  | BIT NO. 32 |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 59
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 12
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 25942000 | SHAKER-1 | 2 x 40 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4802 / 4780.44 |  | 35.67 |  | 301.77 |  |  | 4.39 |  | MWD |  | TOTAL | 132
DAILY WELL COST (US$) |  | 64559.9112 | SHAKER-2 | 2 x 50 + 1 x 60 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4831 / 4804.02 |  | 37.9 |  | 301.51 |  |  | 2.31 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 26125315.0453 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4866 / 4831.86 |  | 36.7 |  | 304.06 |  |  | 1.68 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 100.7% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | 4895 / 4855.15 |  | 36.46 |  | 301.51 |  |  | 1.59 |  | MWD |  | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | 4923 / 4877.80 |  | 35.58 |  | 299.15 |  |  | 1.76 |  | MWD |  | MAASP (PSI) | 2907.2226
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4889 | 1000/1000 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4889 | 1450/1400 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | SHEAR BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4889 | 1550/1600 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4775/4758.16
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4787 / 4768
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-05-04 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 4062 |  | KUSSAK | 4821 / 4796
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-05-25 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4857 / 4825
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-20
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43971 | 43971.5833 | 14 | DRL | NPT-UP | STK | CONT'D CIRCULATION. PRESSURE DROPPED FROM 2600 PSI TO 2400 PSI GRADUALLY AT 290 GPM. MEANWHILE WORKED ON STRING WITH INTERMITTENT JARRING UPWARD (240 TON) / DOWNWARD (100 TON) & TORQUE (11 KFT-LB), NO SUCCESS.
43971.5833 | 43971.6042 | 0.5 | DRL | NPT-P | RS | CONDUCTED POST JARRING TDS INSPECTION & SERVICED TDS.
43971.6042 | 43971.625 | 0.5 | DRL | NPT-UP | RU | R/U WIRELINE GEARS FOR COLLOIDAL JOB.
43971.625 | 43971.7604 | 3.25 | DRL | NPT-UP | W/L | HELD PJSM. OBSERVED COMPLETE RADIO SILENCE & ARMED THE COLLOIDAL TOOL. RIH COLLOIDAL TOOL (TYPE-2), CORRELATED & FIRED AT 4808.6M (TOOL JOINT). WORKED ON STRING 175 TON UP / 135 TON DOWN & 10 KFT-LB TORQUE; STRING SEVERED SUCCESSFULLY. POOH W/L TO SURFACE.
43971.7604 | 43971.8021 | 1 | DRL | NPT-UP | RD | R/D WIRELINE GEARS.
43971.8021 | 43971.8646 | 1.5 | DRL | NPT-UP | CIR | CIRCULATED AT TOP OF FISH TO CONDITION & HOMOGENIZE MUD.
43971.8646 | 43971.875 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED, WELL STATIC.
43971.875 | 43972 | 3 | DRL | NPT-UP | POOH | POOH DRL STRING FROM 4808M TO 3870M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-21
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43972 | 43972.0417 | 1 | DRL | NPT-UP | POOH | CONT'D POOH DRL STRING FROM 3870M TO 3528M.
43972.0417 | 43972.0833 | 1 | DRL | NPT-P | RS | CUT & SLIPPED 90 FT DRILL LINE. ADJUSTED CROWN-O-MATIC & RESET ACS.
43972.0833 | 43972.25 | 4 | DRL | NPT-UP | POOH | POOH DRL STRING FROM 3528M TO 2000M & IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA : SANDSTONE, CLAYSTONE.
OPERATIONS AT 06:00 HRS |  |  | POOH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CIRCULATED AT 290 GPM & WORKED ON STRING WITH INTERMITTENT JARRING UPWARD (240 TON) / DOWNWARD (100 TON) & TORQUE (11 KFT-LB), NO SUCCESS. SEVERED THE STRING WITH COLLOIDAL TOOL AT 4808.6M (TOOL JOINT). WORKED ON STRING 175 TON UP / 135 TON DOWN & 10 KFT-LB TORQUE; STRING SEVERED SUCCESSFULLY. POOH W/L TO SURFACE. CIRCULATED AT TOF & POOH DRL STRING FROM 4808M TO 3870M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE. L/D 3 1/2" HWDP FOR INSPECTION. PERFORM CONDITION TRIP WITH 6" BIT PRIOR CEMENT PLUG JOB.
REMARKS
Formulas:
MIRAJ-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14+7
Note on F38: CMan.Rig3: Thru severed HWDP