## DDR # 384
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 384
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-05-22
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4995 / 4945 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MUHAMMAD ISHAQ / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4969 | 4914.78 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 383.9792
RIG REP.: |  | TARIQ BUTT / KHALID JEELANI |  |  | MD/TVD @ 06:00HRS: |  | 4969 | 4914.78 | [5 empty] | DAILY PROGRESS @ 00:00HRS:
2020-05-21 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 77 |  | BHA NO. |  |  | 96 | IN (M) |  | 4969 |  | OUT (M) |  |  | STRING (BBL) | 104.5
CHECK TIME |  | 21:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 30 RR2 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 828.7
DEPTH, MD (M) |  | 4969 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 | 0.02 |  | PITS (BBL) | 626
MW IN (SG) |  | 1.57 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | BIT SUB |  |  | 4.75 | 2 |  | 3 1/2 IF |  | 1.07 | 0.037088 |  | ACT. SYS (BBL) | 1559.2
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MDSi613 |  | 9 x HWDP |  |  | 3.5 | 2.0625 |  | 3 1/2 IF |  | 83.65 | 2.8994 |  | RESV. SYS (BBL) | 502
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | QF3438 |  | HMD JAR |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 4.72 | 0.1636 |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 6 x HWDP |  |  | 3.5 | 2.0625 |  | 3 1/2 IF |  | 55.97 | 1.94 |  | KILL MW (SG)
µ FUNNEL (SEC) |  | 68 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3 x OPEN JETS | [12 empty] | TOTAL | 2061.2
PV |  | 31 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4969 | [12 empty] | DIESEL (LTR)
YIELD POINT |  | 25 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 104753
GEL ST. |  | 12/16 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 19893
WL (ml/30 min) |  | 5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 3489
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) |  | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 124646
ALK (FILT.) |  | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH |  | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 593025
DIESEL % |  | 0.8 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 78000
KCl (%) |  | 4 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [15 empty] | CONSUMED | 44875
KCl (mg/l) |  | 40040.7 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 31500
CHLORIDES (mg/l) |  | 74000 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | 92800
HARDNESS (mg/l) |  | 160 | 3 1/2" HWDPS |  | MOTOR |  | TFA (IN²) | [15 empty] | POB
PENETRAX % |  |  | PBL SUB |  | STAB-2 |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 145.61 |  |  | MPCL | 4
MAX GUARD % |  |  | DAILY BHA ROT. HRS |  | 0 |  | MOTOR REV/GAL |  |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 4 |  |  | MPCL SERV | 20
SOLIDS % |  | 19.03 | DAILY ON BOTTOM HRS |  | 0 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 2.5 |  |  | SECURITY
M.B.T. (lb/bbl) |  | 3.8 | DAILY CIRC. HRS |  | 0.17 |  | BIT NO. 30 RR2 |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 25942000 | SHAKER-1 | 2 x 40 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4802 / 4780.44 |  | 35.67 |  | 301.77 |  |  | 4.39 |  | MWD |  | TOTAL | 115
DAILY WELL COST (US$) |  | 31036 | SHAKER-2 | 2 x 50 + 1 x 60 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4831 / 4804.02 |  | 37.9 |  | 301.51 |  |  | 2.31 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 26161010.0933 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4866 / 4831.86 |  | 36.7 |  | 304.06 |  |  | 1.68 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 100.8% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | 4895 / 4855.15 |  | 36.46 |  | 301.51 |  |  | 1.59 |  | MWD |  | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | 4923 / 4877.80 |  | 35.58 |  | 299.15 |  |  | 1.76 |  | MWD |  | MAASP (PSI) | 2907.2226
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.65 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4889 | 1000/1000 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4889 | 1450/1400 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | SHEAR BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4889 | 1550/1600 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4775/4758.16
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4787 / 4768
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-05-04 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 4062 |  | KUSSAK | 4821 / 4796
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-05-25 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4857 / 4825
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-21
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43972 | 43972.0417 | 1 | DRL | NPT-UP | POOH | CONT'D POOH DRL STRING FROM 3870M TO 3528M.
43972.0417 | 43972.0833 | 1 | DRL | NPT-P | RS | CUT & SLIPPED 90 FT DRILL LINE. ADJUSTED CROWN-O-MATIC & RESET ACS.
43972.0833 | 43972.4792 | 9.5 | DRL | NPT-UP | POOH | POOH DRL STRING FROM 3528M TO 131M (BHA TOP). WHILE POOH, L/D SKIRTED SCRW IN SUB & 1x 3 1/2" DP.
43972.4792 | 43972.4896 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED, WELL STATIC.
43972.4896 | 43972.5417 | 1.25 | DRL | NPT-UP | BHA | POOH BHA TO SURFACE. WHILE POOH, L/D 12x 3 1/2" HWDP & JAR FOR INSPECTION & 1x 3 1/2" HWDP WITH DAMAGED PIN.
43972.5417 | 43972.6146 | 1.75 | DRL | NPT-UP | BHA | P/U & M/U RR 6" PDC BIT & RIH WITH SLICK BHA FOR CONDITION TRIP PRIOR CEMENT PLUG DOWN TO 145M. WHILE RIH, P/U INSPECTED 15x 3 1/2" HWDP & JAR. FLUSHED BHA.
43972.6146 | 43972.9271 | 7.5 | DRL | NPT-UP | RIH | RIH FROM 145M TO 2009M. WHILE RIH, DRIFTED 3 1/2" DP STRING & TORQUED UP EACH CONNECTION.
43972.9271 | 43972.9375 | 0.25 | DRL | NPT-UP | CIR | BROKE CIRCULATION.
43972.9375 | 43973 | 1.5 | DRL | NPT-UP | RIH | RIH FROM 2009M TO 2703M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-22
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43973 | 43973.2083 | 5 | DRL | NPT-UP | RIH | CONT'D RIH FROM 2703M TO 4707M.
43973.2083 | 43973.25 | 1 | DRL | NPT-UP | RW | WASHED / REAMED DOWN FROM 4707M TO 4808M. TAGGED TOP OF FISH AT 4808M. CIRCULATION IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA : SANDSTONE, CLAYSTONE.
OPERATIONS AT 06:00 HRS |  |  | CIRCULATION IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH DRL STRING FROM 3870M TO SURFACE. L/D BHA FOR INSPECTION. RIH RR 6" PDC BIT WITH INSPECTED SLICK BHA FOR CONDITION TRIP PRIOR CEMENT PLUG DOWN TO 2703M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CIRCULATE BOTTOMS UP & POOH TO SURFACE. RIH WITH OEDP FOR CEMENT PLUG JOB.
REMARKS |  |  | 160.5M FISH LIH (6" PDC BIT + MUD MOTOR + ST. STAB + FLOAT SUB + 4 3/4" DC + ST. STAB + PBL SUB + 4 3/4" PONY NMDC + 14x 3 1/2" HWDP)
Formulas:
MIRAJ-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14+7