## DDR # 386
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [14 empty] | Report No. |  | 386
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-05-24
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4995 / 4945 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MUHAMMAD ISHAQ / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: | [7 empty] | DAYS SINCE SPUD: | [6 empty] | 385.9792
RIG REP.: |  | TARIQ BUTT / KHALID JEELANI |  |  | MD/TVD @ 06:00HRS: | [7 empty] | DAILY PROGRESS @ 00:00HRS:
2020-05-23 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 49.6
CHECK TIME | 9:00 | 19:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 905.9
DEPTH, MD (M) | 4969 | 4969 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) | [14 empty] | PITS (BBL) | 473
MW IN (SG) | 1.6 | 1.6 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER | [14 empty] | ACT. SYS (BBL) | 1428.5
MW OUT (SG) | 1.6 |  | INST. ROP (M/HR) |  |  |  | TYPE | [14 empty] | RESV. SYS (BBL) | 491
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. | [14 empty] | KILL MUD (BBL)
FL TEMP. °F | 112 |  | AVG. WOB (TON) |  |  |  | IADC CODE | [14 empty] | KILL MW (SG)
µ FUNNEL (SEC) | 57 | 64 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") | [14 empty] | TOTAL | 1919.5
PV | 31 | 31 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [14 empty] | DIESEL (LTR)
YIELD POINT | 22 | 23 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [14 empty] | RIG TANK | 122811
GEL ST. | 9/12 | 10/14 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [14 empty] | CAMP TANK | 18704
WL (ml/30 min) | 5.2 | 5.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [14 empty] | CONSUMED | 5211
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | RECEIVED
ALK (MUD) | 0.4 | 0.6 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [14 empty] | TOTAL | 141515
ALK (FILT.) | 0.3/1 | 0.4/1.3 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [14 empty] | WATER (LTR)
pH | 10 | 10.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | RIG STORAGE | 629150
DIESEL % | 0.8 | 0.6 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [14 empty] | CAMP STORAGE | 85000
KCl (%) | 4 | 4 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CONSUMED | 87300
KCl (mg/l) | 36468.7 | 39087.3 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | RECEIVED | 169300
CHLORIDES (mg/l) | 73800 | 73000 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | DRL WASTE | 46400
HARDNESS (mg/l) | 160 | 200 | 3 1/2" HWDPS |  | MOTOR |  | TFA (IN²) | [14 empty] | POB
PENETRAX % |  |  | PBL SUB |  | STAB-2 |  | HSI |  |  |  | TOTAL LENGTH (M) | [7 empty] | 0 |  |  | MPCL | 5
MAX GUARD % |  |  | DAILY BHA ROT. HRS |  | 0 |  | MOTOR REV/GAL |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 0 |  |  | MPCL SERV | 19
SOLIDS % | 19.14 | 19.04 | DAILY ON BOTTOM HRS |  | 0 |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 0 |  |  | SECURITY
M.B.T. (lb/bbl) | 3.8 | 3.8 | DAILY CIRC. HRS |  | 7.7 |  | BIT NO. 30 RR2 |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 46
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 25942000 | SHAKER-1 | 2 x 40 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  | 579 | [11 empty] | TOTAL | 106
DAILY WELL COST (US$) |  | 35786.0508 | SHAKER-2 | 2 x 50 + 1 x 60 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  | 2419 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 26228513.4041 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  | 4549 / 4391 (WND) | [11 empty] | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 101.1% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  | 4815 / 3397 (TOL) | [11 empty] | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  | 4759 (WND) | [11 empty] | MAASP (PSI) | 2704.3931
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (1.57 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4803 | 1080/1080 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4803 | 1300/1300 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | SHEAR BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4803 | 1650/1650 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4775/4758.16
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4787 / 4768
TRIP DRILL | 2020-03-03 | 2020-04-02 | LAST BOP TEST DATE |  | 2020-05-04 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK | 4821 / 4796
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-05-25 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4857 / 4825
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-23
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43974 | 43974.3021 | 7.25 | DRL | NPT-UP | RIH | CONT'D RIH OEDP WITH 5" DP STRING DOWN TO 4780M, WASHED DOWN LAST STAND DOWN TO 4807M. WHILE RIH, BROKE CIRCULATION AT 2000M.
43974.3021 | 43974.4688 | 4 | DRL | NPT-UP | CIR | CIRCULATED TO CONDITION MUD AT 336 GPM & 2800 PSI. (MEANWHILE HELD PJSM, R/U CEMENT LINE AT RIG FLOOR & P/T AT 5000 PSI. PREPARED & WEIGHT UP BATCH MIXED CEMENT SLURRY).
43974.4688 | 43974.5417 | 1.75 | DRL | NPT-UP | CMT | H/U CIRC SWAGE. PUMPED 35 BBL LOW RHEOLOGY MUD @ 5 BPM WITH RIG PUMP. SWITCHED TO CEMENT UNIT; PUMPED 45 BBL 15 PPG MUDPUSH II SPACER @ 5 BPM. DROPPED SOAKED FOAM BALL, PUMPED 5 BBL 17.8 PPG NEAT CEMENT SLURRY & 20 BBL 17.8 PPG DURASTONE SLURRY @ 4 BPM, DROPPED SOAKED FOAM BALL. DISPLACED CEMENT WITH 15 BBL 15 PPG MUDPUSH II SPACER FOLLOWED BY 176 BBL MUD @ 5 BPM & LAST 10 BBL MUD @ 2 BPM - TOTAL DISPLACEMENT = 201 BBL. INITIAL / FINAL PUMPING PRESSURES = 1300 / 1800 PSI RESPECTIVELY. R/D CIRC SWAGE.
43974.5417 | 43974.5625 | 0.5 | DRL | NPT-UP | POOH | POOH SLOWLY FROM 4807M TO 4745M.
43974.5625 | 43974.6979 | 3.25 | DRL | NPT-UP | CIR | CIRCULATED TO CLEAN HOLE. DUMPED 136 BBL CONTAMINATED MUD, SPACER & CEMENT AT SURFACE.
43974.6979 | 43974.7083 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED, WELL STATIC.
43974.7083 | 43975 | 7 | DRL | NPT-UP | POOH | POOH FROM 4745M TO 1723M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-24
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43975 | 43975.1458 | 3.5 | DRL | NPT-UP | POOH | CONT'D POOH FROM 1723M TO SURFACE.
43975.1458 | 43975.1667 | 0.5 | DRL | NPT-UP | WB | M/U COMBINATION TOOL ASSY & RETRIEVED WEAR BUSHING.
43975.1667 | 43975.25 | 2 | DRL | NPT-UP | BOPT | BOP PRESSURE TEST IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | BOP PRESSURE TEST IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH OEDP STRING DOWN TO 4807M. CIRCULATED TO CONDITION MUD. PLACED DURASTONE CEMENT PLUG AS PER PROGRAM. POOH TO 4745M & CIRCULATED TO CLEAN HOLE. POOH TO 1723M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONDUCT BOP PRESSURE TEST. RIH RR 6" TCI BIT WITH SLICK BHA & DRESS CEMENT PLUG.
REMARKS
Formulas:
MIRAJ-1-ST-2 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14+7
Note on F38: CMan.Rig3: OEDP