## DDR # 387
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [14 empty] | Report No. |  | 387
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-2 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-05-25
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4995 / 4945 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MUHAMMAD ISHAQ / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: | [7 empty] | DAYS SINCE SPUD: | [6 empty] | 386.9792
RIG REP.: |  | TARIQ BUTT / KHALID JEELANI |  |  | MD/TVD @ 06:00HRS: | [7 empty] | DAILY PROGRESS @ 00:00HRS:
2020-05-24 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  | 78 |  | BHA NO. |  |  | 97 | IN (M) |  | 4969 |  | OUT (M) | 4969 |  | STRING (BBL) | 215.4
CHECK TIME | 9:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  | 29 RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 673.9
DEPTH, MD (M) | 4969 | 4969 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 6 |  | TCI BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.18 | 0.02 |  | PITS (BBL) | 554
MW IN (SG) | 1.6 | 1.6 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  | SMITH |  | BIT SUB |  |  | 4.75 | 2 |  | 3 1/2 IF |  | 1.07 | 0.037088 |  | ACT. SYS (BBL) | 1443.3
MW OUT (SG) |  | 1.6 | INST. ROP (M/HR) |  |  |  | TYPE |  | XR50YOD1PD |  | 15 x HWDP |  |  | 3.5 | 2.0625 |  | 3 1/2 IF |  | 139.62 | 4.8394 |  | RESV. SYS (BBL) | 451
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  | RJ5617 |  | HMD JAR |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.07 | 0.31438 |  | KILL MUD (BBL)
FL TEMP. °F |  | 110 | AVG. WOB (TON) |  |  |  | IADC CODE |  | 637 |  | 12 x HWDP |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 113.2 | 3.9237 |  | KILL MW (SG)
µ FUNNEL (SEC) | 67 | 75 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  | 3 x OPEN JETS | [12 empty] | TOTAL | 1894.3
PV | 32 | 33 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  | 4969 | [12 empty] | DIESEL (LTR)
YIELD POINT | 23 | 25 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  | 4969 | [12 empty] | RIG TANK | 119524
GEL ST. | 11/15 | 13/16 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [14 empty] | CAMP TANK | 18069
WL (ml/30 min) | 5.5 | 5.6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [14 empty] | CONSUMED | 3922
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | RECEIVED
ALK (MUD) | 0.6 | 0.6 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [14 empty] | TOTAL | 137593
ALK (FILT.) | 0.4/1.3 | 0.4/1.3 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [14 empty] | WATER (LTR)
pH | 10.5 | 10.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | RIG STORAGE | 635900
DIESEL % | 0.6 | 0.6 | SLIMPULSE D & I OFF BIT - (M) |  |  |  | K-REVS IN 24 HRS | [14 empty] | CAMP STORAGE | 83000
KCl (%) | 4 | 4 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CONSUMED | 65500
KCl (mg/l) | 39087.3 | 39087.3 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | RECEIVED | 73500
CHLORIDES (mg/l) | 73000 | 73000 | JAR | 3.06 | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | DRL WASTE
HARDNESS (mg/l) | 200 | 250 | 3 1/2" HWDPS | 5.52 | MOTOR |  | TFA (IN²) | [14 empty] | POB
PENETRAX % |  |  | PBL SUB |  | STAB-2 |  | HSI |  |  |  | TOTAL LENGTH (M) | [7 empty] | 263.14 |  |  | MPCL | 5
MAX GUARD % |  |  | DAILY BHA ROT. HRS |  | 3.06 |  | MOTOR REV/GAL |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 8 |  |  | MPCL SERV | 19
SOLIDS % | 19.49 | 19.49 | DAILY ON BOTTOM HRS |  | 0 |  | DULL CODE |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 4 |  |  | SECURITY
M.B.T. (lb/bbl) | 3.8 | 3.8 | DAILY CIRC. HRS |  | 2.48 |  | BIT NO. 29 RR |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 46
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 25942000 | SHAKER-1 | 2 x 40 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  | 579 | [11 empty] | TOTAL | 106
DAILY WELL COST (US$) |  | 32828.0625 | SHAKER-2 | 2 x 50 + 1 x 60 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  | 2419 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 26261341.4666 | SHAKER-3 | 3 x 140 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  | 4549 / 4391 (WND) | [11 empty] | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 101.2% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  | 4815 / 3397 (TOL) | [11 empty] | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  | 4759 (WND) | [11 empty] | MAASP (PSI) | 2704.3931
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (1.57 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4803 | 1080/1080 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4803 | 1300/1300 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | SHEAR BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4803 | 1650/1650 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4775/4758.16
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4787 / 4768
TRIP DRILL | 2020-05-24 | 2020-06-23 | LAST BOP TEST DATE |  | 2020-05-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK | 4821 / 4796
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-06-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4857 / 4825
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-24
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43975 | 43975.1458 | 3.5 | DRL | NPT-UP | POOH | CONT'D POOH FROM 1723M TO SURFACE.
43975.1458 | 43975.1667 | 0.5 | DRL | NPT-UP | WB | M/U COMBINATION TOOL ASSY & RETRIEVED WEAR BUSHING.
43975.1667 | 43975.3125 | 3.5 | DRL | NPT-UP | BOPT | M/U TEST PLUG ASSEMBLY, SET TEST PLUG INSIDE 11'' THS ALONG WITH 2x 5" DP STDS BELOW. FLUSHED BOP STACK WITH WATER. P/T ANNULAR BOP @ 500/4500 PSI FOR 5/10 MIN - OK. P/T ROTARY HOSE & STANDPIPE MANIFOLD @ 500/6000 PSI FOR 5/10 MIN - OK. P/T UPPER VARIABLE PIPE RAMS (2 7/8" - 5"), LOWER PIPE RAMS, BLIND RAMS, HYD & MANUAL IBOP, FOSV, HCR & MANUAL VALVES @ KILL & CHOKE LINE, NRV AT KILL LINE, CHOKE MANIFOLD MASTER VALVE, CO-FLEXIP HOSE @ 500/9000 PSI FOR 5/10 MIN - OK. L/D TEST PLUG ASSEMBLY. P/T OFFLINE GREY VALVE & CHOKE MANIFOLD VALVES AT 500/9000 PSI FOR 5/10 MIN - OK.
43975.3125 | 43975.3333 | 0.5 | DRL | NPT-UP | WB | M/U COMBINATION TOOL ASSY & INSTALLED WEAR BUSHING. L/D TOOL ASSY.
43975.3333 | 43975.4167 | 2 | DRL | NPT-UP | BHA | P/U & M/U RR 6" TCI BIT WITH SLICK BHA DOWN TO 263M. WHILE RIH, DRIFTED & P/U 12x 3 1/2" INSPECTED HWDP FROM CATWALK. FLUSHED BHA.
43975.4167 | 43975.875 | 11 | DRL | NPT-UP | RIH | CONT'D RIH FROM 263M TO 4715M. FILLED STRING EVERY 15 STANDS. BROKE CIRCULATION AT 2040M.
43975.875 | 43976 | 3 | DRL | NPT-UP | DC | WASHED DOWN FROM 4715M TO 4735M. TAGGED AT 4735M. WASHED DOWN SOFT CEMENT FROM 4735M TO 4739M WITH 108 GPM & 1100 PSI. CLEARED SOFT CEMENT DOWN TO 4749M WITH ROTATION AT 40 RPM, 0-1 WOB, 250 GPM & 2600 PSI. DRILLED HARD CEMENT FROM 4749M DOWN TO 4760M AT 50 RPM, 2-3 WOB, 250 GPM & 2600 PSI.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-25
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43976 | 43976.1458 | 3.5 | DRL | NPT-UP | DC | ENCOUNTERED ERRATIC TORQUE FROM 4760M TO 4760.5M. CLEARED THE SPOT WITH LOW WOB & ENSURED TWICE BY RECIPROCATION THRU WINDOW - OK. CONT'D DRILLING CEMENT DOWN TO 4763M. OBSERVED LOW ROP. DECIDED TO POOH.
43976.1458 | 43976.1562 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED, WELL STATIC.
43976.1562 | 43976.25 | 2.25 | DRL | NPT-UP | POOH | POOH FROM 4763M TO 3825M & IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | POOH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D POOH FROM 1723M TO SURFACE. CONDUCTED PERIODIC BOP PRESSURE TEST. RIH RR 6" TCI BIT WITH SLICK BHA DOWN TO 4735M. WASHED / DRILLED CEMENT FROM 4735M TO 4760M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE. RIH WITH DIRECTIONAL BHA FOR SIDE TRACK.
REMARKS |  |  | CONDUCTED TRIP DRILL. INSTALLED & CLOSED FOSV IN 30 SEC.
Formulas:
MIRAJ-1-ST-2 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14
Note on F38: CMan.Rig3: Dressing Cement