## DDR#39
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 39
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-01-29
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | SAIFULLAH TURK / HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 2355 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 38.5833
RIG REP.: |  | SARDAR NAEEM / IMRAN JAWAD |  |  | MD/TVD @ 06:00HRS: |  | 2355 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2018-01-28 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 17.5 |  | BIT No. |  | 3RR3 | 3RR1 | BHA No. |  |  | 7 | IN (M) |  | 2355 |  | OUT (M) |  |  | STRING (BBL) | 0
CHECK TIME |  | 23:59 | MD @ 00:00HR (M) |  | 2355 |  | SIZE (IN) |  | 17.5 | 17.5 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 2330
DEPTH, MD (M) |  | 2355 | TVD @ 00:00HR (M) |  | 2355 |  | MANUFACTURER |  | NOV | NOV | 17 1/2" PDC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.36 | 0.35 |  | PITS (BBL) | 713
MW IN (SG) |  | 1.52 | DAILY PROGRESS (M) |  |  |  | TYPE |  | TFH519 | TFH519 | BIT SUB |  |  |  | 7.85 |  | 7 5/8 REG |  | 1.07 | 2.9 |  | ACT. SYS (BBL) | 3043
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | E244694 | E244694 | 1 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 9.23 | 0.2 |  | RESV. SYS (BBL) | 232
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | S422 | S422 | STRING STAB |  |  | 17.375 | 3.125 |  | 7 5/8 REG |  | 2.44 | 0.8 |  | KILL MUD (BBL) | 400
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 5 X 18/32" | 5X18/32" | 1 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 9.22 | 0.2 |  | KILL MW (SG) | 1.8
µ FUNNEL (SEC) |  | 62 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 2355 | 1654 | STRING STAB |  |  | 17.375 | 3.0625 |  | 7 5/8 REG |  | 2.15 | 2.7 |  | TOTAL | 3675
PV |  | 33 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 1 X 9 1/2" DCS |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 9.23 | 0.1 |  | DIESEL (LTR)
YIELD POINT |  | 29 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | STRING STAB |  |  | 17.375 | 3.125 |  | 7 5/8 REG |  | 2.36 | 2.4 |  | RIG TANK | 112000
GEL ST. |  | 9/33 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | X/O |  |  | 9.375 | 3 |  | 6 5/8 REG |  | 0.94 | 0.30366 |  | CAMP TANK | 24500
WL (ml/30 min.) |  | 4.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 6 X 8'' DC'S |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 55.68 | 17.9868 |  | CONSUMED | 4500
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | D.JAR |  |  | 8 | 3.25 |  | 6 5/8 REG |  | 5.15 | 1.6636 |  | RECEIVED
ALK (MUD) |  | 0.8 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  |  |  | 3 X 8'' DC'S |  |  | 8 | 2.875 |  | 6 5/8 REG |  | 27.76 | 8.9676 |  | TOTAL | 136500
ALK (FILT.) |  | 0.6 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. |  |  |  | X/O |  |  | 8.25 | 3 |  | 6 5/8 REG |  | 0.9 | 0.20097 |  | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  |  |  | 6 X 5'' HWDP |  |  | 5 | 3 |  | 6 5/8 REG |  | 56.25 | 12.5605 |  | RIG STORAGE | 360000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 100000
KCl (mg/l) |  | 53387.6 | JAR | 94.27 | NMDC |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 91160
CHLORIDES |  | 25000 | 5" HWDPS | 94.27 | STAB - 1 | 94.27 | TFA (IN²) |  | 1.24 | [12 empty] | TOTAL | 400000
CALCIUM |  | 160 | 8" DCS | 94.27 | STAB - 2 & 3 | 0 | HSI | [14 empty] | POB
OIL% |  | 2 | 9 1/2" DCS | 94.27 | SPSA |  | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 182.74 |  |  | MPCL | 3
DIESEL % |  | 2 | BHA ROT. HRS |  | 94.27 |  | BIT No. 3RR2 |  | 2/3/WT/T,S/IN/ER/TD |  | BHA WT. IN MUD (TON) | [7 empty] | 27 |  |  | MPCL SERV | 32
SOLIDS % |  | 16.82 | ON BOTTOM HRS |  | 99.43 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 20 |  |  | SECURITY | 5
M.B.T. |  | 10 | CIRC. HRS |  | 124.42 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 52
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 20" SURFACE CASING |  |  | 594 | 2248 |  | 2.52 |  | 109.3 |  |  | 0.23 |  | MWD |  | TOTAL | 126
DAILY WELL COST (US$) |  | 32003 | SHAKER-2 | 2 X 120 | 1 X 120 |  | 13 3/8" INTERMEDIATE CSG |  |  |  | 2277 |  | 2.47 |  | 105.15 |  |  | 0.19 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 3662649 | SHAKER-3 | 1 X 100 | 2 X 80 |  | 9 5/8" PRODUCTION CSG |  |  |  | 2304 |  | 2.84 |  | 111.01 |  |  | 0.51 |  | MWD |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 20.29% | MUD CLEANER | 3 X 170 |  |  | 7" LINER |  |  |  | 2335 |  | 3.34 |  | 105.62 |  |  | 0.56 |  | MWD |  | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | 0 | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 236
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-01-09 | 2018-01-23 | ANNULAR | RONGSHENG | 20.75 | 3000 | P-1 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | RONGSHENG | 20.75 | 3000 | P-2 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 2355 |  | 180 / 265 |  | CHINJI | 342
FIRE DRILL | 2018-01-03 | 2018-01-17 | BLIND RAMS | RONGSHENG | 20.75 | 3000 | P-3 - F-1600HL | 6 " |  | 12" | 4200 PSI | 97% |  | 0.101 |  | 30 / 40 |  | 2355 |  | 175 / 263 |  | KAMLIAL | 1255
PIT DRILL | 2018-01-16 | 2018-01-30 | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-01-09 | 2018-01-23 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-01-21 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-01-03 | 2018-01-17 | NEXT BOP TEST DATE |  | 2018-02-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-01-28
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43128 | 43128.0521 | 1.25 | DRL | PT-P | CIR | CONT'D CIRCULATING HOLE TILL SHAKERS CLEANED.
43128.0521 | 43128.0625 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43128.0625 | 43128.3542 | 7 | DRL | PT-P | POOH | POOH FROM 2355 M TO 587 M. HOLE CONDITION, GOOD.
43128.3542 | 43128.3646 | 0.25 | DRL | PT-P | FC | FLOW CHECKED. WELL STATIC. PUMPED SLUG.
43128.3646 | 43128.4062 | 1 | DRL | PT-P | POOH | POOH UP TO BHA.
43128.4062 | 43128.4167 | 0.25 | DRL | PT-P | FC | FLOW CHECKED. WELL STATIC.
43128.4167 | 43128.4583 | 1 | DRL | PT-P | BHA | POOH UP TO DIR BHA.
43128.4583 | 43128.5312 | 1.75 | DRL | PT-P | BHA | PJSM. L/DOWN DIR BHA (MUD MOTOR + MWD TOOLS) & BIT.
43128.5312 | 43128.6562 | 3 | DRL | PT-P | RU | PJSM. R/UP SHOOTING NIPPLE & W/LINE BOP. PRESSURE TESTED @ 400 PSI.OK
43128.6562 | 43128.9583 | 7.25 | DRL | PT-P | W/L | R/UP SCHL W/LINE LOGGING TOOLS. CONDUCTED W/LINE LOG (RUN #1: BHC-LDL-PPC-GR).
43128.9583 | 43129 | 1 | DRL | PT-P | RD | R/DOWN SCHL W/LINE TOOLS + GEARS + W/LINE BOP & SHOOTING NIPPLE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-01-29
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43129 | 43129.125 | 3 | DRL | PT-P | BHA | P/UP AND M/UP RR PDC BIT + CONDITION BHA (STAB POSITION: 30', 60' AND 90') AND RIH TO 182 M. WHILE RIH P/UP (3 X STABS +JAR +5 X 8'' DC'S FROM GROUND).
43129.125 | 43129.25 | 3 | DRL | PT-P | RIH | CONT'D RIH FROM 182 M TO 1178 M. RIH IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE (CLAYSTONE, SANDSTONE)
OPERATIONS AT 06:00 HRS |  |  | RIH IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CIRCULATION TILL SHAKERS CLEANED, POOH TO SURFACE, L/DOWN SLB PERFORMANCE ASSY, PERFORMED W/LINE LOGGING.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONDITION TRIP PRIOR TO 13 3/8'' CSG.
REMARKS |  |  | SCHL D&M TOOLS + CREW RELEASED. WFD TRS CREW + EQP ON LOCATION
Formulas:
DHARIAN - 1 = [DATE]+14
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14