## DDR # 390
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 390
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-05-28
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4995 / 4945 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MUHAMMAD ISHAQ / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4770 | 4753.95 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 389.9792
RIG REP.: |  | TARIQ BUTT / KHALID JEELANI |  |  | MD/TVD @ 06:00HRS: |  | 4774 | 4757.52 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 3
2020-05-27 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | RUN NO. |  |  | 80 |  | BHA NO. |  |  | 99 | IN (M) |  | 4767 |  | OUT (M) |  |  | STRING (BBL) | 218.1
CHECK TIME | 10:00 | 23:59 | MD @ 00:00HR (M) |  | 4770 |  | BIT NO. |  |  | 34 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 753.7
DEPTH, MD (M) | 4767 | 4770 | TVD @ 00:00HR (M) |  | 4753.95 |  | SIZE (IN) |  |  | 6 |  | TCI BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 | 0.02 |  | PITS (BBL) | 567
MW IN (SG) | 1.6 | 1.6 | DAILY PROGRESS (M) |  | 3 |  | MANUFACTURER |  |  | BAKER |  | MUD MOTOR |  |  | 4.75 | 3.75 |  | 3 1/2 IF |  | 7.24 | 0.48121 |  | ACT. SYS (BBL) | 1538.8
MW OUT (SG) |  | 1.6 | INST. ROP (M/HR) |  | 0.96 |  | TYPE |  |  | STX-MS50DX2 |  | FLOAT SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.82 | 0.054502 |  | RESV. SYS (BBL) | 386
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 0.96774 |  | SERIAL NO. |  |  | 5307768 |  | LOWER SAVER SUB |  |  | 4.75 | 2.5 |  | 3 1/2 IF |  | 0.47 | 0.031239 |  | KILL MUD (BBL)
FL TEMP. °F |  | 118 | AVG. WOB (TON) |  | 5-6 |  | IADC CODE |  |  | 637 |  | SPSA |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 9.43 | 0.62677 |  | KILL MW (SG)
µ FUNNEL (SEC) | 68 | 75 | AVG. RPM SURFACE |  | 0 |  | NOZZLES (1/32") |  |  | 3 x 12/32 |  | PONY NMDC |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 4.5 | 0.29909 |  | TOTAL | 1924.8
PV | 32 | 33 | AVG. RPM DOWNHOLE |  | 111 |  | DEPTH IN (M) |  |  | 4767 |  | PBL SUB |  |  | 4.6875 | 2.25 |  | 3 1/2 IF |  | 3.06 | 0.20338 |  | DIESEL (LTR)
YIELD POINT | 26 | 26 | FLOWRATE (GPM) |  | 205 |  | DEPTH OUT (M) |  |  |  |  | 15 x HWDP |  |  | 3.5 | 2.0625 |  | 3 1/2 IF |  | 139.92 | 4.8498 |  | RIG TANK | 107018
GEL ST. | 12/14 | 13/17 | PRESSURE (PSI) |  | 2700-2900 |  | METERAGE (M) |  |  | 3 |  | HMD JAR |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.07 | 0.31438 |  | CAMP TANK | 16324
WL (ml/30 min) | 5.3 | 5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  | 0 |  | 12 x HWDP |  |  | 3.5 | 2.0625 |  | 3 1/2 IF |  | 112.9 | 3.9133 |  | CONSUMED | 4058
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  | 111 | [12 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) |  |  | 5-6 | [12 empty] | TOTAL | 123342
ALK (FILT.) | 0.3/1.1 | 0.3/1.1 | PICK-UP WT. (TON) |  | 155 |  | AVG. ROP (M/HR) |  |  | 0.96774 | [12 empty] | WATER (LTR)
pH | 10.5 | 10.5 | SLACK-OFF WT. (TON) |  | 143 |  | BIT ROT HRS. |  |  | 3.1 | [12 empty] | RIG STORAGE | 570963
DIESEL % | 0.5 | 0.6 | SLIMPULSE D & I OFF BIT - (M) |  | 10.22 |  | K-REVS IN 24 HRS |  |  | 20.65 | [12 empty] | CAMP STORAGE | 84000
KCl (%) | 4 | 4 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  | 20.65 | [12 empty] | CONSUMED | 102436
KCl (mg/l) | 38324.7 | 38706 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  | 59.2 | [12 empty] | RECEIVED | 42000
CHLORIDES (mg/l) | 72000 | 72600 | JAR | 13.37 |  |  | JET VELOCITY (M/SEC) |  |  | 60.62 | [12 empty] | DRL WASTE
HARDNESS (mg/l) | 250 | 200 | 3 1/2" HWDPS | 15.83 |  |  | TFA (IN²) |  |  | 0.3313 | [12 empty] | POB
PENETRAX % |  |  | PBL SUB | 0 |  |  | HSI |  |  | 2 |  | TOTAL LENGTH (M) | [7 empty] | 287.61 |  |  | MPCL | 4
MAX GUARD % |  |  | DAILY BHA ROT. HRS |  | 0 |  | MOTOR REV/GAL |  |  | 0.54 |  | BHA WT. IN MUD (TON) | [7 empty] | 8 |  |  | MPCL SERV | 19
SOLIDS % | 19.54 | 19.41 | DAILY ON BOTTOM HRS |  | 3.1 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 6 |  |  | SECURITY
M.B.T. (lb/bbl) | 3.8 | 3.8 | DAILY CIRC. HRS |  | 8.85 |  | BIT NO. 34 |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 63
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 11
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 25942000 | SHAKER-1 | 2 x 40 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [11 empty] | TOTAL | 122
DAILY WELL COST (US$) |  | 102449.406 | SHAKER-2 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 26444968.1826 | SHAKER-3 | 3 x 120 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | [11 empty] | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 101.9% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | [11 empty] | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | [11 empty] | MAASP (PSI) | 2704.3931
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.60 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4754 | 1050/1100/1080 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4754 | 1600/1640/1600 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | SHEAR BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4754 | 2180/2170/2160 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4775/4758.16
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4787 / 4768
TRIP DRILL | 2020-05-24 | 2020-06-23 | LAST BOP TEST DATE |  | 2020-05-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK | 4821 / 4796
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-06-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4857 / 4825
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-27
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43978 | 43978.0833 | 2 | DRL | PT-P | BHA | P/U & M/U NEW 6" TCI (637) BIT + MUD MOTOR + SPSA & INSTALLED MWD TOOL + PONY NMDC + PBL SUB. ADJUSTED MOTOR BEND TO 1.5 DEG & MEASURED TOOLFACE OFFSET.
43978.0833 | 43978.1354 | 1.25 | DRL | NPT-UP | E/C | ATTEMPTED TO FUNCTION TEST MWD TOOL. OBSERVED NOISY SIGNAL. TROUBLE SHOT THE SURFACE SYSTEM AND RELOCATED THE RJB TO REDUCE ELECTRICAL INTERFERENCE..
43978.1354 | 43978.1667 | 0.75 | DRL | PT-P | E/C | FUNCTION TESTED PBL SUB. PBL SUB DEACTIVATED AT 3800 PSI. RETRIEVED DART & BALLS FROM CATCHER SUB.
43978.1667 | 43978.1875 | 0.5 | DRL | PT-P | E/C | FUNCTION TESTED MWD - OK.
43978.1875 | 43978.2292 | 1 | DRL | PT-P | BHA | CONT'D RIH BHA DOWN TO 287M. FLUSHED BHA.
43978.2292 | 43978.6562 | 10.25 | DRL | PT-P | RIH | RIH FROM 287M TO 4477M. FILLED STRING EVERY 15 STDS. BROKE CIRCULATION AT 2010M.
43978.6562 | 43978.6875 | 0.75 | DRL | PT-P | RS | REPLACED TDS WASHPIPE AS PRECAUTIONARY MEASURE & P/T AT 2000 PSI.
43978.6875 | 43978.7083 | 0.5 | DRL | PT-P | RIH | CONT'D RIH FROM 4477M TO 4754M.
43978.7083 | 43978.7812 | 1.75 | DRL | PT-P | RW | RECORDED SCR. ADJUSTED TOOLFACE & WASHED DOWN TO 4767M.
43978.7812 | 43979 | 5.25 | DRL | PT-P | DM | STARTED DRILLING IN SLIDE MODE. DRILLED 6" HOLE FROM 4767M TO 4770M IN SLIDE MODE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-28
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43979 | 43979.25 | 6 | DRL | PT-P | DM | CONT'D DRILLING FROM 4770M TO 4774M IN SLIDE MODE & IS IN PROGRESS. SWEPT 10 BBL BRIDGEFORM PILL DURING DRILLING.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | DANDOT / SANDSTONE, CLAYSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH NEW 6" TCI BIT WITH DIRECTIONAL BHA DOWN TO 4767M. DRILLED 6" HOLE FROM 4767M TO 4770M IN SLIDE MODE.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 6" HOLE DOWN TO ±4777M. CIRCULATE & POOH TO SURFACE.
REMARKS
Formulas:
MIRAJ-1-ST-3 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14