## DDR # 391
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 391
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-05-29
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4995 / 4945 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MUHAMMAD ISHAQ / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4776.5 | 4759.5 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 390.9792
RIG REP.: |  | TARIQ BUTT / KHALID JEELANI |  |  | MD/TVD @ 06:00HRS: |  | 4776.5 | 4759.5 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 6.5
2020-05-28 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | RUN NO. |  |  | 80 |  | BHA NO. |  |  | 99 | IN (M) |  | 4767 |  | OUT (M) | 4776.5 |  | STRING (BBL) | 217.8
CHECK TIME | 11:00 | 23:59 | MD @ 00:00HR (M) |  | 4776.5 |  | BIT NO. |  |  | 34 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 754.8
DEPTH, MD (M) | 4767 | 4770 | TVD @ 00:00HR (M) |  | 4759.5 |  | SIZE (IN) |  |  | 6 |  | TCI BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 | 0.02 |  | PITS (BBL) | 612
MW IN (SG) | 1.6 | 1.55 | DAILY PROGRESS (M) |  | 6.5 |  | MANUFACTURER |  |  | BAKER |  | MUD MOTOR |  |  | 4.75 | 3.75 |  | 3 1/2 IF |  | 7.24 | 0.48121 |  | ACT. SYS (BBL) | 1584.6
MW OUT (SG) | 1.6 | 1.55 | INST. ROP (M/HR) |  | - |  | TYPE |  |  | STX-MS50DX2 |  | FLOAT SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.82 | 0.054502 |  | RESV. SYS (BBL) | 698
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 1.0156 |  | SERIAL NO. |  |  | 5307768 |  | LOWER SAVER SUB |  |  | 4.75 | 2.5 |  | 3 1/2 IF |  | 0.47 | 0.031239 |  | KILL MUD (BBL)
FL TEMP. °F |  | 120 | AVG. WOB (TON) |  | 5-8 |  | IADC CODE |  |  | 637 |  | SPSA |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 9.43 | 0.62677 |  | KILL MW (SG)
µ FUNNEL (SEC) | 76 | 65 | AVG. RPM SURFACE |  | 0 |  | NOZZLES (1/32") |  |  | 3 x 12/32 |  | PONY NMDC |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 4.5 | 0.29909 |  | TOTAL | 2282.6
PV | 34 | 29 | AVG. RPM DOWNHOLE |  | 111 |  | DEPTH IN (M) |  |  | 4767 |  | PBL SUB |  |  | 4.6875 | 2.25 |  | 3 1/2 IF |  | 3.06 | 0.20338 |  | DIESEL (LTR)
YIELD POINT | 28 | 26 | FLOWRATE (GPM) |  | 205 |  | DEPTH OUT (M) |  |  | 4776.5 |  | 15 x HWDP |  |  | 3.5 | 2.0625 |  | 3 1/2 IF |  | 139.92 | 4.8498 |  | RIG TANK | 126301
GEL ST. | 13/17 | 10/14 | PRESSURE (PSI) |  | 2900-3100 |  | METERAGE (M) |  |  | 9.5 |  | HMD JAR |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.07 | 0.31438 |  | CAMP TANK | 15771
WL (ml/30 min) | 4 | 3.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  | 0 |  | 12 x HWDP |  |  | 3.5 | 2.0625 |  | 3 1/2 IF |  | 112.9 | 3.9133 |  | CONSUMED | 9170
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  | 111 | [12 empty] | RECEIVED | 27900
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) |  |  | 5-8 | [12 empty] | TOTAL | 142072
ALK (FILT.) | 0.3/1.1 | 0.3/1.1 | PICK-UP WT. (TON) |  | 155 |  | AVG. ROP (M/HR) |  |  | 1 | [12 empty] | WATER (LTR)
pH | 10.5 | 10.5 | SLACK-OFF WT. (TON) |  | 143 |  | BIT ROT HRS. |  |  | 9.5 | [12 empty] | RIG STORAGE | 618900
DIESEL % | 0.8 | 3 | SLIMPULSE D & I OFF BIT - (M) |  | 10.22 |  | K-REVS IN 24 HRS |  |  | 42.62 | [12 empty] | CAMP STORAGE | 74000
KCl (%) | 5 | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  | 63.27 | [12 empty] | CONSUMED | 90763
KCl (mg/l) | 43854.1 | 43854.1 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  | 59.2 | [12 empty] | RECEIVED | 128700
CHLORIDES (mg/l) | 76000 | 76000 | JAR | 13.37 |  |  | JET VELOCITY (M/SEC) |  |  | 60.62 | [12 empty] | DRL WASTE
HARDNESS (mg/l) | 200 | 160 | 3 1/2" HWDPS | 15.83 |  |  | TFA (IN²) |  |  | 0.3313 | [12 empty] | POB
MAX SHIELD % | 0.8 | 3 | PBL SUB | 0 |  |  | HSI |  |  | 2 |  | TOTAL LENGTH (M) | [7 empty] | 287.61 |  |  | MPCL | 4
MAX GUARD % | 0.5 | 1 | DAILY BHA ROT. HRS |  | 0 |  | MOTOR REV/GAL |  |  | 0.54 |  | BHA WT. IN MUD (TON) | [7 empty] | 8 |  |  | MPCL SERV | 19
SOLIDS % | 19.24 | 17.77 | DAILY ON BOTTOM HRS |  | 6.4 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 6 |  |  | SECURITY
M.B.T. (lb/bbl) | 3.8 | 3.8 | DAILY CIRC. HRS |  | 23.8 |  | BIT NO. 34 |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 63
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 11
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 25942000 | SHAKER-1 | 2 x 40 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [11 empty] | TOTAL | 122
DAILY WELL COST (US$) |  | 74164.38 | SHAKER-2 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 26519132.5626 | SHAKER-3 | 3 x 120 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | [11 empty] | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 102.2% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | [11 empty] | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | [11 empty] | MAASP (PSI) | 3042.4423
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.60 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4754 | 1050/1100/1080 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4754 | 1600/1640/1600 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | SHEAR BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4754 | 2180/2170/2160 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4775/4758.16
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4787 / 4768
TRIP DRILL | 2020-05-24 | 2020-06-23 | LAST BOP TEST DATE |  | 2020-05-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK | 4821 / 4796
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-06-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4857 / 4825
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-28
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43979 | 43979.4688 | 11.25 | DRL | PT-P | DM | CONT'D DRILLING FROM 4770M TO 4776M IN SLIDE MODE. SWEPT 10 BBL BRIDGEFORM PILL DURING DRILLING. DURING DRILLING, P/U STRING INTERMITTENTLY TO CHECK STRING FREE. WHEN PICKED UP STRING AT 4776M, OBSERVED 50 TON OVERPULL AND STRING GOT FREE. CIRCULATED & RECIPROCATED STRING TO CLEAR HOLE.
43979.4688 | 43979.5104 | 1 | DRL | PT-P | DM | RESUMED DRILLING IN SLIDE MODE. DRILLED 6" HOLE FROM 4776M TO 4776.5M IN SLIDE MODE. P/U STRING TO CHECK, OBSERVED STRING DIFFERENTIALLY STUCK. APPLIED TORQUE & JARRED DOWNWARD, STRING GOT FREE.
43979.5104 | 43979.6667 | 3.75 | DRL | PT-P | CIR | CIRCULATED TO CLEAN HOLE. OBSERVED NO CAVING AT SHAKERS. SWEPT 10 BBL BRIDGEFORM PILL DURING CIRCULATION.
43979.6667 | 43980 | 8 | DRL | PT-P | CIR | CIRCULATED TO REDUCE MW (FROM 1.60 SG TO 1.55 SG) & CONDITION MUD.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-29
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43980 | 43980.1458 | 3.5 | DRL | PT-P | CIR | CIRCULATED TO HOMOGENIZE & CONDITION MUD.
43980.1458 | 43980.1562 | 0.25 | DRL | PT-P | FC | FLOW CHECK, WELL STATIC.
43980.1562 | 43980.25 | 2.25 | DRL | PT-P | POOH | POOH FROM 4776M TO 3900M & IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | DANDOT / SANDSTONE, CLAYSTONE
OPERATIONS AT 06:00 HRS |  |  | POOH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 6" HOLE FROM 4770M TO 4776.5M IN SLIDE MODE. P/U STRING TO CHECK, OBSERVED STRING DIFFERENTIALLY STUCK. APPLIED TORQUE & JARRED DOWNWARD, STRING GOT FREE. CIRCULATED TO CLEAN HOLE & CONT'D CIRCULATION TO REDUCE MW (FROM 1.60 SG TO 1.55 SG) & CONDITION MUD.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE. RIH WITH DIRECTIONAL BHA TO DRILL AHEAD.
REMARKS
Formulas:
MIRAJ-1-ST-3 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14
Note on I9: CMan.Rig3: Based on plan (No MWD Survey yet)