## DDR # 392
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [16 empty] | Report No. |  | 392
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [7 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-05-30
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [7 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4945 / 4910 METER | [7 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MUHAMMAD ISHAQ / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4776.5 | 4759.5 | [6 empty] | DAYS SINCE SPUD: | [6 empty] | 391.9792
RIG REP.: |  | TARIQ BUTT / KHALID JEELANI |  |  | MD/TVD @ 06:00HRS: |  | 4776.5 | 4759.5 | [6 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2020-05-29 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA | [5 empty] | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 81 |  | 80 | BHA NO. |  |  | 100 | IN (M) |  | 4776.5 |  | OUT (M) |  |  | STRING (BBL) | 55.4
CHECK TIME | 3:30 | 22:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 35 |  | 34 | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 976.7
DEPTH, MD (M) | 4776.5 | 4776.5 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 6 |  | 6 | TCI BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 | 0.02 |  | PITS (BBL) | 490
MW IN (SG) | 1.55 | 1.55 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | BAKER |  | BAKER | MUD MOTOR |  |  | 4.75 | 3.75 |  | 3 1/2 IF |  | 7.24 | 0.48121 |  | ACT. SYS (BBL) | 1522.1
MW OUT (SG) | 1.55 |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | STX-MS50DX2 |  | STX-MS50DX2 | FLOAT SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.82 | 0.054502 |  | RESV. SYS (BBL) | 739
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | 5307767 |  | 5307768 | ST. STAB |  |  | 5.75 | 2.25 |  | 3 1/2 IF |  | 1.41 | 0.093716 |  | KILL MUD (BBL)
FL TEMP. °F | 120 |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  | 637 |  | 637 | LOWER SAVER SUB |  |  | 4.75 | 2.5 |  | 3 1/2 IF |  | 0.47 | 0.031239 |  | KILL MW (SG)
µ FUNNEL (SEC) | 57 | 65 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3 x 12/32 |  | 3 x 12/32 | SPSA |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 9.43 | 0.62677 |  | TOTAL | 2261.1
PV | 29 | 30 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4776.5 |  | 4767 | PBL SUB |  |  | 4.6875 | 2.25 |  | 3 1/2 IF |  | 3.06 | 0.20338 |  | DIESEL (LTR)
YIELD POINT | 26 | 26 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | 4776.5 | 15 x HWDP |  |  | 3.5 | 2.0625 |  | 3 1/2 IF |  | 139.92 | 4.8498 |  | RIG TANK | 117667
GEL ST. | 11/13 | 12/14 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [5 empty] | HMD JAR |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.07 | 0.31438 |  | CAMP TANK | 15140
WL (ml/30 min) | 3.8 | 3.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [5 empty] | 12 x HWDP |  |  | 3.5 | 2.0625 |  | 3 1/2 IF |  | 112.9 | 3.9133 |  | CONSUMED | 9265
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [16 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [16 empty] | TOTAL | 132807
ALK (FILT.) | 0.3/1.1 | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [16 empty] | WATER (LTR)
pH | 10.5 | 10.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [16 empty] | RIG STORAGE | 638650
DIESEL % | 3 | 3 | SLIMPULSE D & I OFF BIT - (M) |  | 11.65 |  | K-REVS IN 24 HRS | [16 empty] | CAMP STORAGE | 81000
KCl (%) | 5 | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  |  |  | 63.27 | [11 empty] | CONSUMED | 82350
KCl (mg/l) | 43854.1 | 43854.1 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [16 empty] | RECEIVED | 109100
CHLORIDES (mg/l) | 76000 | 76000 | JAR | 13.37 | ST. STAB | 0 | JET VELOCITY (M/SEC) | [16 empty] | DRL WASTE
HARDNESS (mg/l) | 160 | 160 | 3 1/2" HWDPS | 15.83 |  |  | TFA (IN²) |  |  | 0.3313 |  | 0.3313 | [11 empty] | POB
MAX SHIELD % | 3 | 3 | PBL SUB | 0 |  |  | HSI | [5 empty] | TOTAL LENGTH (M) | [7 empty] | 284.52 |  |  | MPCL | 4
MAX GUARD % | 1 | 1 | DAILY BHA ROT. HRS |  | 0 |  | MOTOR REV/GAL |  |  | 0.54 |  |  | BHA WT. IN MUD (TON) | [7 empty] | 8 |  |  | MPCL SERV | 20
SOLIDS % | 17.77 | 17.77 | DAILY ON BOTTOM HRS |  | 0 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 6 |  |  | SECURITY
M.B.T. (lb/bbl) | 3.8 | 3.8 | DAILY CIRC. HRS |  | 4.45 |  | BIT NO. 34 |  |  | 1-3-WT-G-E-I-BT,CT,RG,SD-BHA |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 59
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA | [5 empty] | WELL DEVIATION DATA | [10 empty] | RIG SERV | 11
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) |  | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 29
APPROVED AFE (US$) |  | 25942000 | SHAKER-1 | 2 x 40 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | [12 empty] | TOTAL | 123
DAILY WELL COST (US$) |  | 41058.4575 | SHAKER-2 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [12 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 26560191.0201 | SHAKER-3 | 3 x 120 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | [12 empty] | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 102.4% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | [12 empty] | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | [12 empty] | MAASP (PSI) | 3042.4423
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [10 empty] | SLOW CIRCULATION RATE (1.55 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE |  | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" |  | 5555 | 97% |  | 0.0855 |  | 30 |  | 4763 | 1280/1260 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" |  | 5555 | 97% |  | 0.0855 |  | 40 |  | 4763 | 1680/1600 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | SHEAR BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" |  | 5555 | 97% |  | 0.0855 |  | 50 |  | 4763 | 2340/2320 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA | [5 empty] | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS | [5 empty] | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA
TRIP DRILL | 2020-05-24 | 2020-06-23 | LAST BOP TEST DATE |  | 2020-05-24 |  | OPR. HRS OF CENTRIFUGE-1 | [5 empty] | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-06-07 |  | OPR. HRS OF CENTRIFUGE-2 | [5 empty] | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-29
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43980 | 43980.1458 | 3.5 | DRL | PT-P | CIR | CIRCULATED TO HOMOGENIZE & CONDITION MUD.
43980.1458 | 43980.1562 | 0.25 | DRL | PT-P | FC | FLOW CHECK, WELL STATIC.
43980.1562 | 43980.3125 | 3.75 | DRL | PT-P | POOH | POOH FROM 4776M TO 3273M.
43980.3125 | 43980.3333 | 0.5 | DRL | NPT-P | RS | SERVICED TDS.
43980.3333 | 43980.5833 | 6 | DRL | PT-P | POOH | POOH FROM 3273M TO 315M. FLOW CHECK, WELL STATIC.
43980.5833 | 43980.625 | 1 | DRL | NPT-P | RS | CHANGED TDS GEAR OIL & OIL FILTER.
43980.625 | 43980.6875 | 1.5 | DRL | PT-P | BHA | POOH FROM 315M TO SURFACE. L/D JAR, BIT & PONY NMDC.
43980.6875 | 43980.75 | 1.5 | DRL | PT-P | BHA | P/U & M/U NEW 6" TCI (637) BIT WITH SAME MUD MOTOR & MWD. ADDED 1x ST. STAB. ADJUSTED MOTOR BEND TO 1.15 DEG & MEASURED TOOLFACE OFFSET.
43980.75 | 43980.7708 | 0.5 | DRL | PT-P | E/C | FUNCTION TESTED MWD - OK.
43980.7708 | 43980.8125 | 1 | DRL | PT-P | BHA | CONT'D RIH BHA DOWN TO 284M. FLUSHED BHA.
43980.8125 | 43980.9167 | 2.5 | DRL | PT-P | RIH | RIH FROM 284M TO 1458M. FILLED STRING EVERY 15 STDS.
43980.9167 | 43980.9479 | 0.75 | DRL | NPT-UP | RR | WORKED ON POWER TONG HPU OIL PUMP.
43980.9479 | 43981 | 1.25 | DRL | PT-P | RIH | RIH FROM 1458M TO 1978M. FILLED STRING EVERY 15 STDS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-30
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43981 | 43981.25 | 6 | DRL | PT-P | RIH | CONT'D RIH FROM 1978M TO 4531M & IS IN PROGRESS. BROKE CIRCULATION AT 2150M. FILLED STRING EVERY 15 STDS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | DANDOT / SANDSTONE, CLAYSTONE
OPERATIONS AT 06:00 HRS |  |  | RIH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CIRCULATED TO HOMOGENIZE & CONDITION MUD. POOH TO SURFACE. RIH NEW 6" TCI BIT WITH SAME MOTOR (BEND-1.15 DEG) & MWD DOWN TO 1978M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH DOWN TO BOTTOM. DRILL AHEAD 6" HOLE IN SLIDE & ROTARY MODE.
REMARKS
Formulas:
MIRAJ-1-ST-3 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14