## DDR # 393
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 393
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-05-31
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4945 / 4910 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MUHAMMAD ISHAQ / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4789 | 4771.17 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 392.9792
RIG REP.: |  | TARIQ BUTT / KHALID / FAYYAZ |  |  | MD/TVD @ 06:00HRS: |  | 4794.5 | 4776.15 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 12.5
2020-05-30 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | RUN NO. |  |  | 81 |  | BHA NO. |  |  | 100 | IN (M) |  | 4776.5 |  | OUT (M) |  |  | STRING (BBL) | 219.3
CHECK TIME | 11:00 | 23:59 | MD @ 00:00HR (M) |  | 4789 |  | BIT NO. |  |  | 35 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 754.1
DEPTH, MD (M) | 4779 | 4789 | TVD @ 00:00HR (M) |  | 4771.17 |  | SIZE (IN) |  |  | 6 |  | TCI BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 | 0.02 |  | PITS (BBL) | 561
MW IN (SG) | 1.55 | 1.55 | DAILY PROGRESS (M) |  | 12.5 |  | MANUFACTURER |  |  | BAKER |  | MUD MOTOR |  |  | 4.75 | 3.75 |  | 3 1/2 IF |  | 7.24 | 0.48121 |  | ACT. SYS (BBL) | 1534.4
MW OUT (SG) |  | 1.55 | INST. ROP (M/HR) |  | 1.49 |  | TYPE |  |  | STX-MS50DX2 |  | FLOAT SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.82 | 0.054502 |  | RESV. SYS (BBL) | 738
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 1.0322 |  | SERIAL NO. |  |  | 5307767 |  | ST. STAB |  |  | 5.75 | 2.25 |  | 3 1/2 IF |  | 1.41 | 0.093716 |  | KILL MUD (BBL)
FL TEMP. °F |  | 115 | AVG. WOB (TON) |  | 6/5 |  | IADC CODE |  |  | 637 |  | LOWER SAVER SUB |  |  | 4.75 | 2.5 |  | 3 1/2 IF |  | 0.47 | 0.031239 |  | KILL MW (SG)
µ FUNNEL (SEC) | 74 | 62 | AVG. RPM SURFACE |  | 0/25 |  | NOZZLES (1/32") |  |  | 3 x 12/32 |  | SPSA |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 9.43 | 0.62677 |  | TOTAL | 2272.4
PV | 32 | 30 | AVG. RPM DOWNHOLE |  | 111/136 |  | DEPTH IN (M) |  |  | 4776.5 |  | PBL SUB |  |  | 4.6875 | 2.25 |  | 3 1/2 IF |  | 3.06 | 0.20338 |  | DIESEL (LTR)
YIELD POINT | 27 | 27 | FLOWRATE (GPM) |  | 205 |  | DEPTH OUT (M) |  |  |  |  | 15 x HWDP |  |  | 3.5 | 2.0625 |  | 3 1/2 IF |  | 139.92 | 4.8498 |  | RIG TANK | 111250
GEL ST. | 13/15 | 11/13 | PRESSURE (PSI) |  | 2800-2900 |  | METERAGE (M) |  |  | 12.5 |  | HMD JAR |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.07 | 0.31438 |  | CAMP TANK | 14513
WL (ml/30 min) | 3.8 | 3.6 | TORQ. ON-BTM (KLB-FT) |  | 1-2 |  | RPM SURF. |  |  | 0/25 |  | 12 x HWDP |  |  | 3.5 | 2.0625 |  | 3 1/2 IF |  | 112.9 | 3.9133 |  | CONSUMED | 7044
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 0-1 |  | RPM BTM. |  |  | 111/136 | [12 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  | 145 |  | WOB (TON) |  |  | 6/5 | [12 empty] | TOTAL | 125763
ALK (FILT.) | 0.3/1.1 | 0.3/1.1 | PICK-UP WT. (TON) |  | 160 |  | AVG. ROP (M/HR) |  |  | 1.0322 | [12 empty] | WATER (LTR)
pH | 10.5 | 10.5 | SLACK-OFF WT. (TON) |  | 140 |  | BIT ROT HRS. |  |  | 12.11 | [12 empty] | RIG STORAGE | 634025
DIESEL % | 3 | 3 | SLIMPULSE D & I OFF BIT - (M) |  | 11.65 |  | K-REVS IN 24 HRS |  |  | 121.6278 | [12 empty] | CAMP STORAGE | 85000
KCl (%) | 5 | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  | 121.6278 | [12 empty] | CONSUMED | 81825
KCl (mg/l) | 43854.1 | 44807.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  | 54 | [12 empty] | RECEIVED | 81200
CHLORIDES (mg/l) | 76000 | 77300 | JAR | 18.63 | ST. STAB | 5.26 | JET VELOCITY (M/SEC) |  |  | 60.62 | [12 empty] | DRL WASTE
HARDNESS (mg/l) | 160 | 160 | 3 1/2" HWDPS | 21.09 |  |  | TFA (IN²) |  |  | 0.3313 | [12 empty] | POB
MAX SHIELD % | 3 | 3 | PBL SUB | 5.26 |  |  | HSI |  |  | 1.93 |  | TOTAL LENGTH (M) | [7 empty] | 284.52 |  |  | MPCL | 4
MAX GUARD % | 1 | 1 | DAILY BHA ROT. HRS |  | 5.26 |  | MOTOR REV/GAL |  |  | 0.54 |  | BHA WT. IN MUD (TON) | [7 empty] | 8 |  |  | MPCL SERV | 27
SOLIDS % | 17.77 | 17.92 | DAILY ON BOTTOM HRS |  | 12.11 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 6 |  |  | SECURITY
M.B.T. (lb/bbl) | 3.8 | 3.8 | DAILY CIRC. HRS |  | 17.08 |  | BIT NO. 35 |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 60
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 11
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 29
APPROVED AFE (US$) |  | 25942000 | SHAKER-1 | 2 x 40 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4776.86/4760.14 |  | 25.13 |  | 308.53 |  |  | 19.46 |  | MWD |  | TOTAL | 131
DAILY WELL COST (US$) |  | 38650.4 | SHAKER-2 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 26598841.4201 | SHAKER-3 | 3 x 120 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | [11 empty] | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 102.5% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | [11 empty] | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | [11 empty] | MAASP (PSI) | 3042.4423
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.55 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4763 | 1280/1260 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4763 | 1680/1600 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | SHEAR BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4763 | 2340/2320 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4778/4761.10
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4791/4772.98
TRIP DRILL | 2020-05-24 | 2020-06-23 | LAST BOP TEST DATE |  | 2020-05-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-06-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-30
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43981 | 43981.2708 | 6.5 | DRL | PT-P | RIH | CONT'D RIH FROM 1978M TO 4760M. BROKE CIRCULATION AT 2150M. FILLED STRING EVERY 15 STDS.
43981.2708 | 43981.2917 | 0.5 | DRL | PT-P | RW | WASHED DOWN LAST STAND DOWN TO 4776.5M.
43981.2917 | 43981.7812 | 11.75 | DRL | PT-P | DM | SET TOOLFACE & RESUMED DRILLING. DRILLED 6" HOLE FROM 4776.5M TO 4784M IN SLIDE MODE. P/U STRING INTERMITTENTLY DURING DRILLING TO CHECK FREE. MARKED TOP OF BAGHANWALA FORMATION AT 4778M.
43981.7812 | 43981.9792 | 4.75 | DRL | PT-P | DM | CONT'D DRILLING FROM 4784M TO 4789M IN ROTARY MODE.
43981.9792 | 43982 | 0.5 | DRL | NPT-UP | S | ATTEMPTED TO RECORD MWD SURVEY THRICE, NO SUCCESS DUE TO NOSIY SINGLE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-05-31
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43982 | 43982.25 | 6 | DRL | PT-P | DM | CONT'D DRILLING FROM 4789M TO 4794.5M & IS IN PROGRESS. SWEPT 10 BBL BRIDGEFORM PILL & RECORDED SUCCESSFUL MWD SURVEY AFTER CONNECTION. MARKED TOP OF JUTANA FORMATION AT 4791M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | JUTANA / DOLOMITE, SANDSTONE, CLAYSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH FROM 1978M TO 4776.5M. DRILLED FROM 4776.5M TO 4784M IN SLIDE MODE & FROM 4784M TO 4789M IN ROTARY MODE.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 6" HOLE DOWN TO 4800M. POOH TO SURFACE FOR BHA CHANGE.
REMARKS
Formulas:
MIRAJ-1-ST-3 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14
Note on K30: CMan.Rig3: ON & OFF BOTTOM