## DDR # 397
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 397
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1-ST-3 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2020-06-04
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | ± 4945 / 4910 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MUHAMMAD ISHAQ / ADNAN MANZOOR |  |  | MD/TVD @ 00:00HRS: |  | 4918 | 4885.16 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 396.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4928 | 4894.6 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 58
2020-06-03 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 6 |  | RUN NO. |  |  | 82 |  | BHA NO. |  |  | 100 | IN (M) |  | 4797 |  | OUT (M) |  |  | STRING (BBL) | 226.7
CHECK TIME | 10:00 | 23:59 | MD @ 00:00HR (M) |  | 4918 |  | BIT NO. |  |  | 36 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 758.5
DEPTH, MD (M) | 4884 | 4918 | TVD @ 00:00HR (M) |  | 4885.16 |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 | 0.02 |  | PITS (BBL) | 510
MW IN (SG) | 1.55 | 1.55 | DAILY PROGRESS (M) |  | 58 |  | MANUFACTURER |  |  | SMITH |  | MUD MOTOR |  |  | 4.75 | 3.75 |  | 3 1/2 IF |  | 7.1 | 0.4719 |  | ACT. SYS (BBL) | 1495.2
MW OUT (SG) | 1.55 | 1.55 | INST. ROP (M/HR) |  | 2.3 |  | TYPE |  |  | XZ516 |  | FLOAT SUB |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 0.82 | 0.054502 |  | RESV. SYS (BBL) | 818
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 2.6667 |  | SERIAL NO. |  |  | JM9047 |  | ST. STAB |  |  | 5.75 | 2.25 |  | 3 1/2 IF |  | 1.41 | 0.093716 |  | KILL MUD (BBL)
FL TEMP. °F |  | 127 | AVG. WOB (TON) |  | 3-5 |  | IADC CODE |  |  |  |  | LOWER SAVER SUB |  |  | 4.75 | 2.5 |  | 3 1/2 IF |  | 0.47 | 0.031239 |  | KILL MW (SG)
µ FUNNEL (SEC) | 56 | 54 | AVG. RPM SURFACE |  | 30-40 |  | NOZZLES (1/32") |  |  | 3 x 12/32 |  | SPSA |  |  | 4.75 | 3.25 |  | 3 1/2 IF |  | 9.43 | 0.62677 |  | TOTAL | 2313.2
PV | 30 | 31 | AVG. RPM DOWNHOLE |  | 254-264 |  | DEPTH IN (M) |  |  | 4797 |  | PBL SUB |  |  | 4.6875 | 2.25 |  | 3 1/2 IF |  | 3.06 | 0.20338 |  | DIESEL (LTR)
YIELD POINT | 25 | 26 | FLOWRATE (GPM) |  | 216 |  | DEPTH OUT (M) |  |  |  |  | 15 x HWDP |  |  | 3.5 | 2.0625 |  | 3 1/2 IF |  | 139.92 | 4.8498 |  | RIG TANK | 84783
GEL ST. | 10/13 | 11/15 | PRESSURE (PSI) |  | 2850-3000 |  | METERAGE (M) |  |  | 121 |  | HMD JAR |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.07 | 0.31438 |  | CAMP TANK | 32841
WL (ml/30 min) | 3.6 | 3.6 | TORQ. ON-BTM (KLB-FT) |  | 2-4 |  | RPM SURF. |  |  | 30-40 |  | 12 x HWDP |  |  | 3.5 | 2.0625 |  | 3 1/2 IF |  | 112.9 | 3.9133 |  | CONSUMED | 8552
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 2-3 |  | RPM BTM. |  |  | 254-264 | [12 empty] | RECEIVED | 21000
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  | 152 |  | WOB (TON) |  |  | 3-5 | [12 empty] | TOTAL | 117624
ALK (FILT.) | 0.3/1.1 | 0.3/1.1 | PICK-UP WT. (TON) |  | 160 |  | AVG. ROP (M/HR) |  |  | 2.477 | [12 empty] | WATER (LTR)
pH | 10.5 | 10.5 | SLACK-OFF WT. (TON) |  | 146 |  | BIT ROT HRS. |  |  | 48.85 | [12 empty] | RIG STORAGE | 636400
DIESEL % | 3 | 3 | SLIMPULSE D & I OFF BIT - (M) |  | 14.84 |  | K-REVS IN 24 HRS |  |  | 339.17 | [12 empty] | CAMP STORAGE | 83000
KCl (%) | 5 | 5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  | 732.77 | [12 empty] | CONSUMED | 56500
KCl (mg/l) | 43854.1 | 43854.1 | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  | 56.8 | [12 empty] | RECEIVED | 100000
CHLORIDES (mg/l) | 76300 | 76000 | JAR | 69.41 | ST. STAB | 56.04 | JET VELOCITY (M/SEC) |  |  | 63.81 | [12 empty] | DRL WASTE | 92800
HARDNESS (mg/l) | 160 | 160 | 3 1/2" HWDPS | 71.87 |  |  | TFA (IN²) |  |  | 0.3313 | [12 empty] | POB
MAX SHIELD % | 3 | 3 | PBL SUB | 56.04 |  |  | HSI |  |  | 2.26 |  | TOTAL LENGTH (M) | [7 empty] | 284.38 |  |  | MPCL | 4
MAX GUARD % | 1 | 1 | DAILY BHA ROT. HRS |  | 23.16 |  | MOTOR REV/GAL |  |  | 1.04 |  | BHA WT. IN MUD (TON) | [7 empty] | 8 |  |  | MPCL SERV | 25
SOLIDS % | 17.97 | 17.99 | DAILY ON BOTTOM HRS |  | 21.75 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 6 |  |  | SECURITY
M.B.T. (lb/bbl) | 3.8 | 3.8 | DAILY CIRC. HRS |  | 23.48 |  | BIT NO. 36 |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 63
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 15
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 29
APPROVED AFE (US$) |  | 25942000 | SHAKER-1 | 2 x 40 + 1 x 60 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4789.84/4771.86 |  | 25.4 |  | 303.78 |  |  | 6.58 |  | MWD |  | TOTAL | 136
DAILY WELL COST (US$) |  | 46580.43 | SHAKER-2 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4805.15/4785.60 |  | 26.66 |  | 309.07 |  |  | 5.17 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 26800817.9501 | SHAKER-3 | 3 x 120 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 / 4391 (WND) | 4830.50/4808.18 |  | 27.54 |  | 319.41 |  |  | 5.66 |  | MWD |  | LAST CSG SIZE | 7"
% OF AFE SPENT |  | 103.3% | MUD CLEANER | 3 x 170 |  |  | 7'' LINER- ST1 (VM140HC, 32#, VT) |  |  |  | 4815 / 3397 (TOL) | 4858.57/4832.99 |  | 28.21 |  | 318.25 |  |  | 0.92 |  | MWD |  | FIT (EMW) | 2
[7 empty] | ST-2 IN 7'' LINER |  |  |  | 4759 (WND) | 4887.52/4858.40 |  | 29.03 |  | 316.05 |  |  | 1.38 |  | MWD |  | MAASP (PSI) | 3042.4423
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.55 SG) | [5 empty] | KICK TOL. (BBL)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4904 | 1140/1140 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4904 | 1550/1550 |  |  | HANGU | 4740/4726.58
FIRE DRILL | 2020-04-15 | 2020-05-15 | SHEAR BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5" |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4904 | 2100/2120 |  |  | DANDOT | 4753/4738.56
PIT DRILL |  |  | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | BAGHANWALA | 4778/4761.10
KICK DRILL | 2020-02-12 | 2020-03-13 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | JUTANA | 4791/4772.98
TRIP DRILL | 2020-05-24 | 2020-06-23 | LAST BOP TEST DATE |  | 2020-05-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | KUSSAK | 4827/4805.17
STRETCHER DRILL | 2020-04-15 | 2020-05-15 | NEXT BOP TEST DATE |  | 2020-06-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | KHEWRA | 4882/4853.60
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-06-03
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43985 | 43986 | 24 | DRL | PT-P | DM | DRILLED 6" HOLE FROM 4860M TO 4918M IN ROTARY MODE. SWEPT 10 BBL BRIDGEFORM PILL DURING DRILLING. RECORDED MWD SURVEY AT 4873 & 4902M. (AVG ROP - 2.78 M/H). MARKED TOP OF KHEWRA FORMATION AT 4882M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-06-04
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43986 | 43986.25 | 6 | DRL | PT-P | DM | DRILLED 6" HOLE FROM 4918M TO 4928M IN ROTARY MODE & IS IN PROGRESS. (AVG ROP - 2.09 M/H)
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KHEWRA / SANDSTONE, CLAYSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 6" HOLE FROM 4860M TO 4918M IN ROTARY MODE.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 6" HOLE AS PER PLAN.
REMARKS
Formulas:
MIRAJ-1-ST-3 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14